## Sitelist
NO | AREA | REGIONAL NAME | REGIONAL_ID | SITE ID | SITE ID BARU | PID | Regional | PID Sales1 | PID Sales2 | True PID | New PID 2026 | SITE NAME | Longitude | Latitude | Status MKT | MKT | Tanggal MKT | SoW Actual | Mitra TP | Proposed Mitra Area | Mitra Pleno |  | TP GROUP | SLD Update | ELD Update | ELD+3 Bulan | RFI | Aging SLA | SLA Category | YEAR PLAN CAT | X | Deatail Status | Tipe Rescoping | General Status | Status Akhir | Summary Progress | Remark Akhir | Target RFI | SOW | Type site | Type Tower | Tinggi Tower | remarks
1 | Area 1 | R01 Sumbagut | 1 | LBP319 | LBP319 | 24TS08Z0008 | R01 Sumbagut | 0 | 24TS08Z0008 | 24TS08Z0008 | #N/A | MC JL PAHLAWAN MORAWA | 98.772 | 3.5242 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2014-09-11 | 2024-09-10 | 2024-12-09 | 2024-11-11 | 28 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
2 | Area 1 | R01 Sumbagut | 1 | LBP314 | LBP314 | 25TS09C0001 | R01 Sumbagut | 24TS08Z0009 | 24TS08Z0009 | 25TS09C0001 | #N/A | MCLUCKYSWALAYAN | 98.7795 | 3.5229 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2014-10-24 | 2024-10-23 | 2025-01-21 | 2025-04-29 | -98 | Out SLA | Plan ≤ 2025 | #N/A | 03.RFI |  | RFI | RFI | RFI | Aktual Colo wait Transport, Pemindahan PLN setelah perangkat ready | done
3 | Area 1 | R01 Sumbagut | 1 | LBP315 | LBP315 | 24TS08Z0010 | R01 Sumbagut | 24TS08Z0010 | 24TS08Z0010 | 24TS08Z0010 | #N/A | MCTOLTJMORAWA | 98.7762 | 3.5243 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2014-10-24 | 2024-10-23 | 2025-01-21 | 2025-11-30 | -313 | Out SLA | Plan ≤ 2025 | #N/A | 03.RFI |  | RFI | RFI | RFI | Aktual B2R wait Relok | done
4 | Area 1 | R01 Sumbagut | 1 | LBP320 | LBP320 |  | R01 Sumbagut | 0 | #N/A | NY | #N/A | MC SOSRO | 98.7883 | 3.5215 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2014-10-24 | 2024-10-23 | 2025-01-21 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
5 | Area 1 | R01 Sumbagut | 1 | LBP317 | LBP317 | 24TS02Z0034 | R01 Sumbagut | 0 | 24TS02Z0034 | 24TS02Z0034 | #N/A | MCLIMAUMANIS | 98.7737 | 3.5162 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-12-10 | 2023-12-09 | 2024-03-08 | 2024-07-17 | -131 | Out SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
6 | Area 1 | R01 Sumbagut | 1 | LBP318 | LBP318 | 24TS02Z0035 | R01 Sumbagut | 0 | 24TS02Z0035 | 24TS02Z0035 | #N/A | MCPASAR14 | 98.7707 | 3.5089 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-12-10 | 2023-12-09 | 2024-03-08 | 2024-07-19 | -133 | Out SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
7 | Area 1 | R01 Sumbagut | 1 | LBP321 | LBP321 | 24TS02Z0036 | R01 Sumbagut | 0 | 24TS02Z0036 | 24TS02Z0036 | #N/A | MCPASARTJMORAWA2 | 98.7918 | 3.5163 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-12-10 | 2023-12-09 | 2024-03-08 | 2024-10-25 | -231 | Out SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
8 | Area 1 | R01 Sumbagut | 1 | LBP323 | LBP323 | 24TS02Z0037 | R01 Sumbagut | 0 | 24TS02Z0037 | 24TS02Z0037 | #N/A | MCKIMMORAWA | 98.8073 | 3.5294 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-12-10 | 2023-12-09 | 2024-03-08 | 2024-12-20 | -287 | Out SLA | Plan ≤ 2025 | #N/A | 03.RFI |  | RFI | RFI | RFI |  | done
9 | Area 1 | R01 Sumbagut | 1 | LBP325 | LBP325 |  | R01 Sumbagut | 0 | 24TS02Z0038 | 24TS02Z0038 | #N/A | MCLIMAUMUNGKUR | 98.7907 | 3.5046 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-12-10 | 2023-12-09 | 2024-03-08 | 2024-07-08 | -122 | Out SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
10 | Area 1 | R01 Sumbagut | 1 | LBP316 | LBP316 |  | R01 Sumbagut | 0 | #N/A | NY | #N/A | MCPASAR12 | 98.7792 | 3.5189 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-12-10 | 2023-12-09 | 2024-03-08 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
11 | Area 1 | R01 Sumbagut | 1 | LBP322 | LBP322 | 24TS11Z0003 | R01 Sumbagut | 24TS11Z0003 | 24TS11Z0003 | 24TS11Z0003 | #N/A | MCPASARTJMORAWA | 98.7915 | 3.5195 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-12-10 | 2023-12-09 | 2024-03-08 | 2025-04-29 | -417 | Out SLA | Plan ≤ 2025 | #N/A | 03.RFI |  | RFI | RFI | RFI |  | done
12 | Area 1 | R01 Sumbagut | 1 | LBP324 | LBP324 | 25TS06N0352 | R01 Sumbagut | 0 | #N/A | 25TS06N0352 | #N/A | MCBATANGKUIS | 98.7838 | 3.5444 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-12-10 | 2023-12-09 | 2024-03-08 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
13 | Area 1 | R01 Sumbagut | 1 | BJI156 | BJI156 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0072 | MCSUKARNOHATTADMT | 98.52 | 3.6077 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT WINER INSAN SUKSES HUTAMA |  | Mitratel | 2016-05-01 | 2026-04-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-6 | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to Mini Macro |  | BTR
14 | Area 1 | R01 Sumbagut | 1 | BJI164 | BJI164 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0068 | MCAMIRHAMZAHDMT | 98.5095 | 3.6288 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT M JUSUF & SONS |  | Mitratel | 2016-05-01 | 2026-04-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-6 | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
15 | Area 1 | R01 Sumbagut | 1 | BJI181 | BJI181 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0070 | MCPERINTISKEMERDEKAAN2DMT | 98.4892 | 3.634 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT EDTIM NATAMA PERSADA |  | Mitratel | 2016-05-01 | 2026-04-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 9 RRU Remove 6 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower
16 | Area 1 | R01 Sumbagut | 1 | BJI188 | BJI188 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0074 | MCAMIRHAMZAH2DMT | 98.4974 | 3.6159 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT ANTONIO JAYA ABADI |  | Mitratel | 2016-05-01 | 2026-04-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 8 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
17 | Area 1 | R01 Sumbagut | 1 | BJI201 | BJI201 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0071 | MCSAMAHUDIDMT | 98.4785 | 3.5897 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT EDTIM NATAMA PERSADA |  | Mitratel | 2016-05-01 | 2026-04-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower
18 | Area 1 | R01 Sumbagut | 1 | BJI205 | BJI205 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0075 | MCSAMAHUDI2DMT | 98.4788 | 3.5955 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT WINER INSAN SUKSES HUTAMA |  | Mitratel | 2016-05-01 | 2026-04-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower
19 | Area 1 | R01 Sumbagut | 1 | BJI208 | BJI208 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0056 | MCGATSUDMT | 98.4734 | 3.6069 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT ANTONIO JAYA ABADI |  | Mitratel | 2016-05-01 | 2026-04-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 4 RF Add 7 RRU Remove 7 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
20 | Area 1 | R01 Sumbagut | 1 | BJI209 | BJI209 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0087 | MCBINJAIKUALADMT | 98.4484 | 3.6056 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT ANTONIO JAYA ABADI |  | Mitratel | 2016-05-01 | 2026-04-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
21 | Area 1 | R01 Sumbagut | 1 | BJI210 | BJI210 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0077 | MCSIMPANGKAPTMUSLIMDMT | 98.4929 | 3.6092 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT MADYA PERDANA PRIMA |  | Mitratel | 2016-05-01 | 2026-04-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower
22 | Area 1 | R01 Sumbagut | 1 | MDN993 | MDN993 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0081 | SARI REJO 2 | 98.676 | 3.5521 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT M JUSUF & SONS |  | Mitratel | 2016-05-23 | 2026-05-22 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 3 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to Mini Macro |  | BTR
23 | Area 1 | R01 Sumbagut | 1 | LBP410 | LBP410 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0076 | MCMTHARYONODMT | 98.5102 | 3.6431 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT ANTONIO JAYA ABADI |  | Mitratel | 2016-05-01 | 2026-04-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 9 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
24 | Area 1 | R01 Sumbagut | 1 | LBP411 | LBP411 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0083 | MCROADTOSIMPMEGAWATIDMT | 98.51 | 3.6546 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT ANTONIO JAYA ABADI |  | Mitratel | 2016-05-01 | 2026-04-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 5 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
25 | Area 1 | R01 Sumbagut | 1 | MDN730 | MDN730 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0079 | PERUM TNI AU KARANG SARI-I | 98.6814 | 3.5456 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT MEDCOMM SOLUTION |  | Mitratel | 2016-05-23 | 2026-05-22 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to Mini Macro |  | BTR
26 | Area 1 | R01 Sumbagut | 1 | MDN757 | MDN757 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0080 | MAWAR SARI REJO | 98.6749 | 3.5447 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT M JUSUF & SONS |  | Mitratel | 2016-05-23 | 2026-05-22 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
27 | Area 1 | R01 Sumbagut | 1 | MDX510 | MDX510 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0064 | MC KIM BELAWAN-9 | 98.7029 | 3.6815 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT RAMOS KARYA MANDIRI |  | Mitratel | 2016-11-11 | 2026-11-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 6 RF Add 8 RRU Remove 11 RRU Final Sow Rescope: 1. B2R to Mini Macro |  | BTR
28 | Area 1 | R01 Sumbagut | 1 | BJI175 | BJI175 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0073 | MCMTHARYONO2DMT | 98.4953 | 3.6401 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT ANTONIO JAYA ABADI |  | Mitratel | 2016-06-07 | 2026-06-06 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 5 RF Add 7 RRU Remove 7 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
29 | Area 1 | R01 Sumbagut | 1 | BJI212 | BJI212 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0078 | MCSMRAJADMT | 98.5022 | 3.6129 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT MADYA PERDANA PRIMA |  | Mitratel | 2016-06-07 | 2026-06-06 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to Mini Macro |  | BTR
30 | Area 1 | R01 Sumbagut | 1 | MDN758 | MDN758 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0060 | SARI REJO 3 | 98.6677 | 3.5476 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT KONCERFO SUKSES CEMERLANG |  | Mitratel | 2016-08-14 | 2026-08-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 12 RRU Remove 12 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
31 | Area 1 | R01 Sumbagut | 1 | MDX144 | MDX144 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0091 | MC BELAWAN-4 | 98.7022 | 3.7858 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT TANATO MAKMUR LESTARI |  | Mitratel | 2016-08-14 | 2026-08-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 11 RRU Remove 9 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
32 | Area 1 | R01 Sumbagut | 1 | BJI211 | BJI211 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0088 | MCAMIRHAMZAH3DMT | 98.4989 | 3.6132 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT ANTONIO JAYA ABADI |  | Mitratel | 2016-09-01 | 2026-08-31 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 8 RRU Remove 9 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
33 | Area 1 | R01 Sumbagut | 1 | MDX276 | MDX276 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0062 | MC BELAWAN-9 | 98.6782 | 3.7708 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT RAMOS KARYA MANDIRI |  | Mitratel | 2016-09-13 | 2026-09-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 5 RF Add 5 RRU Remove 5 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
34 | Area 1 | R01 Sumbagut | 1 | BJI213 | BJI213 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0089 | MCPALEMBANGDMT | 98.4895 | 3.599 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT ANTONIO JAYA ABADI |  | Mitratel | 2016-09-28 | 2026-09-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
35 | Area 1 | R01 Sumbagut | 1 | MDX016 | MDX016 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0084 | MC BELAWAN-3 | 98.7071 | 3.7798 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT TANATO MAKMUR LESTARI |  | Mitratel | 2016-10-05 | 2026-10-04 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 9 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
36 | Area 1 | R02 Sumbagsel | 2 | OKI275 | OKI275 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | REKTORAT UNSRI | 104.646 | -3.2191 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-04-08 | 2026-04-07 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | [7 empty] | Terminate
37 | Area 1 | R01 Sumbagut | 1 | MDX028 | MDX028 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0085 | MC BELAWAN-6 | 98.6824 | 3.7868 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT KONCERFO SUKSES CEMERLANG |  | Mitratel | 2016-10-05 | 2026-10-04 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 6 RF Add 12 RRU Remove 9 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
38 | Area 1 | R01 Sumbagut | 1 | MDX048 | MDX048 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0086 | MC BELAWAN-10 | 98.6758 | 3.7674 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT MEDCOMM SOLUTION |  | Mitratel | 2016-10-05 | 2026-10-04 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 6 RF Add 9 RRU Remove 9 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
39 | Area 1 | R01 Sumbagut | 1 | MDX502 | MDX502 |  | R01 Sumbagut | #N/A | #N/A | NY | #N/A | MC KIM BELAWAN-3 | 98.6985 | 3.6633 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-11-11 | 2026-11-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 9 RRU Remove 6 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower
40 | Area 1 | R01 Sumbagut | 1 | MDX504 | MDX504 |  | R01 Sumbagut | #N/A | #N/A | NY | #N/A | MC KIM BELAWAN-5 | 98.6888 | 3.6724 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-11-11 | 2026-11-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 9 RRU Remove 8 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower
41 | Area 1 | R02 Sumbagsel | 2 | BDL407 | BDL407 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | POLE FAK MIPAUNILAH | 105.2442 | -5.3663 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-08-30 | 2026-08-29 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | [7 empty] | One leg 18m
42 | Area 2 | R03 Jabotabek Inner | 3 | JBX077 | JBX077 | 25TS08N2053 | Jabat | 0 | #N/A | 25TS08N2053 | #N/A | PURIBETAUTARA | 106.7243 | -6.2237 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-08 | 2025-09-07 | 2025-12-06 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
43 | Area 1 | R01 Sumbagut | 1 |  | MDX509 |  | R01 Sumbagut | #N/A | #N/A | NY | #N/A | DMT_MC KIM Belawan-8 | 98.7085 | 3.6669 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-11-11 | 2026-11-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 9 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
44 | Area 1 | R01 Sumbagut | 1 | MDX508 | MDX508 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0066 | MC KIM BELAWAN-14 | 98.6864 | 3.662 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT RAMOS KARYA MANDIRI |  | Mitratel | 2017-01-18 | 2027-01-17 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 9 RRU Remove 6 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower
45 | Area 1 | R01 Sumbagut | 1 | MDX506 | MDX506 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0065 | MC KIM BELAWAN-13 | 98.6796 | 3.6647 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT RAMOS KARYA MANDIRI |  | Mitratel | 2017-03-14 | 2027-03-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to Mini Macro |  | BTR
46 | Area 1 | R01 Sumbagut | 1 | MDX035 | MDX035 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0090 | MC BELAWAN-7 | 98.6857 | 3.78 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT RAMOS KARYA MANDIRI |  | Mitratel | 2017-08-28 | 2027-08-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to MCP |  | BTR
47 | Area 1 | R01 Sumbagut | 1 | MDN906 | MDN906 | #N/A | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0061 | TASBIH SELATAN | 98.6358 | 3.5633 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | GAMETRACO | #N/A | PT TRANSDATA SATKOMINDO |  | Mitratel | 2016-04-20 | 2026-04-19 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to Mini Macro |  | BTR
48 | Area 1 | R01 Sumbagut | 1 | MDN051 | MDN051 | #N/A | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0058 | TASBIH UTARA | 98.6292 | 3.5688 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | GAMETRACO | #N/A | PT TRANSDATA SATKOMINDO |  | Mitratel | 2016-04-20 | 2026-04-19 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to Mini Macro |  | BTR
49 | Area 1 | R01 Sumbagut | 1 | MDX025 | MDX025 | #N/A | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0069 | MASJID TASBIH | 98.6364 | 3.5681 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | GAMETRACO | #N/A | PT TRANSDATA SATKOMINDO |  | Mitratel | 2016-04-24 | 2026-04-23 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to Mini Macro |  | BTR
50 | Area 1 | R01 Sumbagut | 1 | MDN938 | MDN938 | #N/A | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0059 | TASBIH 4 | 98.6307 | 3.5648 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | GAMETRACO | #N/A | PT TRANSDATA SATKOMINDO |  | Mitratel | 2016-04-30 | 2026-04-29 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to Mini Macro |  | BTR
51 | Area 1 | R01 Sumbagut | 1 | MDX014 | MDX014 | #N/A | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0057 | TASBIH 5 | 98.6328 | 3.5712 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | GAMETRACO | #N/A | PT TRANSDATA SATKOMINDO |  | Mitratel | 2016-04-30 | 2026-04-29 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to Mini Macro |  | BTR
52 | Area 1 | R02 Sumbagsel | 2 | PLG608 | PLG608 |  | R02 Sumbagsel | 0 | 24TS03N0146 | 24TS03N0146 | #N/A | KEMUNING POLDA PH1 | 104.7353 | -2.9648 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-02-19 | 2025-02-18 | 2025-05-19 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 11.Hold |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
53 | Area 1 | R02 Sumbagsel | 2 | PLG622 | PLG622 | 25TS05N0258 | R02 Sumbagsel | 0 | 24TS03N0150 | 25TS05N0258 | #N/A | ILIR BARAT PH2 | 104.7383 | -2.9785 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-02-19 | 2025-02-18 | 2025-05-19 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 11.Hold |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
54 | Area 1 | R02 Sumbagsel | 2 | PLG624 | PLG624 | 24TS03N0153 | R02 Sumbagsel | 0 | 24TS03N0153 | 24TS03N0153 | #N/A | ILIR BARAT PH4 | 104.7271 | -2.9738 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-03-06 | 2025-03-05 | 2025-06-03 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 11.Hold |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
55 | Area 1 | R02 Sumbagsel | 2 | PLG626 | PLG626 | 24TS03N0149 | R02 Sumbagsel | 0 | 24TS03N0149 | 24TS03N0149 | #N/A | SAKO SAPTAMARGA PH1 | 104.7713 | -2.9418 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-14 | 2025-09-13 | 2025-12-12 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
56 | Area 1 | R02 Sumbagsel | 2 | OKI276 | OKI276 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | TERMINAL UNSRI | 104.649 | -3.2155 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-04-08 | 2026-04-07 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | [7 empty] | 23m (Type-5)
57 | Area 1 | R02 Sumbagsel | 2 | OKI277 | OKI277 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | FAKULTAS MIPA UNSRI | 104.649 | -3.2155 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-04-08 | 2026-04-07 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | [7 empty] | Terminate
58 | Area 1 | R02 Sumbagsel | 2 | PLG629 | PLG629 |  | R02 Sumbagsel | 0 | 24TS03N0154 | 24TS03N0154 | #N/A | POLIGON PH4 | 104.719 | -3.0092 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-12-08 | 2025-12-07 | 2026-03-07 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
59 | Area 2 | R03 Jabotabek Inner | 3 | JKP372 | JKP372 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0109 | PINTUUTARAGBK | 106.8019 | -6.2157 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT ANUGERAH SELARAS RAYA | PT ANUGERAH SELARAS RAYA | 13 | Mitratel | 2018-01-26 | 2028-01-25 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Extend Tower | 0 | 0 | 0 | Extend 3m
60 | Area 1 | R02 Sumbagsel | 2 | PLG610 | PLG610 | 24TS10N0715 | R02 Sumbagsel | 0 | NY | 24TS10N0715 | #N/A | JALAN DLD PH2 | 104.721 | -2.9841 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2014-11-24 | 2024-11-23 | 2025-02-21 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
61 | Area 1 | R02 Sumbagsel | 2 | PLG614 | PLG614 |  | R02 Sumbagsel | 0 | NY | NY | #N/A | SAKO SAPTAMARGA PH4 | 104.7915 | -2.9244 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-14 | 2025-09-13 | 2025-12-12 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
62 | Area 1 | R02 Sumbagsel | 2 | PLG620 | PLG620 |  | R02 Sumbagsel | 0 | NY | NY | #N/A | KEMUNING POLDA PH6 | 104.7558 | -2.9594 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-14 | 2025-09-13 | 2025-12-12 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
63 | Area 2 | R03 Jabotabek Inner | 3 | JBX273 | JBX273 |  | Jabat | #N/A | #N/A | NY | 25TS12B0075 | CENDRAWASIHKEDAUNGKALIANGKEDMT | 106.725 | -6.1453 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT JAGANATA SAKTI UNGGUL | PT JAGANATA SAKTI UNGGUL | 16 | Mitratel | 2018-06-14 | 2028-06-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 100m 285 degree
64 | Area 1 | R02 Sumbagsel | 2 | PLG606 | PLG606 |  | R02 Sumbagsel | 0 | NY | NY | #N/A | SAKO SAPTAMARGA PH2 | 104.7674 | -2.9444 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-11-10 | 2025-11-09 | 2026-02-07 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
65 | Area 2 | R03 Jabotabek Inner | 3 | JKT412 | JKT412 | 25TS08N1972 | Jabat | 0 | #N/A | 25TS08N1972 | #N/A | BLOKBERAMASDMT | 106.9465 | -6.2042 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT INFRAKO |  | Mitratel | 2015-01-31 | 2025-01-30 | 2025-04-30 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate |  | 0 | Monopole | 32
66 | Area 2 | R03 Jabotabek Inner | 3 | JKT424 | JKT424 | 25TS08N2037 | Jabat | 0 | 24TS09B0441 | 25TS08N2037 | #N/A | PERUMNASSUMARNODMT | 106.9505 | -6.2101 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SINERGI REKTA DENTA |  | Mitratel | 2015-02-26 | 2025-02-25 | 2025-05-26 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 09.Pro.Cancel |  | Terminate | Terminate | Terminate |  | Terminate |  | GF | Monopole | 36
67 | Area 2 | R03 Jabotabek Inner | 3 | JKT430 | JKT430 | 25TS08N1747 | Jabat | 0 | 24TS09B0447 | 25TS08N1747 | #N/A | TOLCAKUNGUTARADMT | 106.9425 | -6.1736 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SINERGI REKTA DENTA |  | Mitratel | 2015-02-03 | 2025-02-02 | 2025-05-03 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 09.Pro.Cancel |  | Terminate | Terminate | Terminate |  | Terminate |  | GF | Monopole | 36
68 | Area 2 | R03 Jabotabek Inner | 3 | JTX061 | JTX061 | 24TS09B0437 | Jabat | 24TS09B0437 | 24TS09B0437 | 24TS09B0437 | #N/A | ISTANAANAKTAMINIDMT | 106.8997 | -6.3008 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT CIPTA KARSA ANUGERAH SEMESTA |  | Mitratel | 2015-07-14 | 2025-07-13 | 2025-10-11 | 2025-08-26 | 46 | In SLA | Plan ≤ 2025 | 16.RFI | 03.RFI |  | RFI | RFI | RFI |  | done |  | GF | Monopole | 25
69 | Area 2 | R03 Jabotabek Inner | 3 | JKU199 | JKU199 |  | Jabat | 0 | 24TS09B0451 | 24TS09B0451 | #N/A | HOTELDANAUSUNTERDMT | 106.8789 | -6.1466 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT DENTRA MITRA ABADI |  | Mitratel | 2015-09-19 | 2025-09-18 | 2025-12-17 | 2026-01-31 | -45 | Out SLA | Plan ≤ 2025 | 08.BAN/BAK | 08b.SIS Done |  | SITAC | BAN/BAK | OG | 4.12 proses negosiasi harga sewa pertahun 100 jt/thn untuk sewa per 5 tahun, Waiting Approval nilai | 2026-02-13 | BTR | RT | Monopole | 6
70 | Area 2 | R03 Jabotabek Inner | 3 | JKP368 | JKP368 | 25TS08N2032 |  | #N/A | #N/A | 25TS08N2032 | #N/A | MASJIDALBINAGBK | 106.8024 | -6.2222 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2018-01-26 | 2028-01-25 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
71 | Area 2 | R03 Jabotabek Inner | 3 | JKP371 | JKP371 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0106 | STADIONRENANGGBK | 106.806 | -6.2159 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT ANUGERAH SELARAS RAYA | PT ANUGERAH SELARAS RAYA | 12 | Mitratel | 2018-01-26 | 2028-01-25 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Extend Tower | 0 | 0 | 0 | Extend 3m
72 | Area 1 | R02 Sumbagsel | 2 | PLG612 | PLG612 | 24TS03N0152 | R02 Sumbagsel | 24TS03N0152 | 24TS03N0152 | 24TS03N0152 | #N/A | JALAN DLD PH4 | 104.7364 | -2.9851 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-02-19 | 2025-02-18 | 2025-05-19 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 06.SITAC |  | Terminate | Terminate | Terminate | Proposed Drop, penolakan warga dalam radius, sudah tercover oleh tower lain | Terminate | [5 empty] | Drop
73 | Area 2 | R03 Jabotabek Inner | 3 | JPX110 | JPX110 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0105 | MENTENGJAKPUSDMT | 106.8393 | -6.2037 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INFRAKO DAYAMITRA | PT INFRAKO DAYAMITRA | 13 | Mitratel | 2017-08-01 | 2027-07-31 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend 3m
74 | Area 2 | R03 Jabotabek Inner | 3 | JPX166 | JPX166 | 25TS03Z0004 |  | #N/A | #N/A | 25TS03Z0004 | #N/A | DUKUHPINGGIR5DMT | 106.8146 | -6.198 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | PT Sinergi Rektadenta |  | Mitratel | 2016-10-20 | 2026-10-19 |  |  |  |  | Plan ≥ 2026 |  | RFI |  | RFI | RFI | OG | site solution, sudah RFI, mitra solution, existing lahan sengketa (lahan fasum diakui lahan PT) need solution, on air |  |  | #N/A | #N/A | #N/A
75 | Area 1 | R02 Sumbagsel | 2 | PLG704 | PLG704 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | PERINTIS KEMERDEKAAN 2 | 104.775 | -2.9775 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-06-09 | 2026-06-08 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | [7 empty] | Terminate
76 | Area 1 | R02 Sumbagsel | 2 | PLG623 | PLG623 | 24TS03N0147 | R02 Sumbagsel | 24TS03N0147 | 24TS03N0147 | 24TS03N0147 | #N/A | ILIR BARAT PH3 | 104.7252 | -2.9661 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-14 | 2025-09-13 | 2025-12-12 | 2025-12-31 | -19 | Out SLA | Plan ≤ 2025 | #N/A | 08.SIS |  | SITAC | IW | OG | need extend 3m plan stagging, ganti tower | 2026-01-25 | [5 empty] | Extend 3m
77 | Area 2 | R03 Jabotabek Inner | 3 | JPX169 | JPX169 | 25TS08N1781 |  | #N/A | #N/A | 25TS08N1781 | #N/A | SIMPANGSENENRAYADMT | 106.8368 | -6.171 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-06-27 | 2026-06-26 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
78 | Area 2 | R03 Jabotabek Inner | 3 | JSX444 | JSX444 | 25TS08N2005 |  | #N/A | #N/A | 25TS08N2005 | #N/A | KELKARETPEDURENANDMT | 106.833 | -6.2126 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-10-24 | 2026-10-23 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
79 | Area 1 | R02 Sumbagsel | 2 | PLG609 | PLG609 |  | R02 Sumbagsel | 0 | NY | NY | #N/A | JALAN DLD PH1 | 104.7226 | -2.9871 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2014-10-15 | 2024-10-14 | 2025-01-12 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
80 | Area 1 | R02 Sumbagsel | 2 | PLG611 | PLG611 |  | R02 Sumbagsel | 0 | NY | NY | #N/A | JALAN DLD PH3 | 104.7248 | -2.9786 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2014-11-24 | 2024-11-23 | 2025-02-21 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
81 | Area 1 | R02 Sumbagsel | 2 | PLG616 | PLG616 |  | R02 Sumbagsel | 0 | NY | NY | #N/A | KEMUNING POLDA PH2 | 104.7497 | -2.9536 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2014-11-24 | 2024-11-23 | 2025-02-21 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
82 | Area 1 | R02 Sumbagsel | 2 | PLG618 | PLG618 | 24TS03N0151 | R02 Sumbagsel | 24TS03N0151 | 24TS03N0151 | 24TS03N0151 | #N/A | KEMUNING POLDA PH4 | 104.7557 | -2.9595 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2014-11-24 | 2024-11-23 | 2025-02-21 | 2025-05-24 | -92 | Out SLA | Plan ≤ 2025 | #N/A | 03.RFI |  | RFI | RFI | RFI |  | done | [5 empty] | RFI
83 | Area 1 | R02 Sumbagsel | 2 | PLG625 | PLG625 | 24TS03N0148 | R02 Sumbagsel | 24TS03N0148 | 24TS03N0148 | 24TS03N0148 | #N/A | ILIR BARAT PH5 | 104.7319 | -2.9708 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2014-11-24 | 2024-11-23 | 2025-02-21 |  |  | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC |  | RFI | RFI | RFI | RFI MCP | done | [5 empty] | RFI Ketinggian existing
84 | Area 1 | R02 Sumbagsel | 2 | PLG615 | PLG615 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | SAKO SAPTAMARGA PH5 | 104.7895 | -2.9251 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-01-12 | 2026-01-11 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | [7 empty] | 23m (Type-5)
85 | Area 2 | R03 Jabotabek Inner | 3 | JTX249 | JTX249 | 25TS08N2030 | Jabat | #N/A | #N/A | 25TS08N2030 | 25TS12Z0124 | MAKASARMAKASAR12DMT | 106.8902 | -6.3006 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DYEVA DIGITAL SELULAR | PT LAYTON ENTER PRISE | 3 | Mitratel | 2016-05-31 | 2026-05-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
86 | Area 2 | R03 Jabotabek Inner | 3 | JSX784 | JSX784 |  |  | #N/A | #N/A | NY | #N/A | MULIAPERDANA2DMT | 106.7558 | -6.2435 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-01-06 | 2026-01-05 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
87 | Area 2 | R03 Jabotabek Inner | 3 | JTX285 | JTX285 | 25TS08N1770 | Jabat | #N/A | #N/A | 25TS08N1770 | 25TS12B0104 | MANUNGGALCPMELAYUMAKASSARDMT | 106.92 | -6.2497 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DYEVA DIGITAL SELULAR | PT DYEVA DIGITAL SELULAR | 3 | Mitratel | 2016-08-13 | 2026-08-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
88 | Area 1 | R02 Sumbagsel | 2 | PLG619 | PLG619 | 23TS12Z0001 | R02 Sumbagsel | 0 | 23TS12Z0001 | 23TS12Z0001 | #N/A | KEMUNING POLDA PH5 | 104.7528 | -2.9482 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2014-11-24 | 2024-11-23 | 2025-02-21 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 09.Pro.Cancel |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
89 | Area 2 | R03 Jabotabek Inner | 3 | JTX460 | JTX460 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0107 | TMII6DMT | 106.902 | -6.3032 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DESATRIA ALARD MANDIRI | PT SAMANTA FIBRA ABADI | 3 | Mitratel | 2017-05-12 | 2027-05-11 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Monopole 25m
90 | Area 2 | R04 Jawa Barat | 4 | BDK844 | BDK844 |  | R04 Jawa Barat | 0 | #N/A | NY | #N/A | KAWALUYAANINDAH | 107.6626 | -6.9349 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-22 | 2025-08-21 | 2025-11-19 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
91 | Area 2 | R03 Jabotabek Inner | 3 | JPX144 | JPX144 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0116 | PASARBARUTIMURSAHARIDMT | 106.838 | -6.1622 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INFRAKO DAYAMITRA | PT INFRAKO DAYAMITRA | 12 | Mitratel | 2016-05-31 | 2026-05-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | collo | 0 | 0 | 0 | Reloc to existing MTEL
92 | Area 1 | R02 Sumbagsel | 2 | PLG702 | PLG702 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | PERUMAHAN MASKAREBET | 104.6967 | -2.9283 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-11 | 2026-07-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | [7 empty] | 23m (Type-5)
93 | Area 1 | R02 Sumbagsel | 2 | BDL406 | BDL406 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | POLE REKTORAT UNILAH | 105.2425 | -5.3639 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-08-30 | 2026-08-29 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | [7 empty] | One leg 18m
94 | Area 2 | R03 Jabotabek Inner | 3 | JBX165 | JBX165 |  |  | #N/A | #N/A | NY | #N/A | DURISELATANTAMBORA3DMT | 106.7953 | -6.1521 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-06-11 | 2026-06-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
95 | Area 2 | R12 Jabotabek Outer | 12 | KRW841 | KRW841 | 25TS01B0010 | Eastern Jabodetabek | #N/A | #N/A | 25TS01B0010 | #N/A | KIS6DMT | 107.3232 | -6.3873 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT AGUNGMAS PRIMA SEMPURNA |  | Mitratel | 2016-06-22 | 2026-06-21 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS |  | Sitac | BAN/BAK | OG | Add 3 RF Add 6 RRU Final Sow Rescope: BTR to Macro |  | BTR | GF | SST | 42
96 | Area 2 | R03 Jabotabek Inner | 3 | JKT680 | JKT680 | 24TS09B0455 | Jabat | 24TS09B0455 | 24TS09B0455 | 24TS09B0455 | #N/A | RSISLAMPDKOPIDMT | 106.9417 | -6.2214 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT CIPTA KARSA ANUGERAH SEMESTA |  | Mitratel | 2015-01-26 | 2025-01-25 | 2025-04-25 | 2026-01-31 | -281 | Out SLA | Plan ≤ 2025 | #N/A | 08b.SIS Done |  | Proposed Drop | Hunting | Proposed Drop | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial | 2026-02-13 | BTR | GF | Monopole | 32
97 | Area 2 | R03 Jabotabek Inner | 3 | JKT411 | JKT411 | 25TS08N1759 | Jabat | 24TS09B0449 | 24TS09B0449 | 25TS08N1759 | #N/A | MSJDTAUBAHKOMPSNDNGDMT | 106.91 | -6.2142 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT CIPTA KARSA ANUGERAH SEMESTA |  | Mitratel | 2015-01-29 | 2025-01-28 | 2025-04-28 | 2026-01-31 | -278 | Out SLA | Plan ≤ 2025 | 08.BAN/BAK | 06.SITAC |  | SITAC | BAN/BAK | OG | 4.12 waiting nilai kompensasi pihak DKM (high price), Waiting Approval nilai | 2026-02-26 | Extend Tower | GF | Monopole | 32 | 3m
98 | Area 2 | R03 Jabotabek Inner | 3 | JKT435 | JKT435 | 25TS08N1756 | Jabat | 24TS09B0448 | 24TS09B0448 | 25TS08N1756 | #N/A | PSRKLENDERNGURAHRAIDMT | 106.905 | -6.2134 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT CIPTA KARSA ANUGERAH SEMESTA |  | Mitratel | 2015-01-30 | 2025-01-29 | 2025-04-29 | 2026-01-31 | -277 | Out SLA | Plan ≤ 2025 | 09.PROSES IW | 06.SITAC |  | SITAC | IW | OG | 4.12 issue permintaan warga penambahan kompensasi 20 jt | 2026-02-22 | BTR | GF | Monopole | 30
99 | Area 2 | R03 Jabotabek Inner | 3 | JKT414 | JKT414 | 24TS09B0446 | Jabat | 0 | 24TS09B0446 | 24TS09B0446 | #N/A | INSPEKSIKALIMALANGDMT | 106.8987 | -6.2436 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SINERGI REKTA DENTA |  | Mitratel | 2015-02-03 | 2025-02-02 | 2025-05-03 | 2025-03-16 | 48 | In SLA | Plan ≤ 2025 | 16.RFI | 03.RFI |  | RFI | RFI | RFI |  | done |  | GF | Monopole | 32
100 | Area 2 | R03 Jabotabek Inner | 3 | JPX190 | JPX190 |  |  | #N/A | #N/A | NY | #N/A | JLNASIONALDMT | 106.7963 | -6.2104 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-06-13 | 2027-06-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
101 | Area 2 | R03 Jabotabek Inner | 3 | JKU760 | JKU760 | 24TS09B0442 | Jabat | 24TS09B0442 | 24TS09B0442 | 24TS09B0442 | #N/A | PLUITUTARARAYADMT | 106.7921 | -6.1122 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT AJIAN TRI SUKSES |  | Mitratel | 2015-02-10 | 2025-02-09 | 2025-05-10 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 09.Pro.Cancel |  | Terminate | Terminate | Terminate | Arahan NBAE SAR 150m | Terminate |  | GF | Monopole | 32
102 | Area 2 | R03 Jabotabek Inner | 3 | JKU832 | JKU832 | 24TS09B0443 | Jabat | 24TS09B0443 | 24TS09B0443 | 24TS09B0443 | #N/A | PLUITTIMURBARUDMT | 106.7942 | -6.1207 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT DENTRA MITRA ABADI |  | Mitratel | 2015-02-10 | 2025-02-09 | 2025-05-10 | 2026-01-31 | -266 | Out SLA | Plan ≤ 2025 | #N/A | 08.SIS |  | RFC | RFC | OG | 04.12 proses pabrikasi, target RFI 28 Dec, Lanjut MCP, Proses Design dan Perijinan Pole Extend, drop by tsel, proses nego ke Tsel untuk proposed Extend 3m | 2025-12-28 | Extend Tower | GF | Monopole | 30 | 3m | proposed drop by regional
103 | Area 2 | R03 Jabotabek Inner | 3 | JKU858 | JKU858 | 24TS09B0444 | Jabat | 24TS09B0444 | 24TS09B0444 | 24TS09B0444 | #N/A | PLUITKARANGBARATDMT | 106.7768 | -6.1139 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT DENTRA MITRA ABADI |  | Mitratel | 2015-02-10 | 2025-02-09 | 2025-05-10 | 2026-01-31 | -266 | Out SLA | Plan ≤ 2025 | 08.BAN/BAK | 08.SIS |  | RFC | RFC | OG | 04.12 proses pabrikasi, target RFI 28 Dec, Lanjut MCP, Proses Design dan Perijinan Pole Extend | 2025-12-28 | Extend Tower | GF | Monopole | 32
104 | Area 2 | R03 Jabotabek Inner | 3 | JSX130 | JSX130 | 25TS08N1769 | Jabat | 24TS09B0445 | 24TS09B0445 | 25TS08N1769 | #N/A | PERCETAKAN2DMT | 106.7942 | -6.2483 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT MITRA SARANA KARYA BANGSA |  | Mitratel | 2015-02-10 | 2025-02-09 | 2025-05-10 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 10.Cancel |  | Terminate | Terminate | Terminate |  | Terminate |  | GF | Monopole | 30
105 | Area 2 | R03 Jabotabek Inner | 3 | JSX032 | JSX032 | 25TS08N1979 | Jabat | 24TS09B0440 | 24TS09B0440 | 25TS08N1979 | #N/A | CAMATKEBAYORANLAMADMT | 106.7783 | -6.2488 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT MITRA SARANA KARYA BANGSA |  | Mitratel | 2015-02-27 | 2025-02-26 | 2025-05-27 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 09.Pro.Cancel |  | Terminate | Terminate | Terminate |  | Terminate |  | GF | Monopole | 30
106 | Area 2 | R03 Jabotabek Inner | 3 | JSX998 | JSX998 | 24TS10B0022 | Jabat | #N/A | #N/A | 24TS10B0022 | #N/A | RELOCDANAMONDMT | 106.7977 | -6.2483 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | PT SINERGI REKTA DENTA |  | Mitratel | 2016-09-13 | 2026-09-12 |  |  |  |  | Plan ≥ 2026 |  | 10.Cancel |  | Need DRM | Need DRM | OG |  |  |  | GF | Monopole | 32
107 | Area 2 | R03 Jabotabek Inner | 3 | JKU977 | JKU977 |  | Jabat | 24TS09B0438 | 24TS09B0438 | 24TS09B0438 | #N/A | TELUKNIBUNGDMT | 106.7747 | -6.1274 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT AJIAN TRI SUKSES |  | Mitratel | 2015-04-24 | 2025-04-23 | 2025-07-22 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 04.CME |  | Terminate | Terminate | Terminate |  | Terminate |  | GF | Monopole | 32
108 | Area 2 | R03 Jabotabek Inner | 3 |  | JTX505 |  | Jabat | #N/A | #N/A | NY | #N/A | JENGKIKEBONPALA | 106.8822 | -6.2573 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MULTI BAGASANTI MAHDY | 0 | 10 | Mitratel | 2019-01-24 | 2029-01-23 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 300' 100m
109 | Area 2 | R03 Jabotabek Inner | 3 | JSX500 | JSX500 | 25TS08N2036 |  | #N/A | #N/A | 25TS08N2036 | #N/A | JLNPANGERANANTASARIDMT | 106.8073 | -6.283 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-11-07 | 2026-11-06 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
110 | Area 2 | R03 Jabotabek Inner | 3 | JKU959 | JKU959 |  | Jabat | 24TS09B0435 | 24TS09B0435 | 24TS09B0435 | #N/A | PASARIKANMUARAANGKEDMT | 106.7746 | -6.106 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT NAER TUNAS INDONESIA |  | Mitratel | 2015-07-15 | 2025-07-14 | 2025-10-12 | 2025-05-24 | 141 | In SLA | Plan ≤ 2025 | 16.RFI | 03.RFI |  | RFI | RFI | RFI |  | done |  | RT | 25m+pole9m | 34
111 | Area 2 | R03 Jabotabek Inner | 3 | JKU962 | JKU962 |  | Jabat | 24TS09B0432 | 24TS09B0432 | 24TS09B0432 | #N/A | PERUMMUARAANGKEDMT | 106.768 | -6.107 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT NAER TUNAS INDONESIA |  | Mitratel | 2015-07-23 | 2025-07-22 | 2025-10-20 | 2026-01-31 | -103 | Out SLA | Plan ≤ 2025 | 07.SITAC | 08b.SIS Done |  | Proposed Drop | Hunting | Proposed Drop | 4.12 lahan pemda, ijin dari pemda tdk released, existing monopole 18m extend jadi 32m, proposed drop, hard sitac dan kandidat | 2026-02-13 | BTR | GF | Monopole | 32
112 | Area 2 | R03 Jabotabek Inner | 3 | JSX768 | JSX768 |  | Jabat | 24TS09B0433 | 24TS09B0433 | 24TS09B0433 | #N/A | MESJIDPONDOKINDAHDMT | 106.783 | -6.2622 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SUMBERSOLUSINDO HITECH |  | Mitratel | 2015-07-23 | 2025-07-22 | 2025-10-20 | 2026-01-31 | -103 | Out SLA | Plan ≤ 2025 | 21.LOCK TRIAL | 06.SITAC |  | Proposed Drop | Hunting | Proposed Drop | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial | 2026-02-13 | BTR | GF | Monopole | 32
113 | Area 2 | R03 Jabotabek Inner | 3 | JSX890 | JSX890 | 25TS08N1991 | Jabat | 24TS09B0434 | 24TS09B0434 | 25TS08N1991 | #N/A | KAIBALAIYASAMANGGARAIDMT | 106.8523 | -6.2153 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SUMBERSOLUSINDO HITECH |  | Mitratel | 2015-07-23 | 2025-07-22 | 2025-10-20 | 2026-01-31 | -103 | Out SLA | Plan ≤ 2025 | 08.BAN/BAK | 06.SITAC |  | SITAC | IW | OG | 4.12 IW OG | 2026-02-14 | BTR | GF | Monopole | 32
114 | Area 2 | R03 Jabotabek Inner | 3 | JKU944 | JKU944 | 25TS08N1758 | Jabat | 24TS09B0431 | 24TS09B0431 | 25TS08N1758 | #N/A | MENARAMITRABAHARIDMT | 106.8068 | -6.1281 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT NAER TUNAS INDONESIA |  | Mitratel | 2015-07-23 | 2025-07-22 | 2025-10-20 | 2026-01-31 | -103 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC |  | Proposed Drop | Hunting | Proposed Drop | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial | 2026-02-13 | BTR | GF | Monopole | 32
115 | Area 2 | R03 Jabotabek Inner | 3 | JBX052 | JBX052 |  | Jabat | 24TS09B0427 | 24TS09B0427 | 24TS09B0427 | #N/A | KOMPLEKMIGASDMT | 106.7695 | -6.2027 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT JAGANATA SAKTI UNGGUL |  | Mitratel | 2015-07-24 | 2025-07-23 | 2025-10-21 | 2026-01-31 | -102 | Out SLA | Plan ≤ 2025 | 21.LOCK TRIAL | 06.SITAC |  | Proposed Drop | Hunting | Proposed Drop | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial | 2026-02-14 | BTR | GF | Monopole | 32
116 | Area 2 | R03 Jabotabek Inner | 3 | JPX005 | JPX005 | 24TS09B0428 | Jabat | 24TS09B0428 | 24TS09B0428 | 24TS09B0428 | #N/A | KEBONKACANG4DMT | 106.8174 | -6.1891 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT ANUGERAH SELARAS RAYA |  | Mitratel | 2015-07-24 | 2025-07-23 | 2025-10-21 | 2026-01-31 | -102 | Out SLA | Plan ≤ 2025 | 08.BAN/BAK | 06.SITAC |  | CME | Erection OG | OG | 4.12 erection OG, Target RFI 14 dec | 2025-12-14 | Extend Tower | RT | Monopole | 32
117 | Area 2 | R03 Jabotabek Inner | 3 | JPX017 | JPX017 | 24TS09B0453 | Jabat | 24TS09B0453 | 24TS09B0453 | 24TS09B0453 | #N/A | JALANCISADANECIKINIDMT | 106.8427 | -6.1945 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT ANUGERAH SELARAS RAYA |  | Mitratel | 2015-07-24 | 2025-07-23 | 2025-10-21 | 2026-01-31 | -102 | Out SLA | Plan ≤ 2025 | 08.BAN/BAK | 08b.SIS Done |  | RFC | RFC | OG | 4.12 pabrikasi OG | 2025-12-28 | Extend Tower | GF | Monopole | 32
118 | Area 2 | R03 Jabotabek Inner | 3 | JSX771 | JSX771 | 24TS09B0430 | Jabat | 24TS09B0430 | 24TS09B0430 | 24TS09B0430 | #N/A | KOMPLEKDEPSOSPDKINDHDMT | 106.7879 | -6.2658 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SUMBERSOLUSINDO HITECH |  | Mitratel | 2015-07-24 | 2025-07-23 | 2025-10-21 | 2026-01-31 | -102 | Out SLA | Plan ≤ 2025 | 07.SITAC | 06.SITAC |  | RFC | RFC | OG | 4.12 pabrikasi OG | 2025-12-28 | Extend Tower | GF | Monopole | 32
119 | Area 2 | R03 Jabotabek Inner | 3 | JBX167 | JBX167 |  |  | #N/A | #N/A | NY | #N/A | JLNANGKEJAYA10DMT | 106.7939 | -6.1479 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-11-30 | 2026-11-29 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
120 | Area 2 | R03 Jabotabek Inner | 3 | JPX028 | JPX028 | 24TS09B0429 | Jabat | 24TS09B0429 | 24TS09B0429 | 24TS09B0429 | #N/A | TANAHTINGGIDMT | 106.8462 | -6.179 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT ANUGERAH SELARAS RAYA |  | Mitratel | 2015-07-24 | 2025-07-23 | 2025-10-21 | 2026-01-31 | -102 | Out SLA | Plan ≤ 2025 | 15.STR | 08b.SIS Done |  | RFC | RFC | OG | 10.12 plan erection 12 Dec, Target RFI 16 dec | 2025-12-14 | Extend Tower | RT | Monopole | 32
121 | Area 2 | R03 Jabotabek Inner | 3 | JTX091 | JTX091 | 24TS09B0426 | Jabat | 24TS09B0426 | 24TS09B0426 | 24TS09B0426 | #N/A | GRAHAWIDYAPATRADMT | 106.9059 | -6.3008 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT CIPTA KARSA ANUGERAH SEMESTA |  | Mitratel | 2015-07-28 | 2025-07-27 | 2025-10-25 | 2025-08-26 | 60 | In SLA | Plan ≤ 2025 | 16.RFI | 04.CME |  | RFI | RFI | RFI |  | done |  | GF | Monopole | 25
122 | Area 2 | R03 Jabotabek Inner | 3 | JBX042 | JBX042 | 24TS09B0425 | Jabat | 24TS09B0425 | 24TS09B0425 | 24TS09B0425 | #N/A | PRISMARAYADMT | 106.7584 | -6.1938 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT JAGANATA SAKTI UNGGUL |  | Mitratel | 2015-07-31 | 2025-07-30 | 2025-10-28 | 2026-01-31 | -95 | Out SLA | Plan ≤ 2025 | 15.STR | 08b.SIS Done |  | Proposed Drop | Proposed Drop | Proposed Drop | 4.12 hard kandidat, Hard Sitac, lahan pemda tdk ada ijin, existing 20m extend to 3m | 2026-02-14 | Extend Tower | GF | Monopole | 32
123 | Area 2 | R03 Jabotabek Inner | 3 | JBX021 | JBX021 |  | Jabat | 24TS09B0454 | 24TS09B0454 | 24TS09B0454 | #N/A | KEMBANGANBARUDMT | 106.7501 | -6.1804 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT JAGANATA SAKTI UNGGUL |  | Mitratel | 2015-08-13 | 2025-08-12 | 2025-11-10 | 2026-01-31 | -82 | Out SLA | Plan ≤ 2025 | 21.LOCK TRIAL | 08b.SIS Done |  | Proposed Drop | Hunting | Proposed Drop | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial | 2026-02-13 | BTR | GF | Monopole | 32
124 | Area 2 | R03 Jabotabek Inner | 3 | JBX016 | JBX016 | 25TS08N1780 | Jabat | 24TS09B0424 | 24TS09B0424 | 25TS08N1780 | #N/A | GLOBALNUSANTARASCHOOLDMT | 106.739 | -6.1919 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT JAGANATA SAKTI UNGGUL |  | Mitratel | 2015-08-17 | 2025-08-16 | 2025-11-14 | 2026-01-31 | -78 | Out SLA | Plan ≤ 2025 | 15.STR | 06.SITAC |  | RFC | RFC | OG | 10.12 pabrikasi OG | 2026-01-10 | Extend Tower | GF | Monopole | 32
125 | Area 2 | R03 Jabotabek Inner | 3 | JSX933 | JSX933 |  | Jabat | 24TS09B0452 | 24TS09B0452 | 24TS09B0452 | #N/A | KEMAJUANMULIA2DMT | 106.754 | -6.2392 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT MITRA SARANA KARYA BANGSA |  | Mitratel | 2015-08-28 | 2025-08-27 | 2025-11-25 | 2026-01-31 | -67 | Out SLA | Plan ≤ 2025 | 21.LOCK TRIAL | 06.SITAC |  | Proposed Drop | Hunting | Proposed Drop | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial | 2026-02-13 | BTR | GF | Monopole | 32
126 | Area 2 | R03 Jabotabek Inner | 3 | JPX029 | JPX029 |  | Jabat | 24TS09B0423 | 24TS09B0423 | 24TS09B0423 | #N/A | JALANBAKTIDMT | 106.8063 | -6.2013 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT ANUGERAH SELARAS RAYA |  | Mitratel | 2015-08-31 | 2025-08-30 | 2025-11-28 | 2026-01-31 | -64 | Out SLA | Plan ≤ 2025 | 21.LOCK TRIAL | 08b.SIS Done |  | Proposed Drop | Hunting | Proposed Drop | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial | 2026-02-13 | BTR | GF | Monopole | 30
127 | Area 2 | R03 Jabotabek Inner | 3 | JSX741 | JSX741 | 24TS09B0422 | Jabat | 24TS09B0422 | 24TS09B0422 | 24TS09B0422 | #N/A | KEMANDORANPLUIS1DMT | 106.7926 | -6.2109 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SUMBERSOLUSINDO HITECH |  | Mitratel | 2015-09-05 | 2025-09-04 | 2025-12-03 | 2025-12-31 | -28 | Out SLA | Plan ≤ 2025 | 08.BAN/BAK | 06.SITAC |  | RFI | RFI | RFI | Lanjut B2R | RFI |  | GF | Monopole | 32
128 | Area 4 | R08 Kalimantan | 8 | SMR460 | SMR460 |  | R08 Kalimantan | 0 | 24TS06B0003 | 24TS06B0003 | #N/A | MTH_UNMULSMD2 | 117.1543 | -0.47071 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-19 | 2025-08-18 | 2025-11-16 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
129 | Area 2 | R03 Jabotabek Inner | 3 | JBX084 | JBX084 | 24TS09B0421 | Jabat | 24TS09B0421 | 24TS09B0421 | 24TS09B0421 | #N/A | KOTABAMBUSELATANDMT | 106.8021 | -6.1869 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT JAGANATA SAKTI UNGGUL |  | Mitratel | 2015-09-08 | 2025-09-07 | 2025-12-06 | 2025-12-31 | -25 | Out SLA | Plan ≤ 2025 | 09.PROSES IW | 06.SITAC |  | CME | Excavation | OG | 4.12 excavation stop LL minta DP sewa lahan, monopole 32m, Lanjut B2R, NOD done | 2025-12-21 | BTR | GF | Monopole | 32
130 | Area 2 | R03 Jabotabek Inner | 3 | JSX853 | JSX853 | 24TS09B0420 | Jabat | 24TS09B0420 | 24TS09B0420 | 24TS09B0420 | #N/A | KARETGUSURANDMT | 106.8229 | -6.214 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SUMBERSOLUSINDO HITECH |  | Mitratel | 2015-09-16 | 2025-09-15 | 2025-12-14 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08b.SIS Done |  | Terminate | Terminate | Terminate |  | Terminate |  | GF | Monopole | 32
131 | Area 2 | R03 Jabotabek Inner | 3 | JBX060 | JBX060 | 25TS08N2023 | Jabat | 24TS09B0419 | 24TS09B0419 | 25TS08N2023 | #N/A | ARTABOGAPALMERAHDMT | 106.7907 | -6.204 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT JAGANATA SAKTI UNGGUL |  | Mitratel | 2015-09-17 | 2025-09-16 | 2025-12-15 | 2026-01-31 | -47 | Out SLA | Plan ≤ 2025 | 08.BAN/BAK | 06.SITAC |  | Proposed Drop | Hunting | Proposed Drop | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial | 2026-02-14 | BTR | GF | Monopole | 32
132 | Area 4 | R08 Kalimantan | 8 | BJM313 | BJM313 |  | R08 Kalimantan | 0 | 24TS08Z0005 | 24TS08Z0005 | #N/A | MT_UNLAM_BANJARMASIN1 | 114.5887 | -3.2981 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-19 | 2025-08-18 | 2025-11-16 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
133 | Area 2 | R03 Jabotabek Inner | 3 | JSX693 | JSX693 | 24TS09B0418 | Jabat | 24TS09B0418 | 24TS09B0418 | 24TS09B0418 | #N/A | BANGKA11DMT | 106.8193 | -6.2544 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SUMBERSOLUSINDO HITECH |  | Mitratel | 2015-10-10 | 2025-10-09 | 2026-01-07 | 2026-01-31 | -24 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC |  | Proposed Drop | Hunting | Proposed Drop | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial | 2026-02-14 | BTR | GF | Monopole | 32
134 | Area 4 | R08 Kalimantan | 8 | SMR435 | SMR435 |  | R08 Kalimantan | 0 | 24TS06B0002 | 24TS06B0002 | #N/A | MTH_UNMULSMD3 | 117.157 | -0.46952 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-19 | 2025-08-18 | 2025-11-16 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
135 | Area 2 | R03 Jabotabek Inner | 3 | JPX157 | JPX157 |  |  | #N/A | #N/A | NY | #N/A | HONDAPECENONGANDALAMDMT | 106.8249 | -6.1611 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-06-22 | 2027-06-21 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
136 | Area 2 | R03 Jabotabek Inner | 3 | JPX012 | JPX012 | 25TS08N2047 | Jabat | 24TS09B0417 | 24TS09B0417 | 25TS08N2047 | #N/A | SALEMBARESIDENCEDMT | 106.8544 | -6.196 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT ANUGERAH SELARAS RAYA |  | Mitratel | 2015-10-29 | 2025-10-28 | 2026-01-26 |  |  | Out SLA | Plan ≤ 2025 | 16.RFI | 08b.SIS Done |  | Proposed Drop | Proposed Drop | Proposed Drop | 5.12 proses pabrikasi material extend, target RFI 20 Dec, lock trial, Tsel RFI di TP sebelah | done |  | GF | Monopole | 30 | lock trial
137 | Area 2 | R03 Jabotabek Inner | 3 | JPX048 | JPX048 | 24TS09B0415 | Jabat | 24TS09B0415 | 24TS09B0415 | 24TS09B0415 | #N/A | KEBONSAYURMELATIDMT | 106.8187 | -6.2006 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT ANUGERAH SELARAS RAYA |  | Mitratel | 2015-10-31 | 2025-10-30 | 2026-01-28 | 2026-01-31 | -3 | Out SLA | Plan ≤ 2025 | 21.LOCK TRIAL | 06.SITAC |  | Proposed Drop | Hunting | Proposed Drop | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial | 2026-02-13 | BTR | GF | Monopole | 30
138 | Area 2 | R03 Jabotabek Inner | 3 | JPX062 | JPX062 | 24TS09B0416 | Jabat | 24TS09B0416 | 24TS09B0416 | 24TS09B0416 | #N/A | KEBONKACANG9DMT | 106.8187 | -6.1921 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT ANUGERAH SELARAS RAYA |  | Mitratel | 2015-10-31 | 2025-10-30 | 2026-01-28 | 2026-01-31 | -3 | Out SLA | Plan ≤ 2025 | 21.LOCK TRIAL | 08b.SIS Done |  | SITAC | BAN/BAK | OG | 10.12 kandidat baru, proses BAN BAK, BTR | 2026-02-14 | BTR | GF | Monopole | 30
139 | Area 2 | R03 Jabotabek Inner | 3 | JBX008 | JBX008 | 24TS09B0414 | Jabat | 24TS09B0414 | 24TS09B0414 | 24TS09B0414 | #N/A | JALANHDAUDDMT | 106.7758 | -6.2052 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT JAGANATA SAKTI UNGGUL |  | Mitratel | 2015-11-14 | 2025-11-13 | 2026-02-11 | 2026-01-31 | 11 | In SLA | Plan ≤ 2025 | 07.SITAC | 06.SITAC |  | SITAC | IW | OG | 10.12 plan extend 3m 4.12 LL berubah pikiran tidak bersedia di extend | 2026-02-13 | BTR | GF | Monopole | 32 | proposed extend 3m
140 | Area 2 | R03 Jabotabek Inner | 3 | JUX178 | JUX178 | 24TS09B0413 | Jabat | 24TS09B0413 | 24TS09B0413 | 24TS09B0413 | #N/A | SWASEMBADATIMUR21DMT | 106.8877 | -6.1188 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT NAER TUNAS INDONESIA |  | Mitratel | 2015-11-21 | 2025-11-20 | 2026-02-18 | 2025-12-31 | 49 | In SLA | Plan ≤ 2025 | 08.BAN/BAK | 08b.SIS Done |  | SITAC | REKOM | OG | 4.12 proses rekom, Lanjut B2R | 2026-02-22 | BTR | GF | Monopole | 32
141 | Area 2 | R03 Jabotabek Inner | 3 | JUX318 | JUX318 | 24TS09B0412 | Jabat | 24TS09B0412 | 24TS09B0412 | 24TS09B0412 | #N/A | MESJIDPUSKESMASSUNTERDMT | 106.8609 | -6.1417 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT DYEVA DIGITAL SELULAR |  | Mitratel | 2015-11-23 | 2025-11-22 | 2026-02-20 | 2026-01-31 | 20 | In SLA | Plan ≤ 2025 | 08.BAN/BAK | 06.SITAC |  | CME | Curing Time | OG | 10.12 curing, waiting material tower | 2025-12-14 | BTR | GF | Monopole | 42
142 | Area 2 | R03 Jabotabek Inner | 3 | JTX018 | JTX018 | 24TS09B0411 | Jabat | 24TS09B0411 | 24TS09B0411 | 24TS09B0411 | #N/A | RAYAPENGGILINGANDMT | 106.9354 | -6.2028 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT CIPTA KARSA ANUGERAH SEMESTA |  | Mitratel | 2015-11-24 | 2025-11-23 | 2026-02-21 | 2026-01-31 | 21 | In SLA | Plan ≤ 2025 | 08.BAN/BAK | 08b.SIS Done |  | SITAC | BAN/BAK | OG | 10.12 proses negosiasi sewa lahan | 2026-02-14 | BTR | GF | Monopole | 32
143 | Area 2 | R03 Jabotabek Inner | 3 | JSX802 | JSX802 | 25TS08N2008 | Jabat | 24TS09B0450 | 24TS09B0450 | 25TS08N2008 | #N/A | DEPSOS11DMT | 106.7653 | -6.2679 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT MITRA SARANA KARYA BANGSA |  | Mitratel | 2015-11-29 | 2025-11-28 | 2026-02-26 | 2026-01-31 | 26 | In SLA | Plan ≤ 2025 | 15.STR | 08b.SIS Done |  | SITAC2 | IW | OG | 10.12 proses IW, kurang 4 KK | 2026-01-10 | BTR | GF | Monopole | 32
144 | Area 2 | R03 Jabotabek Inner | 3 | JKU900 | JKU900 | 25TS08N1988 | Jabat | 24TS09B0410 | 24TS09B0410 | 25TS08N1988 | #N/A | SUNTERJAYATIMURDMT | 106.8778 | -6.1572 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT DYEVA DIGITAL SELULAR |  | Mitratel | 2015-11-30 | 2025-11-29 | 2026-02-27 | 2026-01-31 | 27 | In SLA | Plan ≤ 2025 | #N/A | 06.SITAC |  | Proposed Drop | Proposed Drop | Proposed Drop | 4.12 IW OG, hard sitac dan kandidat | 2026-02-22 | BTR | GF | Monopole | 32 | masuk list drop tsel
145 | Area 2 | R03 Jabotabek Inner | 3 | JPX041 | JPX041 | 25TS08N2056 | Jabat | 24TS09B0409 | 24TS09B0409 | 25TS08N2056 | #N/A | BENHIL15 | 106.8117 | -6.2144 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT ANUGERAH SELARAS RAYA |  | Mitratel | 2015-12-11 | 2025-12-10 | 2026-03-10 | 2026-01-31 | 38 | In SLA | Plan ≤ 2025 | 21.LOCK TRIAL | 08b.SIS Done |  | Proposed Drop | Proposed Drop | Proposed Drop | 4.12 IW OG | 2026-02-13 | BTR | RT | Monopole | 32
146 | Area 2 | R03 Jabotabek Inner | 3 | JSX793 | JSX793 | 24TS09B0408 | Jabat | 24TS09B0408 | 24TS09B0408 | 24TS09B0408 | #N/A | PINANGSUASA3DMT | 106.7799 | -6.2627 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SUMBERSOLUSINDO HITECH |  | Mitratel | 2015-12-21 | 2025-12-20 | 2026-03-20 | 2026-01-31 | 48 | In SLA | Plan ≤ 2025 | 08.BAN/BAK | 06.SITAC |  | Proposed Drop | Proposed Drop | Proposed Drop | 4.12 hard kandidat, Hard Sitac, plan BTR gagal IW, kandidat ke 5, proposed ke existing untuk extend | 2026-02-14 | BTR | GF | Monopole | 32
147 | Area 2 | R03 Jabotabek Inner | 3 | JKT433 | JKT433 |  | Jabat | 24TS09B0407 | 24TS09B0407 | 24TS09B0407 | #N/A | GANGSADARDMT | 106.9398 | -6.2124 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SINERGI REKTA DENTA |  | Mitratel | 2014-02-10 | 2024-02-09 | 2024-05-09 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 09.Pro.Cancel |  | Terminate | Terminate | Terminate |  | Terminate |  | GF | Monopole | 32
148 | Area 2 | R03 Jabotabek Inner | 3 | JKB863 | JKB863 | 25TS08N2018 | Jabat | 0 | #N/A | 25TS08N2018 | #N/A | INTERSECTIONPSANGGRAHANDMT | 106.756 | -6.1904 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2014-02-10 | 2024-02-09 | 2024-05-09 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
149 | Area 2 | R03 Jabotabek Inner | 3 | JKP922 | JKP922 | 23TS03Z0018 | Jabat | 23TS03Z0018 | 23TS03Z0018 | 23TS03Z0018 | #N/A | JALANTEUKUUMARDMT | 106.8331 | -6.1898 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | Koperasi Dayamitra Telekomunikasi |  | Mitratel | 2013-04-27 | 2023-04-26 | 2023-07-25 | 2025-10-14 | -812 | Out SLA | Plan ≤ 2025 | 12.RFC | 08b.SIS Done |  | RFI | RFI | RFI |  | done |  | GF | Monopole | 23
150 | Area 2 | R03 Jabotabek Inner | 3 | JKP921 | JKP921 |  | Jabat | 0 | 23TS03Z0019 | 23TS03Z0019 | #N/A | HALTESALEMBAUIDMT | 106.8251 | -6.1832 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | Koperasi Dayamitra Telekomunikasi |  | Mitratel | 2013-04-30 | 2023-04-29 | 2023-07-28 | 2024-12-20 | -511 | Out SLA | Plan ≤ 2025 | 16.RFI | #N/A |  | RFI | RFI | RFI |  | done |  | GF | Monopole | 18
151 | Area 2 | R03 Jabotabek Inner | 3 | JKP920 | JKP920 |  | Jabat | 0 | 23TS03Z0022 | 23TS03Z0022 | #N/A | CITIWALKSUDIRMANDMT | 106.8176 | -6.2091 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT.Geaf Solusianda Pratama |  | Mitratel | 2013-05-04 | 2023-05-03 | 2023-08-01 | 2024-06-03 | -307 | Out SLA | Plan ≤ 2025 | 16.RFI | #N/A |  | RFI | RFI | RFI |  | done |  | GF | Monopole | 23
152 | Area 2 | R03 Jabotabek Inner | 3 | JKP917 | JKP917 |  | Jabat | 0 | #N/A | NY | #N/A | TAMANSUROPATIDMT | 106.8327 | -6.1984 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-05-07 | 2023-05-06 | 2023-08-04 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
153 | Area 2 | R03 Jabotabek Inner | 3 | JKP219 | JKP219 | 25TS08N2001 | Jabat | 0 | 23TS03Z0017 | 25TS08N2001 | #N/A | PENJERNIHANMAKRODMT | 106.8052 | -6.204 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | Koperasi Dayamitra Telekomunikasi |  | Mitratel | 2013-06-23 | 2023-06-22 | 2023-09-20 | 2024-12-20 | -457 | Out SLA | Plan ≤ 2025 | 16.RFI | #N/A |  | RFI | RFI | RFI |  | done |  | GF | Monopole | 25
154 | Area 2 | R03 Jabotabek Inner | 3 | JKS399 | JKS399 |  | Jabat | 0 | 23TS03Z0020 | 23TS03Z0020 | #N/A | KNGNPRSDASPRBLOCKDMT | 106.8334 | -6.2097 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT.Sumbersolusindo Hitech |  | Mitratel | 2013-07-07 | 2023-07-06 | 2023-10-04 | 2024-12-20 | -443 | Out SLA | Plan ≤ 2025 | 16.RFI | #N/A |  | RFI | RFI | RFI |  | done |  | GF | Monopole | 25
155 | Area 2 | R03 Jabotabek Inner | 3 | JKP968 | JKP968 | 23TS03Z0023 | Jabat | 0 | 23TS03Z0023 | 23TS03Z0023 | #N/A | DIPONEGOROMENTENGDMT | 106.8413 | -6.2016 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT.Sumbersolusindo Hitech |  | Mitratel | 2013-07-13 | 2023-07-12 | 2023-10-10 | 2025-05-24 | -592 | Out SLA | Plan ≤ 2025 | 16.RFI | 03.RFI |  | RFI | RFI | RFI |  | done |  | GF | Monopole | 21
156 | Area 2 | R03 Jabotabek Inner | 3 | JSX028 | JSX028 | 25TS08N2123 | Jabat | 0 | 23TS03Z0024 | 25TS08N2123 | #N/A | GARUTMENTENGDMT | 106.8413 | -6.2049 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT.Sumbersolusindo Hitech |  | Mitratel | 2013-07-13 | 2023-07-12 | 2023-10-10 | 2024-12-20 | -437 | Out SLA | Plan ≤ 2025 | 16.RFI | #N/A |  | RFI | RFI | RFI |  | done |  | GF | Monopole | 20
157 | Area 2 | R03 Jabotabek Inner | 3 | JKP965 | JKP965 |  | Jabat | 0 | 23TS03Z0016 | 23TS03Z0016 | #N/A | SIRIHRAYARAVINDOEMAC | 106.8251 | -6.1832 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | Koperasi Dayamitra Telekomunikasi |  | Mitratel | 2013-07-17 | 2023-07-16 | 2023-10-14 | 2024-12-20 | -433 | Out SLA | Plan ≤ 2025 | 16.RFI | #N/A |  | RFI | RFI | RFI |  | done |  | GF | Monopole | 18
158 | Area 2 | R03 Jabotabek Inner | 3 | JKB874 | JKB874 |  | Jabat | 0 | #N/A | NY | #N/A | SIMPANGCIDENGTIMURDMT | 106.8121 | -6.1757 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-07-27 | 2023-07-26 | 2023-10-24 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
159 | Area 2 | R03 Jabotabek Inner | 3 | JKB895 | JKB895 | 25TS08U1375 | Jabat | 0 | 23TS03Z0021 | 25TS08U1375 | #N/A | FACHERUDINDMT | 106.8151 | -6.1848 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT.Geaf Solusianda Pratama |  | Mitratel | 2013-10-31 | 2023-10-30 | 2024-01-28 | 2024-12-20 | -327 | Out SLA | Plan ≤ 2025 | 16.RFI | #N/A |  | RFI | RFI | RFI |  | done |  | GF | Monopole | 20
160 | Area 2 | R03 Jabotabek Inner | 3 | JUX011 | JUX011 | 24TS09B0436 | Jabat | 0 | 24TS09B0436 | 24TS09B0436 | #N/A | PLUITSAMUDRA1DMT | 106.7963 | -6.1089 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT NAER TUNAS INDONESIA |  | Mitratel | 2015-07-15 | 2025-07-14 | 2025-10-12 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate |  | GF | Monopole | 32
161 | Area 2 | R03 Jabotabek Inner | 3 | JKB864 | JKB864 | 25IS08N0109 | Jabat | 0 | #N/A | 25IS08N0109 | #N/A | JALANARJUNAUTARADMT | 106.7831 | -6.1856 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-11-13 | 2023-11-12 | 2024-02-10 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
162 | Area 1 | R01 Sumbagut | 1 |  | MDX501 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0067 | MC KIM Belawan-2 | 98.7025 | 3.6777 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT MEDCOMM SOLUTION |  | Mitratel | 2016-11-11 | 2026-11-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to Mini Macro |  | BTR
163 | Area 2 | R03 Jabotabek Inner | 3 | JTX084 | JTX084 | 25TS08N1762 | Jabat | #N/A | #N/A | 25TS08N1762 | 25TS12B0087 | KAVALERICIPINANGDMT | 106.9152 | -6.2482 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT CIPTA KARSA ANUGERAH SEMESTA | PT CIPTA KARSA ANUGERAH SEMESTA | 5 | Mitratel | 2016-01-16 | 2026-01-15 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 4 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | B2S | 0 | 0 | 0 | 150m utara
164 | Area 2 | R03 Jabotabek Inner | 3 | JTX041 | JTX041 |  | Jabat | #N/A | #N/A | NY | 25TS12B0091 | INSPEKSIKAYUTINGGIDMT | 106.9446 | -6.1803 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT CIPTA KARSA ANUGERAH SEMESTA | PT CIPTA KARSA ANUGERAH SEMESTA | 4 | Mitratel | 2016-01-18 | 2026-01-17 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | B2S | 0 | 0 | 0 | Arah 250m 350 degree
165 | Area 2 | R03 Jabotabek Inner | 3 | JTX098 | JTX098 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0115 | SQUADRONHALIM3DMT | 106.8861 | -6.2756 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT PERSADA SOKKA TAMA | PT SAMANTA FIBRA ABADI | 0 | Mitratel | 2016-01-27 | 2026-01-26 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 5 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Done DRM
166 | Area 2 | R03 Jabotabek Inner | 3 | JSX809 | JSX809 |  | Jabat | #N/A | #N/A | NY | 25TS12B0090 | TAMANBINTAROCEMPAKA4DMT | 106.7596 | -6.2742 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SUMBERSOLUSINDO HITECH | PT TRIPUTRA SURYA SEJAHTERA | 16 | Mitratel | 2016-01-31 | 2026-01-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 150m arah 330 degree
167 | Area 2 | R03 Jabotabek Inner | 3 | JSX779 | JSX779 |  |  | #N/A | #N/A | NY | #N/A | PENINGGARANTIMUR1DMT | 106.778 | -6.243 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-01-31 | 2026-01-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
168 | Area 2 | R03 Jabotabek Inner | 3 | JSX833 | JSX833 |  |  | #N/A | #N/A | NY | #N/A | STALENTENGAGUNGDMT | 106.8355 | -6.3314 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-02-05 | 2026-02-04 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
169 | Area 2 | R03 Jabotabek Inner | 3 | JKU954 | JKU954 |  | Jabat | #N/A | #N/A | NY | 25TS12B0088 | TELUKGONGSELATANFAJARDMT | 106.7831 | -6.1414 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SUMBERSOLUSINDO HITECH | PT SUMBERSOLUSINDO HITECH | 16 | Mitratel | 2016-04-08 | 2026-04-07 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
170 | Area 2 | R03 Jabotabek Inner | 3 | JSX806 | JSX806 | 24TS10B0024 | Jabat | #N/A | #N/A | 24TS10B0024 | #N/A | CINDRAWASIH2DMT | 106.7536 | -6.2687 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | PT Sinergi Rektadenta |  | Mitratel | 2016-04-28 | 2026-04-27 |  |  |  |  | Plan ≥ 2026 |  | 08b.SIS Done |  | Proposed Drop | Proposed Drop | Proposed Drop | Hard Kandidat, proposed drop |  |  | GF | Monopole | 32
171 | Area 2 | R03 Jabotabek Inner | 3 | JSX754 | JSX754 | 25TS08N2048 | Jabat | #N/A | #N/A | 25TS08N2048 | 25TS12B0089 | PERMATAHIJAUTOWNHOUSEDMT | 106.781 | -6.2144 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INTEGRA LINTAS TEKNOLOGI | PT TRIPUTRA SURYA SEJAHTERA | 0 | Mitratel | 2016-04-28 | 2026-04-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 4 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
172 | Area 2 | R03 Jabotabek Inner | 3 | JKU249 | JKU249 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0114 | PLUITKARANGAYU1DMT | 106.7832 | -6.1123 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT AJIAN TRI SUKSES | PT SUMBERSOLUSINDO HITECH | 4 | Mitratel | 2016-05-02 | 2026-05-01 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
173 | Area 3 | R06 Jawa Timur | 6 | MLG569 | MLG569 | 24TS08N0295 | R06 Jawa Timur | #N/A | #N/A | 24TS08N0295 | #N/A | FIAUBMCP | 112.6128 | -7.9517 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-07 | 2025-10-06 | 2026-01-04 | 2025-12-31 | 4 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | SIS/SES | DRM | OG | UB Request Fasilitas Kampus (CSR), harus menyewa lahan yang didirikan bangunan fasum yang diatasnya dirikan tower | NA
174 | Area 2 | R03 Jabotabek Inner | 3 | JUX263 | JUX263 |  | Jabat | #N/A | #N/A | NY | 25TS12B0099 | SUNTERKARYAUTARADMT | 106.8684 | -6.14 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DENTRA MITRA ABADI | PT DENTRA MITRA ABADI | 6 | Mitratel | 2016-06-01 | 2026-05-31 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | ke gedung sebelah
175 | Area 2 | R03 Jabotabek Inner | 3 | JPX153 | JPX153 |  | Jabat | #N/A | #N/A | NY | 25TS12B0093 | SDKENARIDMT | 106.8434 | -6.1853 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SINERGI REKTA DENTA | PT SINERGI REKTA DENTA | 18 | Mitratel | 2016-06-09 | 2026-06-08 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 7 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
176 | Area 2 | R03 Jabotabek Inner | 3 | JSX782 | JSX782 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0112 | BAKTIMURNILEBAKBULUSDMT | 106.7865 | -6.309 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INFRAKO DAYAMITRA | PT SINERGI REKTA DENTA | 11 | Mitratel | 2018-05-13 | 2028-05-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 4 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Extend Tower | 0 | 0 | 0 | Extend 3m
177 | Area 2 | R03 Jabotabek Inner | 3 | JPX137 | JPX137 |  | Jabat | #N/A | #N/A | NY | 25TS12B0092 | DANAUTONDANODMT | 106.8085 | -6.2066 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INFRAKO DAYAMITRA | PT INFRAKO DAYAMITRA | 11 | Mitratel | 2016-06-14 | 2026-06-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
178 | Area 2 | R03 Jabotabek Inner | 3 | JPX156 | JPX156 |  |  | #N/A | #N/A | NY | #N/A | KARETPSRBARUBARATDMT | 106.8144 | -6.2094 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-06-14 | 2026-06-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
179 | Area 2 | R03 Jabotabek Inner | 3 | JPX168 | JPX168 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0119 | KEPUDALAMDMT | 106.8441 | -6.162 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SINERGI REKTA DENTA | PT SINERGI REKTA DENTA | 16 | Mitratel | 2016-06-14 | 2026-06-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend Pole
180 | Area 2 | R03 Jabotabek Inner | 3 | JBX170 | JBX170 | 25TS08N2009 | Jabat | #N/A | #N/A | 25TS08N2009 | 25TS12B0102 | PALMERAHBARAT4JAKARTADMT | 106.7862 | -6.2064 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SINERGI REKTA DENTA | PT SUMBERSOLUSINDO HITECH | 15 | Mitratel | 2016-06-14 | 2026-06-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 7 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
181 | Area 2 | R03 Jabotabek Inner | 3 | JPX158 | JPX158 |  | Jabat | #N/A | #N/A | NY | #N/A | CEMPAKAPUTIHBRT2EDMT | 106.862 | -6.1762 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SINERGI REKTA DENTA | 0 | 15 | Mitratel | 2016-06-22 | 2026-06-21 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
182 | Area 2 | R03 Jabotabek Inner | 3 | JSX454 | JSX454 | 25TS08N1765 |  | #N/A | #N/A | 25TS08N1765 | #N/A | JATIINDAHKEBLAMADMT | 106.7746 | -6.2609 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-06-22 | 2026-06-21 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
183 | Area 2 | R03 Jabotabek Inner | 3 | JSX467 | JSX467 | 25TS08N1764 |  | #N/A | #N/A | 25TS08N1764 | #N/A | SAWOMANGGARAIDMT | 106.8458 | -6.2165 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-06-22 | 2026-06-21 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
184 | Area 3 | R06 Jawa Timur | 6 | MLG089 | MLG089 | 24TS08N0296 | R06 Jawa Timur | #N/A | #N/A | 24TS08N0296 | #N/A | SAMANTHAUBDMTMCP | 112.6156 | -7.9522 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-07 | 2025-10-06 | 2026-01-04 | 2025-12-31 | 4 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | SIS/SES | DRM | OG | UB Request Fasilitas Kampus (CSR), harus menyewa lahan yang didirikan bangunan fasum yang diatasnya dirikan tower | NA
185 | Area 2 | R03 Jabotabek Inner | 3 | JPX146 | JPX146 | 25TS08N2016 |  | #N/A | #N/A | 25TS08N2016 | #N/A | PASARSENENIMPRESSDMT | 106.8384 | -6.174 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-06-28 | 2026-06-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
186 | Area 2 | R03 Jabotabek Inner | 3 | JSX473 | JSX473 | 25TS08N2043 | Jabat | #N/A | #N/A | 25TS08N2043 | #N/A | PERTANIANLEBAKBULUSDMT | 106.7776 | -6.3022 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | PT Sinergi Rektadenta |  | Mitratel | 2016-06-28 | 2026-06-27 |  |  |  |  | Plan ≥ 2026 |  | 04.CME |  | RFI | RFI | RFI | Program Jakarta Quality Improvedment |  |  | GF | Monopole | 32
187 | Area 2 | R03 Jabotabek Inner | 3 | JKU792 | JKU792 |  | Jabat | #N/A | #N/A | NY | 25TS12B0033 | ASRAMAHDMT | 106.9031 | -6.14 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SUMBERSOLUSINDO HITECH | PT SUMBERSOLUSINDO HITECH | 13 | Mitratel | 2016-06-28 | 2026-06-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
188 | Area 2 | R03 Jabotabek Inner | 3 | JSX774 | JSX774 | 25TS08N2026 | Jabat | #N/A | #N/A | 25TS08N2026 | 25TS12Z0095 | SUBURPONDOKPINANGDMT | 106.7711 | -6.2758 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | 5 | Mitratel | 2016-06-29 | 2026-06-28 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend Pole
189 | Area 2 | R03 Jabotabek Inner | 3 | JPX071 | JPX071 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0121 | RELOCKEDUBESAUSTRIADMT | 106.8384 | -6.2011 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SINERGI REKTA DENTA | PT SINERGI REKTA DENTA | 15 | Mitratel | 2016-07-12 | 2026-07-11 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend Pole
190 | Area 2 | R03 Jabotabek Inner | 3 | JBX232 | JBX232 | 25TS08N1975 |  | #N/A | #N/A | 25TS08N1975 | #N/A | NUHRAYAASPARAGUSDMT | 106.7765 | -6.2109 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-08-03 | 2026-08-02 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
191 | Area 2 | R03 Jabotabek Inner | 3 | JBX171 | JBX171 |  | Jabat | #N/A | #N/A | NY | 25TS12B0105 | KSTUBUNSLIPIDMT | 106.804 | -6.1914 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SINERGI REKTA DENTA | PT SUMBERSOLUSINDO HITECH | 14 | Mitratel | 2016-08-09 | 2026-08-08 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 4 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
192 | Area 2 | R03 Jabotabek Inner | 3 | JPX163 | JPX163 |  | Jabat | #N/A | #N/A | NY | 25TS12B0097 | CEPMAKAPUTIHBARATDMT | 106.8678 | -6.1827 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SINERGI REKTA DENTA | PT SINERGI REKTA DENTA | 14 | Mitratel | 2016-08-11 | 2026-08-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
193 | Area 2 | R03 Jabotabek Inner | 3 | JSX507 | JSX507 | 25TS08N1779 |  | #N/A | #N/A | 25TS08N1779 | #N/A | SOUTHQUATERWESTDMT | 106.7826 | -6.2954 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-08-11 | 2026-08-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
194 | Area 2 | R03 Jabotabek Inner | 3 | JUX279 | JUX279 | 25TS08N2004 | Jabat | #N/A | #N/A | 25TS08N2004 | 25TS12B0095 | JLTARIBALUSEDMT | 106.9106 | -6.1692 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DENTRA MITRA ABADI | PT DENTRA MITRA ABADI | 5 | Mitratel | 2016-08-11 | 2026-08-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 150m arah 0 degree
195 | Area 2 | R03 Jabotabek Inner | 3 | JTX255 | JTX255 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0118 | SUMURUTARADURENSAWITDMT | 106.9129 | -6.2162 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT PERSADA SOKKA TAMA | PT MULTI BAGASANTI MAHDY | 0 | Mitratel | 2016-08-11 | 2026-08-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 11 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend 3m
196 | Area 2 | R03 Jabotabek Inner | 3 | JPX167 | JPX167 | 25TS08N2029 | Jabat | #N/A | #N/A | 25TS08N2029 | 25TS12B0101 | JLKARTINIPSBARUDMT | 106.8385 | -6.1511 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SINERGI REKTA DENTA | PT SINERGI REKTA DENTA | 13 | Mitratel | 2016-08-11 | 2026-08-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 10 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
197 | Area 2 | R03 Jabotabek Inner | 3 | JBX234 | JBX234 | 25TS08N2014 | Jabat | #N/A | #N/A | 25TS08N2014 | 25TS12B0106 | JLNLINGKARLUARDMT | 106.7284 | -6.1472 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT AGUNGMAS PRIMA SEMPURNA | PT AGUNGMAS PRIMA SEMPURNA | 19 | Mitratel | 2016-08-11 | 2026-08-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
198 | Area 2 | R03 Jabotabek Inner | 3 | BKX293 | BKX293 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0092 | ANUGRAHRAYADMT | 106.9149 | -6.2521 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INDOJAR MULIA ABADI | PT INDOJAR MULIA ABADI | 4 | Mitratel | 2016-08-11 | 2026-08-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend Pole
199 | Area 2 | R03 Jabotabek Inner | 3 | JPX133 | JPX133 | 25TS08N1993 |  | #N/A | #N/A | 25TS08N1993 | #N/A | SEGITIGAPASARSENENDMT | 106.841 | -6.1746 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-08-11 | 2026-08-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
200 | Area 2 | R03 Jabotabek Inner | 3 | JBX164 | JBX164 |  |  | #N/A | #N/A | NY | #N/A | SUPENOPERMATAHIJAUDMT | 106.777 | -6.2178 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-08-11 | 2026-08-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
201 | Area 2 | R03 Jabotabek Inner | 3 | JUX264 | JUX264 | 25TS08N1984 | Jabat | #N/A | #N/A | 25TS08N1984 | 25TS12B0096 | MASJIDALMANARDMT | 106.885 | -6.1242 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DENTRA MITRA ABADI | PT DENTRA MITRA ABADI | 4 | Mitratel | 2016-08-12 | 2026-08-11 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | Arah 160m 0 degree
202 | Area 2 | R03 Jabotabek Inner | 3 | JBX194 | JBX194 | 25TS08N2017 | Jabat | #N/A | #N/A | 25TS08N2017 | 25TS12B0108 | HJPEENGDMT | 106.7766 | -6.1983 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT AGUNGMAS PRIMA SEMPURNA | PT INFRAKO DAYAMITRA | 18 | Mitratel | 2016-08-12 | 2026-08-11 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
203 | Area 2 | R03 Jabotabek Inner | 3 | JTX067 | JTX067 | 25TS08N2006 | Jabat | #N/A | #N/A | 25TS08N2006 | 25TS12Z0120 | SMP275DMT | 106.8934 | -6.2583 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT PERSADA SOKKA TAMA | PT LAYTON ENTER PRISE | 0 | Mitratel | 2016-08-13 | 2026-08-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 10 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Done DRM
204 | Area 2 | R03 Jabotabek Inner | 3 | JSA041 | JSA041 |  | Jabat | #N/A | #N/A | NY | 25TS12B0053 | JLMANGGISMANGGARAIDMT | 106.8484 | -6.2196 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MITRA SARANA KARYA BANGSA | PT AGUNGMAS PRIMA SEMPURNA | 1 | Mitratel | 2018-07-10 | 2028-07-09 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | B2S | 0 | 0 | 0 | 290' 80m
205 | Area 2 | R03 Jabotabek Inner | 3 | JTX283 | JTX283 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0094 | JLUDOWOPONDOKGEDEDMT | 106.8934 | -6.2882 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INDOJAR MULIA ABADI | PT INDOJAR MULIA ABADI | 3 | Mitratel | 2016-08-13 | 2026-08-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend 3m
206 | Area 2 | R03 Jabotabek Inner | 3 | JTX241 | JTX241 |  | Jabat | #N/A | #N/A | NY | 25TS12B0098 | JLERAMAS2000DMT | 106.9483 | -6.2075 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SAMANTA FIBRA ABADI | PT SAMANTA FIBRA ABADI | 10 | Mitratel | 2016-08-26 | 2026-08-25 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
207 | Area 2 | R03 Jabotabek Inner | 3 | JPX155 | JPX155 |  | Jabat | #N/A | #N/A | NY | 25TS12B0094 | JLPERNEGCEMPAKAPUTIHDMT | 106.8621 | -6.19 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SINERGI REKTA DENTA | PT SINERGI REKTA DENTA | 12 | Mitratel | 2016-09-13 | 2026-09-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 11 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
208 | Area 2 | R03 Jabotabek Inner | 3 | JTX257 | JTX257 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0117 | JATINEGARAKAUMSELATANDMT | 106.8984 | -6.2088 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT PERSADA SOKKA TAMA | PT SAMANTA FIBRA ABADI | 0 | Mitratel | 2016-09-13 | 2026-09-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend 3m
209 | Area 2 | R03 Jabotabek Inner | 3 | JTX291 | JTX291 | 25TS08N2013 | Jabat | #N/A | #N/A | 25TS08N2013 | 25TS12Z0122 | TAMANDURENSAWITDMT | 106.9103 | -6.2437 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INDOJAR MULIA ABADI | PT INDOJAR MULIA ABADI | 2 | Mitratel | 2016-09-13 | 2026-09-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 5 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend 3m
210 | Area 2 | R03 Jabotabek Inner | 3 | JSX351 | JSX351 |  | Jabat | #N/A | #N/A | NY | 25TS12B0107 | RELOCSWADARMDMT | 106.7572 | -6.2313 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INTEGRA LINTAS TEKNOLOGI | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | 0 | Mitratel | 2016-09-13 | 2026-09-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
211 | Area 2 | R03 Jabotabek Inner | 3 | JBX195 | JBX195 | 25TS08N1992 |  | #N/A | #N/A | 25TS08N1992 | #N/A | POSPALMERAHBARATDMT | 106.7969 | -6.2081 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-09-13 | 2026-09-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
212 | Area 2 | R03 Jabotabek Inner | 3 | JTX510 | JTX510 |  | Jabat | #N/A | #N/A | NY | 25TS12B0038 | KOMPLEKKEBAKARANDMT | 106.8791 | -6.3313 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MULTI BAGASANTI MAHDY | PT MULTI BAGASANTI MAHDY | 9 | Mitratel | 2018-08-17 | 2028-08-16 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 100m 250 Degree
213 | Area 2 | R03 Jabotabek Inner | 3 |  | JPX173 |  |  | #N/A | #N/A | NY | #N/A | CPPUTIHTENGAH27A | 106.8722 | -6.1742 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-09-14 | 2026-09-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
214 | Area 2 | R03 Jabotabek Inner | 3 | JSX498 | JSX498 | 25TS08N2035 | Jabat | #N/A | #N/A | 25TS08N2035 | 25TS12B0112 | KEMANGDALAMDMT | 106.819 | -6.2712 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INTEGRA LINTAS TEKNOLOGI | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | 0 | Mitratel | 2016-09-22 | 2026-09-21 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
215 | Area 2 | R03 Jabotabek Inner | 3 | JTX211 | JTX211 |  | Jabat | #N/A | #N/A | NY | 25TS12B0015 | KESATRIAN3DMT | 106.869 | -6.2017 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MULTI BAGASANTI MAHDY | PT MULTI BAGASANTI MAHDY | 8 | Mitratel | 2016-10-06 | 2026-10-05 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 11 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 170m arah 150 degree
216 | Area 2 | R03 Jabotabek Inner | 3 | JUX265 | JUX265 |  | Jabat | #N/A | #N/A | NY | 25TS12B0100 | PERTAMINADEPOPLUMPANGDMT | 106.9012 | -6.1342 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DENTRA MITRA ABADI | PT DENTRA MITRA ABADI | 3 | Mitratel | 2016-10-13 | 2026-10-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | Arah 200m 300 degree
217 | Area 2 | R03 Jabotabek Inner | 3 | JSX486 | JSX486 |  | Jabat | #N/A | #N/A | NY | 25TS12B0014 | TANGKASPESANGGRAHANDMT | 106.7595 | -6.2486 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INTEGRA LINTAS TEKNOLOGI | PT JAGANATA SAKTI UNGGUL | 0 | Mitratel | 2016-10-18 | 2026-10-17 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
218 | Area 2 | R03 Jabotabek Inner | 3 | JUX247 | JUX247 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0128 | JALANANANTARAYADMT | 106.9226 | -6.1322 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT AGUNGMAS PRIMA SEMPURNA | PT SUMBERSOLUSINDO HITECH | 17 | Mitratel | 2016-10-19 | 2026-10-18 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend 3m
219 | Area 2 | R03 Jabotabek Inner | 3 | JTX215 | JTX215 | 25TS08N2044 | Jabat | #N/A | #N/A | 25TS08N2044 | 25TS12Z0127 | ARABIKA8DMT | 106.945 | -6.2311 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT PERSADA SOKKA TAMA | CV LUXLO KARYA GEMILANG | 0 | Mitratel | 2016-10-24 | 2026-10-23 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend 3m
220 | Area 2 | R03 Jabotabek Inner | 3 | JSX791 | JSX791 |  | Jabat | #N/A | #N/A | NY | 25TS12B0048 | SEKOLAHDUTA2DMT | 106.7893 | -6.2862 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SUMBERSOLUSINDO HITECH | PT JAGANATA SAKTI UNGGUL | 10 | Mitratel | 2016-10-24 | 2026-10-23 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arahan Quadran 2 & 3 (dekat sekolah SAR 150m)
221 | Area 2 | R03 Jabotabek Inner | 3 | JBX235 | JBX235 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0123 | BANDENGANUTARAGEDONGDMT | 106.8037 | -6.1348 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT JAGANATA SAKTI UNGGUL | PT SINERGI REKTA DENTA | 6 | Mitratel | 2016-10-25 | 2026-10-24 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 12 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
222 | Area 2 | R03 Jabotabek Inner | 3 | JBX202 | JBX202 |  | Jabat | #N/A | #N/A | NY | 25TS12B0110 | JLMERUYAILIRRAYAUTARADMT | 106.7533 | -6.1975 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT AGUNGMAS PRIMA SEMPURNA | PT AGUNGMAS PRIMA SEMPURNA | 17 | Mitratel | 2016-10-27 | 2026-10-26 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 12 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
223 | Area 2 | R03 Jabotabek Inner | 3 | JBX207 | JBX207 |  | Jabat | #N/A | #N/A | NY | 25TS12B0111 | SATUMARETKALIDERESDMT | 106.7038 | -6.1291 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT AGUNGMAS PRIMA SEMPURNA | PT AGUNGMAS PRIMA SEMPURNA | 16 | Mitratel | 2016-11-02 | 2026-11-01 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 7 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
224 | Area 2 | R03 Jabotabek Inner | 3 | JBX178 | JBX178 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0125 | JALANDAANMOGOTDMT | 106.7187 | -6.1531 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SUMBERSOLUSINDO HITECH | PT SINERGI REKTA DENTA | 10 | Mitratel | 2016-11-03 | 2026-11-02 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 7 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend Pole
225 | Area 2 | R03 Jabotabek Inner | 3 | JBX197 | JBX197 | 25TS08N1973 | Jabat | #N/A | #N/A | 25TS08N1973 | 25TS12B0109 | BUDHIBATUSARIDMT | 106.7817 | -6.1878 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT AGUNGMAS PRIMA SEMPURNA | PT AGUNGMAS PRIMA SEMPURNA | 15 | Mitratel | 2016-11-07 | 2026-11-06 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
226 | Area 2 | R03 Jabotabek Inner | 3 | JBX386 | JBX386 | 24TS12N0420 | Jabat | #N/A | #N/A | 24TS12N0420 | 25TS12B0022 | STADIONCENDRAWASIHDMT | 106.7201 | -6.1434 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT NAER TUNAS INDONESIA | PT NAER TUNAS INDONESIA | 7 | Mitratel | 2018-08-20 | 2028-08-19 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 310' 150m
227 | Area 2 | R03 Jabotabek Inner | 3 | JBX200 | JBX200 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0126 | PURILINGKARLUARDMT | 106.736 | -6.1911 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SUMBERSOLUSINDO HITECH | PT INFRAKO DAYAMITRA | 10 | Mitratel | 2016-11-21 | 2026-11-20 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 10 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend Pole
228 | Area 2 | R03 Jabotabek Inner | 3 |  | JTX611 | #N/A |  | #N/A | #N/A | NY | #N/A | RELOCBATUAMPAR ex NUSA1KRAMATJATI | 106.858 | -6.2935 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2018-09-19 | 2028-09-18 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
229 | Area 2 | R03 Jabotabek Inner | 3 | JUX209 | JUX209 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0093 | JLWARAKAS4DMT | 106.8797 | -6.1208 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT AGUNGMAS PRIMA SEMPURNA | PT SUMBERSOLUSINDO HITECH | 14 | Mitratel | 2016-12-06 | 2026-12-05 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Done DRM
230 | Area 2 | R03 Jabotabek Inner | 3 | JTX471 | JTX471 |  | Jabat | #N/A | #N/A | NY | #N/A | DEPNAKER2DMT | 106.8518 | -6.2863 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DESATRIA ALARD MANDIRI | 0 | 3 | Mitratel | 2016-12-15 | 2026-12-14 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
231 | Area 1 | R10 Sumbagteng | 10 | PBR992 | PBR992 | 25TS07Z0001 | R10 Sumbagteng | 0 | #N/A | 25TS07Z0001 | #N/A | N_PBR992HL1_KAWASANUINSUSKA6DMT | 101.3647 | 0.46261 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-06-30 | 2025-06-29 | 2025-09-27 | 2025-10-27 | -30 | Out SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-1 | RFI | RFI | RFI |  | done
232 | Area 2 | R03 Jabotabek Inner | 3 | JTX359 | JTX359 |  | Jabat | #N/A | #N/A | NY | 25TS12B0042 | PINTUUTAMATMIIDMT | 106.8867 | -6.3019 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MANDAU JAYA KONTRINDO | PT MANDAU JAYA KONTRINDO | 5 | Mitratel | 2017-01-17 | 2027-01-16 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 7 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Monopole 25m
233 | Area 2 | R03 Jabotabek Inner | 3 | JTX294 | JTX294 |  | Jabat | #N/A | #N/A | NY | 25TS12B0046 | JLNAMALIACAKUNGDMT | 106.9327 | -6.2093 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DYEVA DIGITAL SELULAR | PT DYEVA DIGITAL SELULAR | 2 | Mitratel | 2017-03-31 | 2027-03-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 170m arah 140 degree
234 | Area 2 | R03 Jabotabek Inner | 3 | JTX398 | JTX398 |  | Jabat | #N/A | #N/A | NY | 25TS12B0012 | LAPANGANKENANGADMT | 106.9 | -6.3149 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SAMANTA FIBRA ABADI | PT SAMANTA FIBRA ABADI | 8 | Mitratel | 2017-04-01 | 2027-03-31 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 200m arah 275 degree
235 | Area 2 | R03 Jabotabek Inner | 3 | JTX382 | JTX382 |  | Jabat | #N/A | #N/A | NY | 25TS12B0043 | NUSAINDAHMALAKADMT | 106.9334 | -6.2179 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MANDAU JAYA KONTRINDO | PT MANDAU JAYA KONTRINDO | 4 | Mitratel | 2017-04-04 | 2027-04-03 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Lahan Masjid
236 | Area 2 | R03 Jabotabek Inner | 3 | JBX286 | JBX286 |  | Jabat | #N/A | #N/A | NY | 25TS12B0025 | JLPANJANGKODAYATURDMT | 106.7629 | -6.1618 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT JAGANATA SAKTI UNGGUL | PT JAGANATA SAKTI UNGGUL | 6 | Mitratel | 2017-04-10 | 2027-04-09 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 4 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 170m arah 230 degree
237 | Area 2 | R03 Jabotabek Inner | 3 | JKP233 | JKP233 |  | Jabat | #N/A | #N/A | NY | 25TS12B0032 | CEMPAKAPUTIHRAYADMT | 106.8683 | -6.1763 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INFRAKO DAYAMITRA | PT INFRAKO DAYAMITRA | 8 | Mitratel | 2017-04-13 | 2027-04-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 150m arah 90 degree
238 | Area 1 | R10 Sumbagteng | 10 | PBR981 | PBR981 | 25TS07Z0002 | R10 Sumbagteng | 0 | #N/A | 25TS07Z0002 | #N/A | PBR981HM1_JLDIPONEGORODMT | 101.4506 | 0.52314 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-07-14 | 2025-07-13 | 2025-10-11 | 2025-10-27 | -16 | Out SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-1 | RFI | RFI | RFI |  | done
239 | Area 2 | R03 Jabotabek Inner | 3 | JTX381 | JTX381 | 24TS08Z0002 |  | #N/A | #N/A | 24TS08Z0002 | #N/A | UTANKAYUUTRMATRAMANINDAHDMT | 106.8595 | -6.1955 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | PT Sinergi Rektadenta |  | Mitratel | 2017-05-13 | 2027-05-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | RFI | RFI | RFI | Solution, menggunakan project Solution, terkait project program pembebasan untuk LRT, on air |  |  | #N/A | #N/A | #N/A
240 | Area 2 | R03 Jabotabek Inner | 3 | JTX207 | JTX207 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0129 | JLMAKASARJAKTIMDMT | 106.8763 | -6.2687 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT PERSADA SOKKA TAMA | CV LUXLO KARYA GEMILANG | 0 | Mitratel | 2017-05-13 | 2027-05-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 11 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Extend Tower | 0 | 0 | 0 | Continue Renewal Eksisting (perizinan Bandara)
241 | Area 2 | R03 Jabotabek Inner | 3 | JTX206 | JTX206 |  | Jabat | #N/A | #N/A | NY | 25TS12B0047 | JLMUSACIPINANGMUARADMT | 106.8893 | -6.2238 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT CIPTA KARSA ANUGERAH SEMESTA | PT CIPTA KARSA ANUGERAH SEMESTA | 3 | Mitratel | 2017-05-13 | 2027-05-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 150m arah 270 degree
242 | Area 2 | R03 Jabotabek Inner | 3 | JKT417 | JKT417 |  | Jabat | #N/A | #N/A | NY | 25TS12B0030 | MASJIDANNURBUARANDMT | 106.9211 | -6.2189 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT CIPTA KARSA ANUGERAH SEMESTA | PT CIPTA KARSA ANUGERAH SEMESTA | 2 | Mitratel | 2017-05-24 | 2027-05-23 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 100m arah Selatan
243 | Area 1 | R10 Sumbagteng | 10 | PAD660 | PAD660 | 25TS07Z0003 | R10 Sumbagteng | 0 | #N/A | 25TS07Z0003 | #N/A | STOPADANGKANTORGUBERNUR | 100.3622 | -0.93969 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-07-22 | 2025-07-21 | 2025-10-19 | 2025-11-30 | -42 | Out SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-1 | RFC | RFC | OG | [30/10/25] Plan Eksekusi W4 Nov 19/07/25 Wait Dok. RFIN Plan 21/07 | 2025-12-18 | Type-1
244 | Area 2 | R03 Jabotabek Inner | 3 | JBX262 | JBX262 |  | Jabat | #N/A | #N/A | NY | 25TS12B0013 | GOLDENARCHYSAKTIDMT | 106.7628 | -6.1538 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT JAGANATA SAKTI UNGGUL | PT JAGANATA SAKTI UNGGUL | 5 | Mitratel | 2017-06-13 | 2027-06-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | [30/10/25] Plan Eksekusi W4 Nov 19/07/25 Wait Dok. RFIN Plan 21/07 |  | BTR | 0 | 0 | 0 | BTR Ruko
245 | Area 2 | R03 Jabotabek Inner | 3 | JSX470 | JSX470 |  | Jabat | #N/A | #N/A | NY | 25TS12B0052 | LEBAKSARITJBARATDMT | 106.8534 | -6.3024 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MITRA SARANA KARYA BANGSA | PT AGUNGMAS PRIMA SEMPURNA | 1 | Mitratel | 2017-06-13 | 2027-06-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | [30/10/25] Plan Eksekusi W4 Nov [9/09/25] Proses Fabrikan Ring mounting + Rack Gendong + Bracket Panel KWH + ACPDB [20/07/2025] Submit Dok.RFIN done |  | BTR | 0 | 0 | 0 | 280m arah 0 (106.852667 -6.298361 )
246 | Area 1 | R10 Sumbagteng | 10 | PBR441 | PBR441 | 25TS07Z0004 | R10 Sumbagteng | 0 | #N/A | 25TS07Z0004 | #N/A | PBR441HW1_KAWASANUINSUSKA5DMT | 101.3753 | 0.47552 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-07-23 | 2025-07-22 | 2025-10-20 | 2025-11-30 | -41 | Out SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-1 | RFI | RFI | RFI | [30/10/25] Plan Eksekusi W4 Nov [9/09/25] Proses Fabrikan Ring mounting + Rack Gendong + Bracket Panel KWH + ACPDB [20/07/2025] Submit Dok.RFIN done | done
247 | Area 2 | R03 Jabotabek Inner | 3 | JPX188 | JPX188 |  | Jabat | #N/A | #N/A | NY | 25TS12B0060 | JALANWAHIDHASYIMDMT | 106.8201 | -6.1871 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INFRAKO DAYAMITRA | PT INFRAKO DAYAMITRA | 7 | Mitratel | 2017-06-13 | 2027-06-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | [30/10/25] Plan Eksekusi W4 Nov [9/09/25] Proses Fabrikan Ring mounting + Rack Gendong + Bracket Panel KWH + ACPDB [20/07/2025] Submit Dok.RFIN done |  | collo | 0 | 0 | 0 | Reloc Ke Tower terdekat Need Panoramic site terdekat 16HC09W0004 Wahid Hasyim('106.81996 '-6.18664)
248 | Area 2 | R03 Jabotabek Inner | 3 | JBX239 | JBX239 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0096 | CITRAGARDENCITYSECTOR6DMT | 106.7153 | -6.128 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SUMBERSOLUSINDO HITECH | PT INFRAKO DAYAMITRA | 9 | Mitratel | 2017-06-14 | 2027-06-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | [30/10/25] Plan Eksekusi W4 Nov [9/09/25] Proses Fabrikan Ring mounting + Rack Gendong + Bracket Panel KWH + ACPDB [20/07/2025] Submit Dok.RFIN done |  | Extend Tower | 0 | 0 | 0 | Extend 3m
249 | Area 2 | R03 Jabotabek Inner | 3 | JPX186 | JPX186 |  | Jabat | #N/A | #N/A | NY | 25TS12B0019 | JLPSGEMBRONGDMT | 106.8546 | -6.1805 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | PT INFRAKO DAYAMITRA | 2 | Mitratel | 2017-07-04 | 2027-07-03 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 100m arah barat ruko depan alfamart
250 | Area 2 | R03 Jabotabek Inner | 3 | JBX294 | JBX294 |  | Jabat | #N/A | #N/A | NY | 25TS12B0021 | DEPLUJOGLOJAKBARDMT | 106.7328 | -6.2185 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SUMBERSOLUSINDO HITECH | PT SUMBERSOLUSINDO HITECH | 9 | Mitratel | 2017-07-04 | 2027-07-03 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | Need Survey Extend
251 | Area 2 | R03 Jabotabek Inner | 3 | JKP231 | JKP231 |  | Jabat | #N/A | #N/A | NY | 25TS12B0029 | CEMPAKABARUBARATDMT | 106.8585 | -6.1716 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INFRAKO DAYAMITRA | PT INFRAKO DAYAMITRA | 4 | Mitratel | 2017-07-04 | 2027-07-03 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 200m arah 90 degree
252 | Area 2 | R03 Jabotabek Inner | 3 | JTX410 | JTX410 |  | Jabat | #N/A | #N/A | NY | 25TS12B0041 | PALEMKARTIKAKOMPLEKTNIADDMT | 106.8992 | -6.312 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SAMANTA FIBRA ABADI | PT SAMANTA FIBRA ABADI | 7 | Mitratel | 2017-08-01 | 2027-07-31 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 300m arah 270 degree
253 | Area 2 | R03 Jabotabek Inner | 3 | JSX409 | JSX409 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0103 | JLRAYAMAJADMT | 106.7993 | -6.2663 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INFRAKO DAYAMITRA | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | 3 | Mitratel | 2017-08-01 | 2027-07-31 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend 3m
254 | Area 2 | R03 Jabotabek Inner | 3 | JBX290 | JBX290 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0097 | JLJERUKSEGARDMT | 106.736 | -6.2034 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SUMBERSOLUSINDO HITECH | PT NAER TUNAS INDONESIA | 8 | Mitratel | 2017-08-04 | 2027-08-03 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 7 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend 3m
255 | Area 2 | R03 Jabotabek Inner | 3 | JBX293 | JBX293 |  | Jabat | #N/A | #N/A | NY | 25TS12B0026 | JLBENDAKAMALDMT | 106.7003 | -6.1075 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT NAER TUNAS INDONESIA | PT NAER TUNAS INDONESIA | 5 | Mitratel | 2017-08-04 | 2027-08-03 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 150m arah 0 degree
256 | Area 2 | R03 Jabotabek Inner | 3 | JTX310 | JTX310 |  | Jabat | #N/A | #N/A | NY | 25TS12B0050 | KLENDERDURENSAWITDMT | 106.9094 | -6.2178 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DYEVA DIGITAL SELULAR | PT MULTI BAGASANTI MAHDY | 1 | Mitratel | 2017-08-04 | 2027-08-03 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 200m arah 180 degree
257 | Area 2 | R03 Jabotabek Inner | 3 | JPX187 | JPX187 |  | Jabat | #N/A | #N/A | NY | 25TS12B0016 | JLLUMBALUMBADMT | 106.8648 | -6.1673 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | PT INFRAKO DAYAMITRA | 1 | Mitratel | 2017-08-11 | 2027-08-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 7 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR lapangan
258 | Area 2 | R03 Jabotabek Inner | 3 | JBX263 | JBX263 |  |  | #N/A | #N/A | NY | #N/A | PASARDARURATKAPUKDMT | 106.7461 | -6.135 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-08-11 | 2027-08-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
259 | Area 2 | R03 Jabotabek Inner | 3 | JBX288 | JBX288 |  | Jabat | #N/A | #N/A | NY | 25TS12B0018 | JLHSUAIBKBJERUKDMT | 106.7724 | -6.2007 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT NAER TUNAS INDONESIA | PT NAER TUNAS INDONESIA | 4 | Mitratel | 2017-08-14 | 2027-08-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 180m arah 270 degree
260 | Area 2 | R03 Jabotabek Inner | 3 | JTX383 | JTX383 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0101 | MELATIASEMGEDEMATRAMANDMT | 106.8561 | -6.2088 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INFRAKO DAYAMITRA | PT SAMANTA FIBRA ABADI | 2 | Mitratel | 2017-09-06 | 2027-09-05 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend 3m
261 | Area 2 | R03 Jabotabek Inner | 3 | JSX395 | JSX395 |  | Jabat | #N/A | #N/A | NY | 25TS12B0017 | LURAHKEBONBARUDMT | 106.8597 | -6.2328 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MULTI BAGASANTI MAHDY | PT JAGANATA SAKTI UNGGUL | 6 | Mitratel | 2017-09-11 | 2027-09-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 150m arah 90 degree
262 | Area 2 | R03 Jabotabek Inner | 3 | JTX208 | JTX208 |  | Jabat | #N/A | #N/A | NY | #N/A | KEBUNBUNGADMT | 106.9332 | -6.2145 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT PERSADA SOKKA TAMA | 0 | 0 | Mitratel | 2017-09-11 | 2027-09-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend 3m
263 | Area 2 | R03 Jabotabek Inner | 3 | JTX327 | JTX327 |  | Jabat | #N/A | #N/A | NY | 25TS12B0049 | POMADPASARREBODMT | 106.8448 | -6.3284 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT CELEBES KONTRUKSINDO | PT MULTI BAGASANTI MAHDY | 3 | Mitratel | 2017-09-11 | 2027-09-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 200m arah 90 degree
264 | Area 2 | R03 Jabotabek Inner | 3 | JKB919 | JKB919 |  | Jabat | #N/A | #N/A | NY | 25TS12B0024 | JLJATI1DMT | 106.7361 | -6.1464 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INTERTEL MEDIA PRIMA | PT INTERTEL MEDIA PRIMA | 5 | Mitratel | 2017-09-13 | 2027-09-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 150m arah 90 degree
265 | Area 2 | R03 Jabotabek Inner | 3 | JTX408 | JTX408 |  | Jabat | #N/A | #N/A | NY | 25TS12B0037 | JAYASAKTI3DMT | 106.8598 | -6.3352 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SAMANTA FIBRA ABADI | PT SAMANTA FIBRA ABADI | 5 | Mitratel | 2017-09-14 | 2027-09-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 200m arah 90 degree
266 | Area 2 | R03 Jabotabek Inner | 3 | JTX379 | JTX379 |  | Jabat | #N/A | #N/A | NY | 25TS12B0044 | MAKASARKRAMATJATIDMT | 106.8738 | -6.2788 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MANDAU JAYA KONTRINDO | PT MANDAU JAYA KONTRINDO | 3 | Mitratel | 2017-09-14 | 2027-09-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 200m arah 90 degree
267 | Area 2 | R03 Jabotabek Inner | 3 | JBX271 | JBX271 |  | Jabat | #N/A | #N/A | NY | 25TS12B0020 | TAMANKOTAPEDONGKELANDMT | 106.76 | -6.1596 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT JAGANATA SAKTI UNGGUL | PT JAGANATA SAKTI UNGGUL | 3 | Mitratel | 2017-10-12 | 2027-10-11 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 170m arah 150 degree
268 | Area 2 | R03 Jabotabek Inner | 3 | JUX051 | JUX051 |  | Jabat | #N/A | #N/A | NY | #N/A | PELABUHANKALIADEMPLUITDMT | 106.7718 | -6.1052 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT GEAF SOLUSIANDA PRATAMA | 0 | 5 | Mitratel | 2017-10-18 | 2027-10-17 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 200m arah 300 degree
269 | Area 2 | R03 Jabotabek Inner | 3 | JSX574 | JSX574 |  |  | #N/A | #N/A | NY | #N/A | TEGALPARANGUTARAMAMPANGDMT | 106.8198 | -6.2612 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-11-03 | 2027-11-02 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
270 | Area 2 | R03 Jabotabek Inner | 3 | JPX199 | JPX199 |  |  | #N/A | #N/A | NY | #N/A | UTANPANJANGDMT | 106.8554 | -6.1642 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-11-15 | 2027-11-14 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
271 | Area 2 | R03 Jabotabek Inner | 3 | JTX452 | JTX452 |  | Jabat | #N/A | #N/A | NY | 25TS12B0040 | LAPANGANGOLFCILANGKAPDMT | 106.8916 | -6.3168 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DESATRIA ALARD MANDIRI | PT DESATRIA ALARD MANDIRI | 3 | Mitratel | 2017-12-14 | 2027-12-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 200m arah 90 degree
272 | Area 2 | R03 Jabotabek Inner | 3 | JPX211 | JPX211 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0104 | JLKEBONSIRIHMENTENGDMT | 106.8276 | -6.1848 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT ANUGERAH SELARAS RAYA | PT ANUGERAH SELARAS RAYA | 3 | Mitratel | 2017-12-14 | 2027-12-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 5 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend Pole 10m (Need Survey dan cek pondasi pole)
273 | Area 2 | R03 Jabotabek Inner | 3 | JUX377 | JUX377 |  | Jabat | #N/A | #N/A | NY | 25TS12B0067 | GARDENMARBEL1DMT | 106.9187 | -6.1344 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT GEAF SOLUSIANDA PRATAMA | PT GEAF SOLUSIANDA PRATAMA | 5 | Mitratel | 2017-12-14 | 2027-12-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 200m arah 270 degree
274 | Area 2 | R03 Jabotabek Inner | 3 | JUX369 | JUX369 |  |  | #N/A | #N/A | NY | #N/A | MSJDALJIHADDMT | 106.9112 | -6.1129 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-12-29 | 2027-12-28 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
275 | Area 2 | R03 Jabotabek Inner | 3 | JTX396 | JTX396 |  |  | #N/A | #N/A | NY | #N/A | RAWAGEMILANGLIMADMT | 106.9114 | -6.1999 | Non MKT | Non MKT | 0 | Non-HBTS | MITRATEL | #N/A | #N/A |  | Mitratel | 2018-01-11 | 2028-01-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
276 | Area 2 | R03 Jabotabek Inner | 3 | JTX395 | JTX395 | 25TS08N1768 |  | #N/A | #N/A | 25TS08N1768 | #N/A | KYOESTEELDMT | 106.9092 | -6.1961 | Non MKT | Non MKT | 0 | Non-HBTS | MITRATEL | #N/A | #N/A |  | Mitratel | 2018-01-12 | 2028-01-11 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
277 | Area 2 | R03 Jabotabek Inner | 3 | JTX391 | JTX391 |  |  | #N/A | #N/A | NY | #N/A | RAWASUMURBARATDMT | 106.9147 | -6.2066 | Non MKT | Non MKT | 0 | Non-HBTS | MITRATEL | #N/A | #N/A |  | Mitratel | 2018-01-12 | 2028-01-11 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
278 | Area 2 | R03 Jabotabek Inner | 3 | JTX388 | JTX388 |  |  | #N/A | #N/A | NY | #N/A | RAWAPULOKAMBINGDMT | 106.9106 | -6.19 | Non MKT | Non MKT | 0 | Non-HBTS | MITRATEL | #N/A | #N/A |  | Mitratel | 2018-01-12 | 2028-01-11 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
279 | Area 1 | R10 Sumbagteng | 10 | PBR985 | PBR985 | 25TS07Z0021 | R10 Sumbagteng | 0 | #N/A | 25TS07Z0021 | #N/A | PBR985HL1_SPLITPBR007GDMT | 101.4585 | 0.5105 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-07-31 | 2025-07-30 | 2025-10-28 | 2025-11-30 | -33 | Out SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-1 | RFI | RFI | RFI | 05. RFI | done
280 | Area 1 | R10 Sumbagteng | 10 | PBR380 | PBR380 | 25TS07Z0005 | R10 Sumbagteng | 0 | #N/A | 25TS07Z0005 | #N/A | PBR380HL1_PASARBUAHDMT | 101.4182 | 0.46827 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-05 | 2025-08-04 | 2025-11-02 | 2025-11-30 | -28 | Out SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-1 | RFI | RFI | RFI | 05. RFI | done
281 | Area 1 | R10 Sumbagteng | 10 | PBR383 | PBR383 |  | R10 Sumbagteng | 0 | #N/A | 25TS07Z0006 | #N/A | PBR383HL1_JALANSUKARNOHATTADMT | 101.4192 | 0.46611 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-14 | 2025-08-13 | 2025-11-11 | 2025-08-26 | 77 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-1 | RFI | RFI | RFI |  | done
282 | Area 1 | R10 Sumbagteng | 10 | PBR993 | PBR993 | 25TS07Z0007 | R10 Sumbagteng | 0 | #N/A | 25TS07Z0007 | #N/A | PBR993HL1_JALANSUKARNOHATTA3DMT | 101.4197 | 0.51382 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-14 | 2025-08-13 | 2025-11-11 | 2025-08-26 | 77 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-1 | RFI | RFI | RFI |  | done
283 | Area 2 | R03 Jabotabek Inner | 3 | JTX419 | JTX419 |  | Jabat | #N/A | #N/A | NY | 25TS12B0036 | HAJIYAHYAKPMELAYUDMT | 106.8748 | -6.3404 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SAMANTA FIBRA ABADI | PT SAMANTA FIBRA ABADI | 4 | Mitratel | 2018-02-13 | 2028-02-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 320m 0 degree
284 | Area 2 | R03 Jabotabek Inner | 3 | JTX418 | JTX418 |  | Jabat | #N/A | #N/A | NY | 25TS12B0070 | RAYAJENGKIKEBONPALADMT | 106.8693 | -6.2505 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SAMANTA FIBRA ABADI | PT SAMANTA FIBRA ABADI | 3 | Mitratel | 2018-02-13 | 2028-02-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 110 degree arah 120m
285 | Area 2 | R03 Jabotabek Inner | 3 | JUX053 | JUX053 |  | Jabat | #N/A | #N/A | NY | 25TS12B0082 | ATTAQWATUGUPERMAIDMT | 106.9104 | -6.1269 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT AJIAN TRI SUKSES | PT AJIAN TRI SUKSES | 4 | Mitratel | 2018-04-05 | 2028-04-04 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 100m 90 degree
286 | Area 2 | R03 Jabotabek Inner | 3 | JTX397 | JTX397 |  | Jabat | #N/A | #N/A | NY | 25TS12B0081 | TOLBAMBUAPUSTIMURDUADMT | 106.8985 | -6.3091 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MANDAU JAYA KONTRINDO | PT MANDAU JAYA KONTRINDO | 2 | Mitratel | 2018-04-06 | 2028-04-05 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 130 Degree 120m
287 | Area 2 | R03 Jabotabek Inner | 3 | JPX178 | JPX178 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0111 | JLPERCETAKANNEGARADMT | 106.8567 | -6.1885 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT ANUGERAH SELARAS RAYA | PT ANUGERAH SELARAS RAYA | 2 | Mitratel | 2018-04-13 | 2028-04-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Extend Tower | 0 | 0 | 0 | Extend 3m
288 | Area 2 | R03 Jabotabek Inner | 3 | JPX193 | JPX193 |  |  | #N/A | #N/A | NY | #N/A | KRAMATLIMADMT | 106.8438 | -6.1881 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2018-04-13 | 2028-04-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
289 | Area 2 | R03 Jabotabek Inner | 3 | JBX266 | JBX266 |  | Jabat | #N/A | #N/A | NY | 25TS12B0074 | KEBONJERUKINDAHUTAMADMT | 106.7609 | -6.2032 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT JAGANATA SAKTI UNGGUL | PT JAGANATA SAKTI UNGGUL | 2 | Mitratel | 2018-05-13 | 2028-05-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 0 degree Arah 100m
290 | Area 2 | R03 Jabotabek Inner | 3 | JSX408 | JSX408 |  | Jabat | #N/A | #N/A | NY | 25TS12B0079 | JLDUKUCILEDUGDMT | 106.7566 | -6.2296 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT CELEBES KONTRUKSINDO | PT CELEBES KONTRUKSINDO | 3 | Mitratel | 2018-05-13 | 2028-05-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | arah 100m 230 degree
291 | Area 2 | R03 Jabotabek Inner | 3 | JSX536 | JSX536 |  | Jabat | #N/A | #N/A | NY | 25TS12B0077 | PDKLABUCILANDAKDMT | 106.7936 | -6.3069 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT PERSADA SOKKA TAMA | PT VALUE TELECOMMUNICATION | 0 | Mitratel | 2018-05-13 | 2028-05-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | Arah 110m 320 degree
292 | Area 2 | R03 Jabotabek Inner | 3 | JTX387 | JTX387 |  | Jabat | #N/A | #N/A | NY | 25TS12B0083 | BUNGARAMPAIDMT | 106.9346 | -6.2215 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MANDAU JAYA KONTRINDO | PT MANDAU JAYA KONTRINDO | 1 | Mitratel | 2018-05-13 | 2028-05-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 120 Degree 110m
293 | Area 2 | R03 Jabotabek Inner | 3 | JUX347 | JUX347 |  | Jabat | #N/A | #N/A | NY | 25TS12B0085 | IMPERIALGADINGDMT | 106.9222 | -6.1603 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT AJIAN TRI SUKSES | PT AJIAN TRI SUKSES | 3 | Mitratel | 2018-05-13 | 2028-05-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 150m 350 degree
294 | Area 2 | R03 Jabotabek Inner | 3 | JBX268 | JBX268 |  | Jabat | #N/A | #N/A | NY | 25TS12B0068 | KPSALOKEMBANGANDMT | 106.7541 | -6.1635 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT JAGANATA SAKTI UNGGUL | PT JAGANATA SAKTI UNGGUL | 1 | Mitratel | 2018-05-24 | 2028-05-23 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 50m 310 degree
295 | Area 2 | R03 Jabotabek Inner | 3 | JBX292 | JBX292 |  | Jabat | #N/A | #N/A | NY | 25TS12B0069 | SURWAWIDURIKEDOYADMT | 106.7627 | -6.1766 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT NAER TUNAS INDONESIA | PT NAER TUNAS INDONESIA | 3 | Mitratel | 2018-05-24 | 2028-05-23 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 4 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah Sekolah Ichtus dan arah utara 150m ketinggian 30m
296 | Area 2 | R03 Jabotabek Inner | 3 | JSX510 | JSX510 |  | Jabat | #N/A | #N/A | NY | 25TS12B0080 | KESEHATANRYBINTARODMT | 106.761 | -6.2706 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT PERSADA SOKKA TAMA | PT TRIPUTRA SURYA SEJAHTERA | 0 | Mitratel | 2018-06-05 | 2028-06-04 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | SAR 100 quadran 3
297 | Area 2 | R03 Jabotabek Inner | 3 | JSA035 | JSA035 |  | Jabat | #N/A | #N/A | NY | 25TS12B0056 | GRENINTANRESIDENCEDMT | 106.8044 | -6.2666 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MITRA SARANA KARYA BANGSA | PT AGUNGMAS PRIMA SEMPURNA | 1 | Mitratel | 2018-06-08 | 2028-06-07 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 70' 150m
298 | Area 1 | R01 Sumbagut | 1 | MDX505 | MDX505 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0063 | MC KIM BELAWAN-6 | 98.6877 | 3.6689 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT M JUSUF & SONS |  | Mitratel | 2016-11-11 | 2026-11-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 9 RRU Remove 6 RRU Final Sow Rescope: 3. reheight tower
299 | Area 2 | R03 Jabotabek Inner | 3 | JSX413 | JSX413 |  | Jabat | #N/A | #N/A | NY | 25TS12B0076 | JALANKHROYANIDMT | 106.8226 | -6.2186 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT PERSADA SOKKA TAMA | PT VALUE TELECOMMUNICATION | 0 | Mitratel | 2018-06-14 | 2028-06-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | Arah 70m 290 degree
300 | Area 2 | R03 Jabotabek Inner | 3 | JTX204 | JTX204 |  |  | #N/A | #N/A | NY | #N/A | RELOCPULOGBPERMAIDMT | 106.9523 | -6.2005 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2018-06-14 | 2028-06-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
301 | Area 2 | R03 Jabotabek Inner | 3 | JUX048 | JUX048 |  | Jabat | #N/A | #N/A | NY | 25TS12B0084 | JLSWATIRTAKBBAWANGDMT | 106.885 | -6.1203 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT GEAF SOLUSIANDA PRATAMA | PT GEAF SOLUSIANDA PRATAMA | 4 | Mitratel | 2018-06-14 | 2028-06-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 340 Degree arah 60m
302 | Area 2 | R03 Jabotabek Inner | 3 | JSX951 | JSX951 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0113 | GURUMUHYINDMT | 106.8378 | -6.3153 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | 1 | Mitratel | 2018-06-28 | 2028-06-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Extend Tower | 0 | 0 | 0 | Extend 3m
303 | Area 2 | R03 Jabotabek Inner | 3 | JBX393 | JBX393 |  | Jabat | #N/A | #N/A | NY | 25TS12B0023 | JLJAYA25CENGKARENGDMT | 106.7232 | -6.1288 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INTERTEL MEDIA PRIMA | PT INTERTEL MEDIA PRIMA | 4 | Mitratel | 2018-08-03 | 2028-08-02 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 7 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 260' 90m
304 | Area 2 | R03 Jabotabek Inner | 3 | JBX407 | JBX407 |  | Jabat | #N/A | #N/A | NY | 25TS12B0028 | JLPELOPORTEGALALURDMT | 106.7169 | -6.1232 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INTERTEL MEDIA PRIMA | PT INTERTEL MEDIA PRIMA | 3 | Mitratel | 2018-08-03 | 2028-08-02 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 60m 220 Degree
305 | Area 2 | R03 Jabotabek Inner | 3 | JUX401 | JUX401 |  | Jabat | #N/A | #N/A | NY | 25TS12B0034 | KALIBARUTIMUR5DMT | 106.9345 | -6.0995 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DENTRA MITRA ABADI | PT DENTRA MITRA ABADI | 2 | Mitratel | 2018-08-03 | 2028-08-02 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 200m arah 330 degree
306 | Area 2 | R03 Jabotabek Inner | 3 | JTX493 | JTX493 |  | Jabat | #N/A | #N/A | 25TS09B0011 | #N/A | TAMANBAMBUDMT | 106.9155 | -6.3033 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT SINERGI REKTA DENTA |  | Mitratel | 2018-08-03 | 2028-08-02 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  |  | GF | Monopole | 36
307 | Area 2 | R03 Jabotabek Inner | 3 | JSA024 | JSA024 |  | Jabat | #N/A | #N/A | NY | 25TS12B0057 | ULUJAMIPERDATAMDMT | 106.7649 | -6.2416 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MITRA SARANA KARYA BANGSA | PT VALUE TELECOMMUNICATION | 1 | Mitratel | 2018-08-03 | 2028-08-02 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 100m 270 Degree
308 | Area 2 | R03 Jabotabek Inner | 3 | JPX235 | JPX235 |  | Jabat | #N/A | #N/A | NY | 25TS12B0059 | JLPENJERNIHAN2DMT | 106.8081 | -6.2037 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INFRAKO DAYAMITRA | PT INFRAKO DAYAMITRA | 2 | Mitratel | 2018-08-03 | 2028-08-02 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 50m 230 degree
309 | Area 2 | R03 Jabotabek Inner | 3 | JTX500 | JTX500 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0100 | MASJIDAMINJIDIATULAHDMT | 106.8768 | -6.3251 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INDOJAR MULIA ABADI | PT INDOJAR MULIA ABADI | 1 | Mitratel | 2018-08-17 | 2028-08-16 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Extend Tower | 0 | 0 | 0 | Extend 3m
310 | Area 2 | R03 Jabotabek Inner | 3 | JBX389 | JBX389 |  | Jabat | #N/A | #N/A | NY | 25TS12B0063 | JOGLORAYAKEMBANGANDMT | 106.7402 | -6.2195 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SUMBERSOLUSINDO HITECH | PT SUMBERSOLUSINDO HITECH | 8 | Mitratel | 2018-08-17 | 2028-08-16 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 100m 10 degree
311 | Area 2 | R03 Jabotabek Inner | 3 | JSA012 | JSA012 |  | Jabat | #N/A | #N/A | NY | 25TS12B0064 | SEKOLAHKOMANDOTNIALDMT | 106.7779 | -6.2404 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT CELEBES KONTRUKSINDO | PT MULTI BAGASANTI MAHDY | 2 | Mitratel | 2018-08-17 | 2028-08-16 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 270' 150m
312 | Area 2 | R03 Jabotabek Inner | 3 | JSA043 | JSA043 |  |  | #N/A | #N/A | NY | #N/A | RELOCCILANDAKDMT | 106.8031 | -6.3043 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2018-08-17 | 2028-08-16 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
313 | Area 2 | R03 Jabotabek Inner | 3 | JTX497 | JTX497 |  | Jabat | #N/A | #N/A | NY | 25TS12B0066 | JLGORDACIPAYUNGDMT | 106.8963 | -6.2938 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DESATRIA ALARD MANDIRI | PT DESATRIA ALARD MANDIRI | 2 | Mitratel | 2018-08-17 | 2028-08-16 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | B2S | 0 | 0 | 0 | 100 degree arah 70m
314 | Area 2 | R03 Jabotabek Inner | 3 | JTX498 | JTX498 |  | Jabat | #N/A | #N/A | NY | 25TS12B0071 | PULOMERSKTAMANSARIDMT | 106.8827 | -6.3559 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DESATRIA ALARD MANDIRI | PT DESATRIA ALARD MANDIRI | 1 | Mitratel | 2018-08-17 | 2028-08-16 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | B2S | 0 | 0 | 0 | BTR Arah 170m 50 degree
315 | Area 2 | R03 Jabotabek Inner | 3 | JBX390 | JBX390 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0098 | TANAHTAMBORADMT | 106.8117 | -6.1513 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SUMBERSOLUSINDO HITECH | PT NAER TUNAS INDONESIA | 7 | Mitratel | 2018-08-20 | 2028-08-19 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Extend Tower | 0 | 0 | 0 | Extend 12 m (Rooftop)
316 | Area 2 | R03 Jabotabek Inner | 3 | JSA015 | JSA015 |  | Jabat | #N/A | #N/A | NY | 25TS12B0055 | JLDAMAIRAYA8DMT | 106.7533 | -6.2489 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MITRA SARANA KARYA BANGSA | PT AGUNGMAS PRIMA SEMPURNA | 1 | Mitratel | 2018-08-29 | 2028-08-28 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 100m 260 Degree
317 | Area 2 | R03 Jabotabek Inner | 3 | JTX502 | JTX502 |  | Jabat | #N/A | #N/A | NY | 25TS12B0039 | JLRADENINTEN2DMT | 106.9193 | -6.2415 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MULTI BAGASANTI MAHDY | PT MULTI BAGASANTI MAHDY | 4 | Mitratel | 2018-09-09 | 2028-09-08 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 150m 100 degree
318 | Area 2 | R03 Jabotabek Inner | 3 | JPX184 | JPX184 |  | Jabat | #N/A | #N/A | NY | 25TS12B0078 | KOMPLEKDITJENDMT | 106.8621 | -6.1702 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INFRAKO DAYAMITRA | PT INFRAKO DAYAMITRA | 1 | Mitratel | 2018-09-11 | 2028-09-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 100m 110 degree
319 | Area 2 | R03 Jabotabek Inner | 3 | JTX507 | JTX507 |  | Jabat | #N/A | #N/A | NY | 25TS12B0035 | JALANDUYUNGRAWAMANGUNDMT | 106.8942 | -6.1972 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MULTI BAGASANTI MAHDY | PT MULTI BAGASANTI MAHDY | 3 | Mitratel | 2018-09-14 | 2028-09-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 100m 340 degree
320 | Area 2 | R03 Jabotabek Inner | 3 | JUX417 | JUX417 |  | Jabat | #N/A | #N/A | NY | 25TS12B0072 | AKSESMARUNDADMT | 106.9351 | -6.1175 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT GEAF SOLUSIANDA PRATAMA | PT GEAF SOLUSIANDA PRATAMA | 3 | Mitratel | 2018-09-14 | 2028-09-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 75 quadran 4
321 | Area 2 | R03 Jabotabek Inner | 3 | JUX402 | JUX402 |  | Jabat | #N/A | #N/A | NY | 25TS12B0031 | WARAKASGANG3DMT | 106.8816 | -6.1246 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SINERGI REKTA DENTA | PT SUMBERSOLUSINDO HITECH | 8 | Mitratel | 2018-09-19 | 2028-09-18 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Extend Tower | 0 | 0 | 0 | Locktrial, coba diextend
322 | Area 2 | R03 Jabotabek Inner | 3 | JSA033 | JSA033 |  | Jabat | #N/A | #N/A | NY | 25TS12B0054 | JLKENCANAINDAHDMT | 106.7925 | -6.2754 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MITRA SARANA KARYA BANGSA | PT AGUNGMAS PRIMA SEMPURNA | 1 | Mitratel | 2018-09-19 | 2028-09-18 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | Parkiran mobil, 120' 80m
323 | Area 2 | R03 Jabotabek Inner | 3 | JSA037 | JSA037 | #N/A | Jabat | #N/A | #N/A | NY | 25TS12B0062 | JLDIENGMAMPANGDMT | 106.8301 | -6.2543 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT CELEBES KONTRUKSINDO | PT CELEBES KONTRUKSINDO | 2 | Mitratel | 2018-09-19 | 2028-09-18 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 170 degree arah 180m
324 | Area 2 | R03 Jabotabek Inner | 3 | JUX407 | JUX407 | 25TS08U1308 | Jabat | #N/A | #N/A | 25TS08U1308 | #N/A | JLKAKAPPENJARINGANDMT | 106.805 | -6.1041 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | PT SINERGI REKTA DENTA |  | Mitratel | 2018-09-19 | 2028-09-18 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | GF | Monopole | 32
325 | Area 2 | R03 Jabotabek Inner | 3 | JSA010 | JSA010 |  | Jabat | #N/A | #N/A | NY | 25TS12B0058 | TEGALPARANGUTRDMT | 106.8336 | -6.2444 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT CELEBES KONTRUKSINDO | PT CELEBES KONTRUKSINDO | 1 | Mitratel | 2018-09-24 | 2028-09-23 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 80m 200 degree
326 | Area 2 | R03 Jabotabek Inner | 3 | JUX419 | JUX419 |  | Jabat | #N/A | #N/A | NY | #N/A | KOMPSWASEMBADABARATDMT | 106.8902 | -6.1271 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT AJIAN TRI SUKSES | 0 | 2 | Mitratel | 2019-01-10 | 2029-01-09 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 35' 200m
327 | Area 2 | R03 Jabotabek Inner | 3 | JBX397 | JBX397 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0110 | DANAWIJAYAKESUMADMT | 106.7696 | -6.16 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT AGUNGMAS PRIMA SEMPURNA | PT AGUNGMAS PRIMA SEMPURNA | 10 | Mitratel | 2019-01-24 | 2029-01-23 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 7 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | Extend 3m
328 | Area 2 | R03 Jabotabek Inner | 3 | JBX391 | JBX391 |  | Jabat | #N/A | #N/A | NY | #N/A | JLKALIANYARTAMBORADMTHL | 106.7988 | -6.1582 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INTERTEL MEDIA PRIMA | 0 | 2 | Mitratel | 2019-01-31 | 2029-01-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower | 0 | 0 | 0 | 150m 300 degree
329 | Area 2 | R03 Jabotabek Inner | 3 | JBX398 | JBX398 |  | Jabat | #N/A | #N/A | NY | 25TS12B0073 | GREENGARDENKEDOYADMT | 106.7562 | -6.1715 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INTERTEL MEDIA PRIMA | PT INTERTEL MEDIA PRIMA | 2 | Mitratel | 2019-02-04 | 2029-02-03 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | B2S | 0 | 0 | 0 | 350' 100m
330 | Area 1 | R10 Sumbagteng | 10 | BTM673 | BTM673 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09R0005 | #N/A | PERUMBEVERLY2 | 103.9887 | 1.1185 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-01-27 | 2027-01-26 |  |  |  |  | Plan ≥ 2026 |  | 03.RFI | Type-6 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-6 (Same TP)
331 | Area 1 | R10 Sumbagteng | 10 | BTM845 | BTM845 | 25TS07Z0008 | R10 Sumbagteng | 0 | #N/A | 25TS07Z0008 | #N/A | BTM845GDPEHAL | 104.057 | 1.1042 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-20 | 2025-08-19 | 2025-11-17 | 2025-10-27 | 21 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-1 | RFI | RFI | RFI |  | done
332 | Area 1 | R10 Sumbagteng | 10 | PBR393 | PBR393 | 25TS07Z0009 | R10 Sumbagteng | 0 | #N/A | 25TS07Z0009 | #N/A | PBR393HL1_LABUHBARU2DMT | 101.4138 | 0.51701 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-27 | 2025-08-26 | 2025-11-24 | 2025-11-30 | -6 | Out SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-1 | RFI | RFI | RFI | 05. RFI | done
333 | Area 1 | R10 Sumbagteng | 10 |  | PAD677 |  | R10 Sumbagteng | 0 | #N/A | 25TS07Z0010 | #N/A | TERMINAL ANDALAS | 100.3811 | -0.94442 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-09 | 2025-09-08 | 2025-12-07 | 2025-11-30 | 7 | In SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-1 | RFC | RFC | OG | [30/10/25] Plan Eksekusi W4 Nov 19/07/25 Wait Dok. RFIN Plan 21/07 | 2025-12-18 | Type-1
334 | Area 2 | R03 Jabotabek Inner | 3 |  | JTX394 |  |  | #N/A | #N/A | NY | #N/A | PULOLENTUTRAYADMT | 106.9151 | -6.1894 | Non MKT | Non MKT | 0 | Non-HBTS | MITRATEL | #N/A | #N/A |  | Mitratel | 2018-01-12 | 2028-01-11 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
335 | Area 1 | R10 Sumbagteng | 10 | BTM355 | BTM355 |  | R10 Sumbagteng | 0 | #N/A | NY | #N/A | STOSAGULUNGSIMPANGTAROKA | 103.8986 | 1.0912 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-20 | 2025-08-19 | 2025-11-17 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A | Type-6 | Terminate | Terminate | Terminate |  | Terminate
336 | Area 2 | R03 Jabotabek Inner | 3 | JBX034 | JBX034 |  | Jabat | #N/A | #N/A | 25TS09B0009 | #N/A | TAMANKEDOYABARUDMT | 106.7615 | -6.1853 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SINERGI REKTA DENTA |  | Mitratel | 2015-07-24 | 2025-07-23 | 2025-10-21 | 2026-01-31 | -102 | Out SLA | Plan ≤ 2025 | 04.HUNT/REHUNT | 08.SIS |  | SIS/SES | Hunting | OG | 4.12 hard kandidat, Hard Sitac, plan BTR gagal IW, hunting kandidat ke 4 | 2026-02-13 | BTR | GF | Monopole | 36
337 | Area 1 | R10 Sumbagteng | 10 | PAD672 | PAD672 |  | R10 Sumbagteng | 0 | #N/A | 25TS07Z0011 | #N/A | STOULAKARANGULAKKARANG2 | 100.3556 | -0.91061 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-12 | 2025-09-11 | 2025-12-10 | 2025-11-30 | 10 | In SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-1 | RFC | RFC | OG | [30/10/25] Plan Eksekusi W4 Nov [9/09/25] Proses Fabrikan Ring mounting + Rack Gendong + Bracket Panel KWH + ACPDB [20/07/2025] Submit Dok.RFIN done | 2025-12-18 | Type-1
338 | Area 1 | R10 Sumbagteng | 10 | BTM404 | BTM404 |  | R10 Sumbagteng | 0 | #N/A | NY | #N/A | STOSAGULUNGPERUMFANINDO | 103.9484 | 1.0476 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-11 | 2025-09-10 | 2025-12-09 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A | Type-6 | Terminate | Terminate | Terminate |  | Terminate
339 | Area 1 | R10 Sumbagteng | 10 | BTM423 | BTM423 |  | R10 Sumbagteng | 0 | #N/A | NY | #N/A | STOKABILCOMBETPUNGGUR | 104.1316 | 1.0348 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-14 | 2025-09-13 | 2025-12-12 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A | Type-6 | Terminate | Terminate | Terminate |  | Terminate
340 | Area 1 | R10 Sumbagteng | 10 | BTM849 | BTM849 |  | R10 Sumbagteng | 0 | #N/A | 25TS07Z0012 | #N/A | BTM849HWD_STO_SAGULUNG_PERUM_GENTA | 103.9744 | 1.0476 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-13 | 2025-09-12 | 2025-12-11 | 2025-10-27 | 45 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-1 | RFI | RFI | RFI | bts hotel, perangkat tsel | done
341 | Area 1 | R10 Sumbagteng | 10 | PAD662 | PAD662 |  | R10 Sumbagteng | 0 | #N/A | 25TS07Z0013 | #N/A | STOPADANGCENTERVETERAN3 | 100.3565 | -0.9322 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-30 | 2025-09-29 | 2025-12-28 | 2025-11-30 | 28 | In SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-1 | RFC | RFC | OG | [30/10/25] Plan Eksekusi W4 Nov [9/09/25] Proses Fabrikan Ring mounting + Rack Gendong + Bracket Panel KWH + ACPDB [20/07/2025] Submit Dok.RFIN done | 2025-12-18 | Type-1
342 | Area 1 | R10 Sumbagteng | 10 | PAD686 | PAD686 | 25TS07C0003 | R10 Sumbagteng | 0 | #N/A | 25TS07C0003 | #N/A | STOTELUKBAYURRSSEMENPADANG | 100.4005 | -0.94075 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-13 | 2025-10-12 | 2026-01-10 | 2025-08-26 | 137 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-6 | RFI | RFI | RFI |  | done
343 | Area 1 | R10 Sumbagteng | 10 | PAP225 | PAP225 |  | R10 Sumbagteng | #N/A | #N/A | NY | #N/A | PAP225GDLBAN3 | 100.364 | -0.47409 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-07-28 | 2027-07-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-1 | Need DRM |  | OG | Add 3 RF Add 7 RRU Final Sow Rescope: Type-1
344 | Area 1 | R10 Sumbagteng | 10 | PAD683 | PAD683 |  | R10 Sumbagteng | #N/A | #N/A | NY | #N/A | STOTELUKBAYURPELABUHAN3 | 100.3695 | -0.99771 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-01-21 | 2026-01-20 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-6 | Need DRM |  | OG | Add 3 RF Add 3 RRU Final Sow Rescope: Type-6 (Same TP)
345 | Area 1 | R10 Sumbagteng | 10 | BTM523 | BTM523 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09B0001 | #N/A | BTM523HWD_STO_SAGULUNG_KBI_II | 103.9291 | 1.056 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-04 | 2026-07-03 |  |  |  |  | Plan ≥ 2026 |  | 03.RFI | Type-6 | RFI | RFI | RFI | Add 3 RF Add 9 RRU Final Sow Rescope: Type-6 (Same TP)
346 | Area 1 | R10 Sumbagteng | 10 | PAD673 | PAD673 |  | R10 Sumbagteng | 0 | #N/A | 25TS07Z0014 | #N/A | STOPADANGCENTERVETERAE4 | 100.3545 | -0.93754 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-05 | 2025-10-04 | 2026-01-02 | 2025-11-30 | 33 | In SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-1 | RFC | RFC | OG | [30/10/25] Plan Eksekusi W4 Nov [9/09/25] Proses Fabrikan Ring mounting + Rack Gendong + Bracket Panel KWH + ACPDB [20/07/2025] Submit Dok.RFIN done | 2025-12-18 | Type-1
347 | Area 1 | R10 Sumbagteng | 10 | BTM860 | BTM860 | 25TS07Z0015 | R10 Sumbagteng | 0 | #N/A | 25TS07Z0015 | #N/A | MALLFANINDO | 103.9404 | 1.0469 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-07 | 2025-10-06 | 2026-01-04 | 2025-10-27 | 69 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-1 | RFI | RFI | RFI |  | done
348 | Area 1 | R10 Sumbagteng | 10 | PAD476 | PAD476 |  | R10 Sumbagteng | #N/A | #N/A | NY | #N/A | STOBANDARBUATPASARBARU2 | 100.4294 | -0.93105 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-08 | 2026-07-07 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-6 | Need DRM |  | OG
349 | Area 1 | R10 Sumbagteng | 10 | BTM933 | BTM933 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0019 | #N/A | BESTWESTERNCONDOMINIUM | 104.0297 | 1.0826 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-03-29 | 2027-03-28 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS | Type-6 | SIS/SES | SIS | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Macro
350 | Area 1 | R10 Sumbagteng | 10 | PBR567 | PBR567 |  | R10 Sumbagteng | #N/A | #N/A | NY | #N/A | BANGAUSAKTI3DMT | 101.4454 | 0.56405 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-11-02 | 2027-11-01 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-6 | Need DRM |  | OG
351 | Area 2 | R03 Jabotabek Inner | 3 | JKT711 | JKT711 | 25TS08N2002 | Jabat | #N/A | #N/A | 25TS08N2002 | 25TS12B0086 | JAKARTAPRIMASTEELDMT | 106.9281 | -6.1795 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT MULTI BAGASANTI MAHDY | PT MULTI BAGASANTI MAHDY | 2 | Mitratel | 2016-12-25 | 2026-12-24 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
352 | Area 1 | R10 Sumbagteng | 10 | PAD682 | PAD682 |  | R10 Sumbagteng | 0 | #N/A | 25TS07Z0016 | #N/A | STOPADANGCENTERGUNUNGPANGILUN4 | 100.3769 | -0.92319 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-10 | 2025-10-09 | 2026-01-07 | 2025-11-30 | 38 | In SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-1 | RFC | RFC | OG | [30/10/25] Plan Eksekusi W4 Nov [9/09/25] Proses Fabrikan Ring mounting + Rack Gendong + Bracket Panel KWH + ACPDB [20/07/2025] Submit Dok.RFIN done | 2025-12-18 | Type-1
353 | Area 1 | R01 Sumbagut | 1 | MDX500 | MDX500 |  | R01 Sumbagut | #N/A | #N/A | NY | 25TS12Z0082 | MC KIM BELAWAN-1 | 98.6724 | 3.6604 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT M JUSUF & SONS |  | Mitratel | 2016-11-10 | 2026-11-09 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 6 RF Add 9 RRU Remove 6 RRU Final Sow Rescope: 3. reheight tower |  | Extend Tower
354 | Area 1 | R10 Sumbagteng | 10 | BTM302 | BTM302 |  | R10 Sumbagteng | 0 | #N/A | 25TS07Z0017 | #N/A | BATAMCENTERHIJRAHINDUSTRIALPARK | 104.0468 | 1.1154 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-13 | 2025-10-12 | 2026-01-10 | 2025-10-27 | 75 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-1 | RFI | RFI | RFI |  | done
355 | Area 2 | R03 Jabotabek Inner | 3 | JKP203 | JKP203 | 25TS08N1777 | Jabat | 23TS03Z0015 | 23TS03Z0015 | 25TS08N1777 | #N/A | DIPONEGOROMENTENG2DMT | 106.8354 | -6.2006 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | Koperasi Dayamitra Telekomunikasi |  | Mitratel | 2013-10-31 | 2023-10-30 | 2024-01-28 | 2025-05-24 | -482 | Out SLA | Plan ≤ 2025 | 12.RFC | 03.RFI |  | RFI | RFI | RFI | Lanjut Extend 3m | done |  | GF | Monopole | 23
356 | Area 1 | R10 Sumbagteng | 10 | BTM850 | BTM850 | 25TS07Z0018 | R10 Sumbagteng | 0 | #N/A | 25TS07Z0018 | #N/A | STOLUBUKBAJACITRABUANACPARKII | 104.0231 | 1.1585 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-13 | 2025-10-12 | 2026-01-10 | 2025-10-27 | 75 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-1 | RFI | RFI | RFI |  | done
357 | Area 1 | R10 Sumbagteng | 10 | PBR975 | PBR975 | 25TS07Z0019 | R10 Sumbagteng | 0 | #N/A | 25TS07Z0019 | #N/A | PBR975HL1_RUMAHSAKITISLAMIBNUSINADMT | 101.4544 | 0.48589 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-13 | 2025-10-12 | 2026-01-10 | 2025-11-30 | 41 | In SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-1 | RFI | RFI | RFI | 05. RFI | done
358 | Area 1 | R10 Sumbagteng | 10 | PBR991 | PBR991 | 25TS07Z0020 | R10 Sumbagteng | 0 | #N/A | 25TS07Z0020 | #N/A | PBR991HL1_PURWODADI3DMT | 101.4059 | 0.4583 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-13 | 2025-10-12 | 2026-01-10 | 2025-11-30 | 41 | In SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-1 | RFI | RFI | RFI | 05. RFI | done
359 | Area 2 | R12 Jabotabek Outer | 12 | KRW829 | KRW829 | 25TS01B0007 | Eastern Jabodetabek |  | 25TS01B0007 | 25TS01B0007 | #N/A | KIM7DMT | 107.3153 | -6.3724 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT. Samanta Fibra Abadi |  | Mitratel | 2015-06-22 | 2025-06-21 | 2025-09-19 | 2026-01-31 | -134 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC |  | SITAC | BAN/BAK | OG | 4.12. plan macronisasi di site existing, upgrade perangkat (swap) type 1, per tahun per pole 300 Juta, need special price, geser hunting ke Peruri | 2026-02-24 |  | GF | SST | 42
360 | Area 2 | R03 Jabotabek Inner | 3 | JTX341 | JTX341 | #N/A | Jabat | #N/A | #N/A | NY | 25TS12Z0102 | TMII9DMT | 106.8901 | -6.3039 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT CIPTA KARSA ANUGERAH SEMESTA | PT CIPTA KARSA ANUGERAH SEMESTA | 1 | Mitratel | 2016-12-02 | 2026-12-01 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
361 | Area 2 | R12 Jabotabek Outer | 12 | KRW811 | KRW811 | 25TS01B0004 | Eastern Jabodetabek |  | 25TS01B0004 | 25TS01B0004 | #N/A | KIIC5DMT | 107.2945 | -6.3721 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT AGUNGMAS PRIMA SEMPURNA |  | Mitratel | 2015-06-24 | 2025-06-23 | 2025-09-21 | 2025-09-24 | -3 | Out SLA | Plan ≤ 2025 | #N/A | 04.CME |  | RFI | RFI | RFI |  | done |  | GF | SST | 42
362 | Area 2 | R12 Jabotabek Outer | 12 | KRW807 | KRW807 | 25TS01B0002 | Eastern Jabodetabek |  | 25TS01B0002 | 25TS01B0002 | #N/A | KIIC1DMT | 107.2727 | -6.3653 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT AGUNGMAS PRIMA SEMPURNA |  | Mitratel | 2015-06-30 | 2025-06-29 | 2025-09-27 |  |  | Out SLA | Plan ≤ 2025 | #N/A | 04.CME |  | RFI | RFI | RFI |  | done |  | GF | SST | 42
363 | Area 2 | R12 Jabotabek Outer | 12 | KRW809 | KRW809 | 25TS01B0003 | Eastern Jabodetabek |  | 25TS01B0003 | 25TS01B0003 | #N/A | KIIC3DMT | 107.2954 | -6.359 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT AGUNGMAS PRIMA SEMPURNA |  | Mitratel | 2015-06-30 | 2025-06-29 | 2025-09-27 | 2026-01-31 | -126 | Out SLA | Plan ≤ 2025 | #N/A | 04.CME |  | CME | Excavation | OG | 10.12 Excation OG, geser 150m, Waiting Surat Kerja Pihak Kawasan | 2026-01-14 |  | GF | SST | 42
364 | Area 4 | R08 Kalimantan | 8 | BBR228 | BBR228 |  | R08 Kalimantan | #N/A | #N/A | NY | #N/A | MTH_LAPMURJANI2 | 114.8312 | -3.4394 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-08-02 | 2026-08-01 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
365 | Area 2 | R12 Jabotabek Outer | 12 | KRW833 | KRW833 | 25TS01B0009 | Eastern Jabodetabek |  | 25TS01B0009 | 25TS01B0009 | #N/A | KIM11DMT | 107.3031 | -6.3829 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT. Samanta Fibra Abadi |  | Mitratel | 2015-06-30 | 2025-06-29 | 2025-09-27 | 2026-01-31 | -126 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC |  | SITAC | BAN/BAK | OG | 4.12. plan macronisasi di site existing, upgrade perangkat (swap) type 1, per tahun per pole 300 Juta, need special price, geser hunting ke Lahan BI | 2026-02-24 |  | GF | SST | 42
366 | Area 2 | R12 Jabotabek Outer | 12 | CPT251 | CPT251 |  | Jabat | #N/A | #N/A | 25TS09Z0031 | #N/A | TERATAIPUTIHDMT | 106.7561 | -6.2775 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT GEAF SOLUSIANDA PRATAMA |  | Mitratel | 2015-10-06 | 2025-10-05 | 2026-01-03 | 2025-12-31 | 3 | In SLA | Plan ≤ 2025 | 09.PROSES IW | 08.SIS |  | SITAC | IW | OG | 10.12 IW OG | 2026-01-26 |  | GF | Monopole | 32
367 | Area 2 | R03 Jabotabek Inner | 3 | JPX152 | JPX152 |  |  | #N/A | #N/A | NY | #N/A | CIMAHIMENTENGDMT | 106.8301 | -6.2032 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-06-29 | 2026-06-28 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
368 | Area 2 | R12 Jabotabek Outer | 12 | BKX173 | BKX173 |  | Eastern Jabodetabek | #N/A | #N/A | 25TS09Z0030 | #N/A | BINTARACIPTABARATDMT | 106.9569 | -6.23 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SUMBERSOLUSINDO HITECH |  | Mitratel | 2015-10-31 | 2025-10-30 | 2026-01-28 | 2025-12-31 | 28 | In SLA | Plan ≤ 2025 | #N/A | 08.SIS |  | SITAC | REKOM | OG | 10.12 Rekom OG | 2026-01-26 |  | GF | Monopole | 30
369 | Area 1 | R10 Sumbagteng | 10 | PAP224 | PAP224 |  | R10 Sumbagteng | #N/A | #N/A | NY | #N/A | PAP224GDLEAN2 | 100.3471 | -0.47844 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-07-28 | 2027-07-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-1 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
370 | Area 2 | R12 Jabotabek Outer | 12 | KRW844 | KRW844 |  | Eastern Jabodetabek | 0 | #N/A | NY | #N/A | KIS9DMT | 107.3274 | -6.3734 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-06-22 | 2025-06-21 | 2025-09-19 | 2026-01-31 | -134 | Out SLA | Plan ≤ 2025 | #N/A | #N/A |  |  |  |  | Lock Trial | NA |  | #N/A | #N/A | #N/A
371 | Area 2 | R03 Jabotabek Inner | 3 | JPX149 | JPX149 | 25TS08N1773 | Jabat | #N/A | #N/A | 25TS08N1773 | 25TS12B0103 | KALIBARUBARATDMT | 106.8428 | -6.1704 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SINERGI REKTA DENTA | PT SINERGI REKTA DENTA | 6 | Mitratel | 2016-06-27 | 2026-06-26 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR
372 | Area 2 | R12 Jabotabek Outer | 12 | KRW843 | KRW843 |  | Eastern Jabodetabek | 0 | #N/A | NY | #N/A | KIS8DMT | 107.3332 | -6.4015 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-06-22 | 2025-06-21 | 2025-09-19 | 2026-01-31 | -134 | Out SLA | Plan ≤ 2025 | #N/A | #N/A |  |  |  |  | Lock Trial | NA |  | #N/A | #N/A | #N/A
373 | Area 2 | R12 Jabotabek Outer | 12 | KRW814 | KRW814 |  | Eastern Jabodetabek | 0 | #N/A | NY | #N/A | KIIC8DMT | 107.2777 | -6.356 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-06-27 | 2025-06-26 | 2025-09-24 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
374 | Area 2 | R12 Jabotabek Outer | 12 | KRW836 | KRW836 |  | Eastern Jabodetabek | 0 | #N/A | NY | #N/A | KIS1DMT | 107.3367 | -6.3939 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-06-27 | 2025-06-26 | 2025-09-24 | 2026-01-31 | -129 | Out SLA | Plan ≤ 2025 | #N/A | #N/A |  |  |  |  | Lock Trial | NA |  | #N/A | #N/A | #N/A
375 | Area 2 | R12 Jabotabek Outer | 12 | KRW172 | KRW172 |  | Eastern Jabodetabek | #N/A | #N/A | NY | #N/A | PERMANENTCMBTMITRAKARAWANGDMT | 107.3104 | -6.3819 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-11-14 | 2025-11-13 | 2026-02-11 | 2026-01-31 | 11 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  |  |  |  | NA | NA | blm ada didata regional | #N/A | #N/A | #N/A
376 | Area 2 | R12 Jabotabek Outer | 12 | BOO571 | BOO571 |  | Eastern Jabodetabek | 0 | #N/A | NY | #N/A | IPBDARMAGAREKTORAT | 106.7226 | -6.5566 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-12-01 | 2025-11-30 | 2026-02-28 | 2026-01-31 | 28 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | SITAC | BAN/BAK | OG | proses BAN/BAK ke pihak IPB | 2026-01-22 |  | #N/A | #N/A | #N/A
377 | Area 2 | R12 Jabotabek Outer | 12 | KRW813 | KRW813 |  | Eastern Jabodetabek | 0 | #N/A | NY | #N/A | KIIC7DMT | 107.2743 | -6.3603 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-06-30 | 2025-06-29 | 2025-09-27 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
378 | Area 2 | R12 Jabotabek Outer | 12 | BKX163 | BKX163 |  | Eastern Jabodetabek | 0 | #N/A | 25TS09Z0032 | #N/A | JATIASIHKALIMANTANDMT | 106.9707 | -6.2914 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SUMBERSOLUSINDO HITECH |  | Mitratel | 2015-12-18 | 2025-12-17 | 2026-03-17 | 2025-12-31 | 76 | In SLA | Plan ≤ 2025 | #N/A | 08.SIS |  | SITAC | BAN/BAK | OG | proses BAN/BAK | 2026-01-10 |  | GF | Monopole | 30
379 | Area 2 | R12 Jabotabek Outer | 12 | BKX174 | BKX174 |  | Eastern Jabodetabek | #N/A | #N/A | 25TS09Z0033 | #N/A | JLDARAMAHKOTADMT | 106.923 | -6.2621 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT SUMBERSOLUSINDO HITECH |  | Mitratel | 2016-04-28 | 2026-04-27 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: BTR to Mini Macro |  | BTR | GF | Monopole | 30
380 | Area 2 | R12 Jabotabek Outer | 12 | BKX116 | BKX116 | 25TS08U1438 | Eastern Jabodetabek | 0 | #N/A | 25TS08U1438 | #N/A | PALEMBARAT12DMT | 106.9809 | -6.2652 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SUMBERSOLUSINDO HITECH |  | Mitratel | 2015-09-13 | 2025-09-12 | 2025-12-11 | 2026-01-31 | -51 | Out SLA | Plan ≤ 2025 | #N/A | 08.SIS |  | SIS/SES | Hunting | OG | Need Validasi NBAE | 2026-01-26 |  | GF | Monopole | 30
381 | Area 2 | R12 Jabotabek Outer | 12 | KRW838 | KRW838 | 25TS05U0042 | Eastern Jabodetabek | #N/A | #N/A | 25TS05U0042 | 25TS12B0011 | KIS3DMT | 107.3403 | -6.4116 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT AGUNGMAS PRIMA SEMPURNA | PT AGUNGMAS PRIMA SEMPURNA | 6 | Mitratel | 2016-06-24 | 2026-06-23 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 7 RRU Final Sow Rescope: BTR to Macro |  | BTR | 0 | 0 | 0 | BTR
382 | Area 2 | R12 Jabotabek Outer | 12 | KRW817 | KRW817 | 25TS01B0005 | Eastern Jabodetabek | #N/A | #N/A | 25TS01B0005 | #N/A | KIIC13DMT | 107.2647 | -6.3764 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT AGUNGMAS PRIMA SEMPURNA |  | Mitratel | 2016-08-11 | 2026-08-10 |  |  |  |  | Plan ≥ 2026 |  | 04.CME |  | RFI | RFI | RFI | Add 3 RF Add 6 RRU Final Sow Rescope: BTR to Macro |  | BTR | GF | SST | 42
383 | Area 2 | R12 Jabotabek Outer | 12 | KRW842 | KRW842 |  | Eastern Jabodetabek | #N/A | #N/A | NY | #N/A | KIS7DMT | 107.3349 | -6.3861 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-06-30 | 2026-06-29 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
384 | Area 2 | R12 Jabotabek Outer | 12 | BOO572 | BOO572 | 25TS08N0303 | Eastern Jabodetabek | #N/A | #N/A | 25TS08N0303 | #N/A | IPBDRAMAGAFAKPERTANIAN | 106.7313 | -6.5569 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT DENTRA MITRA ABADI |  | Mitratel | 2016-12-01 | 2026-11-30 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS |  | Need DRM | Need DRM | OG | Add 3 RF Add 13 RRU Final Sow Rescope: reheight tower |  | Extend Tower | GF | Monopole | 30
385 | Area 2 | R12 Jabotabek Outer | 12 | KRW828 | KRW828 |  | Eastern Jabodetabek | #N/A | #N/A | 25TS01B0006 | #N/A | KIM6DMT | 107.3085 | -6.3765 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT SAMANTA FIBRA ABADI |  | Mitratel | 2016-12-15 | 2026-12-14 |  |  |  |  | Plan ≥ 2026 |  | 06.SITAC |  | SITAC | BAN/BAK | OG | 4.12. plan macronisasi di site existing, upgrade perangkat (swap) type 1, Add 3 RF Add 8 RRU Final Sow Rescope: BTR to Macro |  | Type-1 | GF | SST | 42
386 | Area 2 | R12 Jabotabek Outer | 12 | JBX370 | JBX370 |  | Jabat | #N/A | #N/A | 25TS09Z0028 | #N/A | KAMALKALIDERES16DMT | 106.6872 | -6.1287 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT AGUNGMAS PRIMA SEMPURNA |  | Mitratel | 2017-06-13 | 2027-06-12 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | GF | Monopole | 25
387 | Area 2 | R12 Jabotabek Outer | 12 | KRW953 | KRW953 | 25TS01B0012 | Eastern Jabodetabek | #N/A | #N/A | 25TS01B0012 | #N/A | KIM10DMT | 107.3136 | -6.3761 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT SAMANTA FIBRA ABADI |  | Mitratel | 2017-06-13 | 2027-06-12 |  |  |  |  | Plan ≥ 2026 |  | 06.SITAC |  | SITAC | BAN/BAK | OG | 4.12. plan macronisasi di site existing, upgrade perangkat (swap) type 1, Add 3 RF Add 9 RRU Final Sow Rescope: BTR to Macro |  | Type-1 | GF | SST | 42
388 | Area 2 | R12 Jabotabek Outer | 12 | BKX288 | BKX288 |  | Eastern Jabodetabek | #N/A | #N/A | 25TS09Z0034 | #N/A | PTSOSROPENGGILINGANCAKUNGDMT | 106.9712 | -6.1926 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT MITRA SARANA KARYA BANGSA |  | Mitratel | 2017-08-04 | 2027-08-03 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: BTR to Macro |  |  | GF | Monopole | 30
389 | Area 2 | R12 Jabotabek Outer | 12 | DPK239 | DPK239 |  | Eastern Jabodetabek | #N/A | #N/A | 25TS09B0008 | #N/A | JLJUANDABAKTIJAYATBG | 106.8483 | -6.3792 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT Multi Bagasanti Mahdy |  | Mitratel | 2018-08-17 | 2028-08-16 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: BTR to Mini Macro |  |  | GF | Monopole | 36
390 | Area 3 | R05 Jawa Tengah | 5 | YOG230 | YOG230 |  | R05 Jawa Tengah | 24TS02Z0031 | #N/A | 24TS02Z0031 | #N/A | HOTEL BTS UGM REKTORAT PERTAMINA | 110.3782 | -7.768 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2014-01-06 | 2024-01-05 | 2024-04-04 | 2026-01-31 | -667 | Out SLA | Plan ≤ 2025 | #N/A | #N/A |  | SIS/SES | Validasi | OG | 4.12 waiting validasi, pihak UGM tidak bersedia dengan rencana plan rescooping (wallmounted ke tower pole rooftop)Propose Reseller untuk Pole yang berada di RT, sisanya ke MTEL | 2026-01-25 | BTR
391 | Area 3 | R05 Jawa Tengah | 5 | YOG223 | YOG223 |  | R05 Jawa Tengah | 0 | 22TS01H1382 | NY | #N/A | HOTELBTS UGM OLAHRAGA PANCASILA | 110.3765 | -7.7738 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-07-31 | 2023-07-30 | 2023-10-28 | UGM | 0 | IN SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI | Lanjut MCP skema khusus | done
392 | Area 3 | R05 Jawa Tengah | 5 | YOG224 | YOG224 |  | R05 Jawa Tengah | 0 | 12TS12H1122 | NY | #N/A | HOTEL BTS UGM OLAHRAGA PANCASILA | 110.381 | -7.7706 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-08-13 | 2023-08-12 | 2023-11-10 | UGM | 0 | IN SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI | Lanjut MCP skema khusus | done
393 | Area 3 | R05 Jawa Tengah | 5 | YOG225 | YOG225 |  | R05 Jawa Tengah | 0 | 13TS05H8725 | NY | #N/A | HOTELBTS UGM MEDIKA KALIURANG | 110.3749 | -7.7701 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-08-13 | 2023-08-12 | 2023-11-10 | UGM | 0 | IN SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI | Lanjut MCP skema khusus | done
394 | Area 3 | R05 Jawa Tengah | 5 | YOG226 | YOG226 |  | R05 Jawa Tengah | 0 | 12TS12H1123 | NY | #N/A | HOTELBTSUGMMEDIKAKALIURANG | 110.3775 | -7.7687 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-08-13 | 2023-08-12 | 2023-11-10 | UGM | 0 | IN SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI | Lanjut MCP skema khusus | done
395 | Area 3 | R05 Jawa Tengah | 5 | YOG228 | YOG228 |  | R05 Jawa Tengah | 0 | 13TS05H8726 | NY | #N/A | HOTELBTS UGM TEKNIK KEDOKTERAN HEWAN | 110.3828 | -7.7678 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-08-13 | 2023-08-12 | 2023-11-10 | UGM | 0 | IN SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI | Lanjut MCP skema khusus, MTEL tidak memiliki kapabalitas untuk relok transport | done
396 | Area 3 | R05 Jawa Tengah | 5 | YOG232 | YOG232 |  | R05 Jawa Tengah | 0 | 12TS12H1126 | NY | #N/A | HOTEL BTS UGM TEKNIK KEDOKTERAN HEWAN | 110.373 | -7.7655 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-08-13 | 2023-08-12 | 2023-11-10 | UGM | 0 | IN SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI | Lanjut MCP skema khusus, MTEL tidak memiliki kapabalitas untuk relok transport | done
397 | Area 3 | R05 Jawa Tengah | 5 | YOG229 | YOG229 |  | R05 Jawa Tengah | 0 | 13TS05H8727 | NY | #N/A | HOTELBTS UGM S1 CARGO | 110.3809 | -7.7668 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-10-30 | 2023-10-29 | 2024-01-27 | UGM | 0 | IN SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI | Lanjut MCP skema khusus | done
398 | Area 3 | R05 Jawa Tengah | 5 | YOG227 | YOG227 |  | R05 Jawa Tengah | 0 | 12TS12H1124 | NY | #N/A | HOTELBTS UGM REKTORAT PERTAMINA | 110.3782 | -7.768 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-11-06 | 2023-11-05 | 2024-02-03 | UGM | 0 | IN SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI | Lanjut MCP skema khusus | done
399 | Area 3 | R05 Jawa Tengah | 5 | YOG231 | YOG231 |  | R05 Jawa Tengah | 0 | 13TS05H8729 | NY | #N/A | HOTELBTSUGMSICARGO | 110.3809 | -7.7668 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-11-20 | 2023-11-19 | 2024-02-17 | UGM | 0 | IN SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI | Lanjut MCP skema khusus | done
400 | Area 2 | R12 Jabotabek Outer | 12 | KRW955 | KRW955 |  | Eastern Jabodetabek | #N/A | #N/A | NY | #N/A | KIIC10DMT | 107.2886 | -6.3594 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-06-28 | 2027-06-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
401 | Area 2 | R12 Jabotabek Outer | 12 | KRW954 | KRW954 |  | Eastern Jabodetabek | #N/A | #N/A | NY | #N/A | KIIC14DMT | 107.2951 | -6.3656 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-06-28 | 2027-06-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
402 | Area 1 | R01 Sumbagut | 1 | MDX023 | MDX023 |  | R01 Sumbagut | #N/A | #N/A | NY | #N/A | MC BELAWAN-5 | 98.6932 | 3.7857 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-10-05 | 2026-10-04 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
403 | Area 1 | R01 Sumbagut | 1 | MDX507 | MDX507 |  | R01 Sumbagut | #N/A | #N/A | NY | #N/A | MC KIM BELAWAN-7 | 98.6941 | 3.6601 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-11-11 | 2026-11-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
404 | Area 1 | R01 Sumbagut | 1 | MDX503 | MDX503 |  | R01 Sumbagut | #N/A | #N/A | NY | #N/A | MC KIM BELAWAN-4 | 98.6835 | 3.6746 | Non MKT | Non MKT | #N/A |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-12-12 | 2026-12-11 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | #N/A
405 | Area 1 | R10 Sumbagteng | 10 | BTM348 | BTM348 |  | R10 Sumbagteng | #N/A | #N/A | NY | #N/A | STOBATUAMPARMEGACIPTALPARK | 104.0115 | 1.1774 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-01 | 2025-08-31 | 2025-11-29 | #N/A | #N/A | Out SLA | Plan ≤ 2025 | #N/A | #N/A | Type-6 | RFI | RFI | RFI |  | Rescoping done, site id change to BTM004 (Done OA)
406 | Area 4 | R08 Kalimantan | 8 | BBR222 | BBR222 | 24TS05C0003 | R08 Kalimantan | 0 | 24TS05C0003 | 24TS05C0003 | #N/A | MTH_UNLAM_BANJARBARU1 | 114.8429 | -3.4435 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-07-23 | 2025-07-22 | 2025-10-20 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate | Aktual RFI Colo di eksisting MTEL beda coverage | Terminate
407 | Area 1 | R02 Sumbagsel | 2 | OKI316 | OKI316 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | POLE FAKULTAS TEKHNIK 1 UNSRI | 104.647 | -3.2166 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-04-19 | 2026-04-18 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | [7 empty] | 32m Max (Type-6)
408 | Area 1 | R02 Sumbagsel | 2 | OKI317 | OKI317 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | POLE FAKULTAS TEKHNIK 2 UNSRI | 104.645 | -3.2182 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-04-19 | 2026-04-18 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | [7 empty] | 32m Max (Type-6)
409 | Area 4 | R08 Kalimantan | 8 | SMR461 | SMR461 |  | R08 Kalimantan | 24TS08Z0006 | #N/A | 24TS08Z0006 | #N/A | MTH_UNMULSMD1 | 117.1515 | -0.46982 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-14 | 2025-09-13 | 2025-12-12 | 2026-01-31 | -50 | Out SLA | Plan ≤ 2025 | #N/A | 08.SIS |  | SITAC | BAN/BAK | OG | 4.12 BAN/BAK, menunggu tim asset negosiasi dengan pihak fakultas Unmul, Lahan Fasum, tidak bisa peninggian 10, bisanya 3m, tetap di titik eksisting | Hold | BTR
410 | Area 4 | R08 Kalimantan | 8 | SMR436 | SMR436 |  | R08 Kalimantan | 24TS08Z0004 | #N/A | 24TS08Z0004 | #N/A | MTH_GUBERNURANSMD2 | 117.1412 | -0.5017 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-28 | 2025-10-27 | 2026-01-25 | 2026-01-31 | -6 | Out SLA | Plan ≤ 2025 | #N/A | 08.SIS |  | SIS/SES | Hunting | OG | 4.12 Rehunting, hard kandidat, waiting arahan tsel regional, Lahan Fasum, tidak bisa peninggian 10, bisanya 3m, tetap di titik eksisting | Hold | BTR
411 | Area 1 | R02 Sumbagsel | 2 | OKI318 | OKI318 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | POLE FAKULTAS EKONOMI UNSRI | 104.651 | -3.2175 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-04-19 | 2026-04-18 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | [7 empty] | Terminate
412 | Area 1 | R02 Sumbagsel | 2 | PLG617 | PLG617 |  | R02 Sumbagsel | 0 | NY | NY | #N/A | KEMUNING POLDA PH3 | 104.7345 | -2.9659 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-02-19 | 2025-02-18 | 2025-05-19 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
413 | Area 1 | R02 Sumbagsel | 2 | PLG613 | PLG613 |  | R02 Sumbagsel | 0 | NY | NY | #N/A | SAKO SAPTAMARGA PH3 | 104.7788 | -2.9399 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-14 | 2025-09-13 | 2025-12-12 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
414 | Area 1 | R02 Sumbagsel | 2 | PLG628 | PLG628 |  | R02 Sumbagsel | 0 | NY | NY | #N/A | POLIGON PH3 | 104.7228 | -3.0126 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-12-08 | 2025-12-07 | 2026-03-07 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
415 | Area 1 | R02 Sumbagsel | 2 | PLG630 | PLG630 |  | R02 Sumbagsel | 0 | NY | NY | #N/A | POLIGON PH5 | 104.7174 | -3.0065 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-12-08 | 2025-12-07 | 2026-03-07 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
416 | Area 4 | R09 Sulawesi | 9 | UPD764 | UPD764 | 24TS02Z0005 | R09 Sulawesi | 0 | 24TS02Z0005 | 24TS02Z0005 | #N/A | BHT_UPD_ALAUDDIN1 | 119.42 | -5.1674 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-14 | 2025-10-13 | 2026-01-11 | 2024-09-10 | 488 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
417 | Area 4 | R09 Sulawesi | 9 | UPD758 | UPD758 | 24TS02Z0002 | R09 Sulawesi | 0 | 24TS02Z0002 | 24TS02Z0002 | #N/A | BHT_UPD_SUDIRMAN2 | 119.415 | -5.1427 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-27 | 2025-10-26 | 2026-01-24 | 2024-12-13 | 407 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
418 | Area 4 | R09 Sulawesi | 9 | UPD774 | UPD774 |  | R09 Sulawesi | 0 | 24TS02Z0009 | 24TS02Z0009 | #N/A | BHT_UPD_MESJIDRAYA3 | 119.4266 | -5.1317 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-11-13 | 2025-11-12 | 2026-02-10 | 2024-10-02 | 496 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
419 | Area 2 | R03 Jabotabek Inner | 3 | JSX870 | JSX870 | 25TS08N2000 | Jabat | 0 | #N/A | 25TS08N2000 | #N/A | PESONARASUNAMENTENGPULODMT | 106.8358 | -6.2222 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SINERGI REKTA DENTA |  | Mitratel | 2015-09-30 | 2025-09-29 | 2025-12-28 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate |  | 0 | 0 | 0
420 | Area 4 | R09 Sulawesi | 9 | UPD772 | UPD772 | 24TS02Z0013 | R09 Sulawesi | 0 | 24TS02Z0013 | 24TS02Z0013 | #N/A | BHT_UPD_MESJIDRAYA1 | 119.4191 | -5.1313 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-12-14 | 2025-12-13 | 2026-03-13 | 2024-12-13 | 455 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
421 | Area 4 | R09 Sulawesi | 9 | UPD759 | UPD759 |  | R09 Sulawesi | 24TS02B0001 | 24TS02B0001 | 24TS02B0001 | #N/A | BHT_UPD_RATULANGI1 | 119.4156 | -5.1466 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-27 | 2025-10-26 | 2026-01-24 | 2025-08-22 | 155 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI |  | RFI | RFI | RFI |  | done
422 | Area 4 | R09 Sulawesi | 9 | UPD770 | UPD770 | 24TS02Z0014 | R09 Sulawesi | 0 | 24TS02Z0014 | 24TS02Z0014 | #N/A | BHT_UPD_AYANI4 | 119.4137 | -5.1328 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-12-14 | 2025-12-13 | 2026-03-13 | 2024-10-17 | 512 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
423 | Area 4 | R09 Sulawesi | 9 | UPD769 | UPD769 |  | R09 Sulawesi | 0 | 24TS02Z0004 | 24TS02Z0004 | #N/A | BHT_UPD_AYANI3 | 119.4106 | -5.1328 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-12-14 | 2025-12-13 | 2026-03-13 | 2024-10-17 | 512 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
424 | Area 4 | R09 Sulawesi | 9 | UPD741 | UPD741 | 24TS01B0627 | R09 Sulawesi | 24TS01B0627 | 24TS01B0627 | 24TS01B0627 | #N/A | BHT_UPD_VETERAN2 | 119.4244 | -5.1422 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-11-13 | 2025-11-12 | 2026-02-10 | 2025-10-27 | 106 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI |  | RFI | RFI | RFI |  | done
425 | Area 4 | R09 Sulawesi | 9 | UPD766 | UPD766 | 24TS02Z0011 | R09 Sulawesi | 0 | 24TS02Z0011 | 24TS02Z0011 | #N/A | BHT_UPD_ALAUDDIN3 | 119.4272 | -5.1719 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-14 | 2025-10-13 | 2026-01-11 | 2024-09-10 | 488 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
426 | Area 4 | R09 Sulawesi | 9 | UPD705 | UPD705 | 24TS01B0629 | R09 Sulawesi | 24TS01B0629 | 24TS01B0629 | 24TS01B0629 | #N/A | BHT_UPD_VETERAN1 | 119.4212 | -5.1325 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-11-13 | 2025-11-12 | 2026-02-10 | 2025-10-16 | 117 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI |  | RFI | RFI | RFI |  | done
427 | Area 4 | R09 Sulawesi | 9 | UPD765 | UPD765 |  | R09 Sulawesi | 24TS02Z0003 | 24TS02Z0003 | 24TS02Z0003 | #N/A | BHT_UPD_ALAUDDIN2 | 119.4217 | -5.1685 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-11-13 | 2025-11-12 | 2026-02-10 | 2025-08-22 | 172 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI |  | RFI | RFI | RFI |  | done
428 | Area 4 | R09 Sulawesi | 9 | UPD773 | UPD773 | 24TS02B0003 | R09 Sulawesi | 24TS02B0003 | 24TS02B0003 | 24TS02B0003 | #N/A | BHT_UPD_MESJIDRAYA2 | 119.4236 | -5.1309 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-11-13 | 2025-11-12 | 2026-02-10 | 2025-08-22 | 172 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI |  | RFI | RFI | RFI |  | done
429 | Area 4 | R09 Sulawesi | 9 | UPD742 | UPD742 | 24TS01B0626 | R09 Sulawesi | 24TS01B0626 | 24TS01B0626 | 24TS01B0626 | #N/A | BHT_UPD_VETERAN3 | 119.425 | -5.1469 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-11-13 | 2025-11-12 | 2026-02-10 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 11.Hold |  | Terminate | Terminate | Terminate |  | Terminate
430 | Area 1 | R02 Sumbagsel | 2 | PLG701 | PLG701 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | EKONOMI UNSRI | 104.733 | -2.9843 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-04-25 | 2026-04-24 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | [7 empty] | Terminate
431 | Area 1 | R02 Sumbagsel | 2 | PLG705 | PLG705 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | TIRTA GARDE PLG | 104.769 | -2.9524 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-05-10 | 2026-05-09 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | [7 empty] | Terminate
432 | Area 4 | R09 Sulawesi | 9 | UPD757 | UPD757 | 24TS02Z0006 | R09 Sulawesi | 0 | 24TS02Z0006 | 24TS02Z0006 | #N/A | BHT_UPD_SUDIRMAN1 | 119.4143 | -5.1382 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-26 | 2025-10-25 | 2026-01-23 | 2024-10-02 | 478 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
433 | Area 4 | R09 Sulawesi | 9 | UPD763 | UPD763 | 24TS02Z0001 | R09 Sulawesi | 0 | 24TS02Z0001 | 24TS02Z0001 | #N/A | BHT_UPD_RATULANGI5 | 119.4187 | -5.1647 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-26 | 2025-10-25 | 2026-01-23 | 2024-09-10 | 500 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
434 | Area 4 | R09 Sulawesi | 9 | UPD761 | UPD761 | 24TS02Z0010 | R09 Sulawesi | 0 | 24TS02Z0010 | 24TS02Z0010 | #N/A | BHT_UPD_RATULANGI3 | 119.4166 | -5.1559 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-27 | 2025-10-26 | 2026-01-24 | 2024-09-10 | 501 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
435 | Area 4 | R09 Sulawesi | 9 | UPD768 | UPD768 | 24TS02Z0007 | R09 Sulawesi | 0 | 24TS02Z0007 | 24TS02Z0007 | #N/A | BHT_UPD_AYANI2 | 119.407 | -5.132 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-12-14 | 2025-12-13 | 2026-03-13 | 2024-08-16 | 574 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | RFI | RFI | RFI |  | done
436 | Area 4 | R09 Sulawesi | 9 | UPD908 | UPD908 |  | R09 Sulawesi | #N/A | #N/A | NY | #N/A | DMT BHT HERTASNING 3 | 119.446 | -5.1647 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-11 | 2026-07-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
437 | Area 4 | R09 Sulawesi | 9 | UPD911 | UPD911 |  | R09 Sulawesi | #N/A | #N/A | NY | 25TS12Z0002 | DMT BHT BORONG INDAH | 119.4541 | -5.1687 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT BERKAH SUKSES SEJATI |  | Mitratel | 2016-07-11 | 2026-07-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 1 RF Add 3 RRU Remove 6 RRU Final Sow Rescope: B2R To MCP
438 | Area 4 | R09 Sulawesi | 9 | UPD909 | UPD909 |  | R09 Sulawesi | #N/A | #N/A | NY | 25TS12Z0001 | DMT BHT HERTASNING 4 | 119.4481 | -5.1672 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT AJIAN TRI SUKSES |  | Mitratel | 2016-07-11 | 2026-07-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 1 RF Add 3 RRU Remove 6 RRU Final Sow Rescope: B2R To MCP
439 | Area 4 | R09 Sulawesi | 9 | UPD910 | UPD910 |  | R09 Sulawesi | #N/A | #N/A | NY | 25TS12Z0003 | DMT BHT HERTASNING 5 | 119.4507 | -5.1698 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT BERKAH SUKSES SEJATI |  | Mitratel | 2016-07-11 | 2026-07-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 1 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: B2R To MCP
440 | Area 4 | R09 Sulawesi | 9 | UPD907 | UPD907 |  | R09 Sulawesi | #N/A | #N/A | NY | #N/A | DMT BHT HERTASNING 2 | 119.4423 | -5.1625 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-11 | 2026-07-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
441 | Area 4 | R09 Sulawesi | 9 | UPD906 | UPD906 |  | R09 Sulawesi | #N/A | #N/A | NY | #N/A | DMT BHT HERTASNING 1 | 119.4369 | -5.1651 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-11 | 2026-07-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
442 | Area 1 | R02 Sumbagsel | 2 | PLG621 | PLG621 |  | R02 Sumbagsel | 0 | NY | NY | #N/A | ILIR BARAT PH1 | 104.725 | -2.9746 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-14 | 2025-09-13 | 2025-12-12 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
443 | Area 4 | R09 Sulawesi | 9 | UPD913 | UPD913 |  | R09 Sulawesi | #N/A | #N/A | NY | #N/A | DMT BHT GRIYA PANAKKUKANG | 119.4436 | -5.1673 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-28 | 2026-07-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
444 | Area 1 | R02 Sumbagsel | 2 | PLG631 | PLG631 |  | R02 Sumbagsel | 0 | NY | NY | #N/A | POLIGON PH6 | 104.7221 | -3.0052 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-12-08 | 2025-12-07 | 2026-03-07 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 08.SIS |  | Terminate | Terminate | Terminate |  | Terminate | [5 empty] | Terminate
445 | Area 1 | R02 Sumbagsel | 2 | PLG700 | PLG700 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | GRAHA UNSRI | 104.734 | -2.9865 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-04-23 | 2026-04-22 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | [7 empty] | Terminate
446 | Area 1 | R02 Sumbagsel | 2 | PLG703 | PLG703 |  | R02 Sumbagsel | #N/A | #N/A | NY | #N/A | HBR MOTIK PLG | 104.71 | -2.9358 | Non MKT | Non MKT | #N/A |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-11 | 2026-07-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | #N/A | [6 empty] | Terminate
447 | Area 2 | R03 Jabotabek Inner | 3 | JUX356 | JUX356 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0099 | PELABUHANMUARABARUDMT | 106.9052 | -6.1083 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SINERGI REKTA DENTA | PT SUMBERSOLUSINDO HITECH | 4 | Mitratel | 2018-02-13 | 2028-02-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Extend Tower | 0 | 0 | 0 | Extend 3m
448 | Area 2 | R03 Jabotabek Inner | 3 | JUX363 | JUX363 |  | Jabat | #N/A | #N/A | NY | 25TS12B0065 | GOLFISLANDMWDMT | 106.9265 | -6.1229 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT GEAF SOLUSIANDA PRATAMA | PT GEAF SOLUSIANDA PRATAMA | 1 | Mitratel | 2018-03-14 | 2028-03-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | B2S | 0 | 0 | 0 | 290 degree arah 130m
449 | Area 2 | R03 Jabotabek Inner | 3 | JKP370 | JKP370 |  | Jabat | #N/A | #N/A | NY | 25TS12Z0108 | PARKIRTIMURGBK | 106.8066 | -6.2181 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT ANUGERAH SELARAS RAYA | PT ANUGERAH SELARAS RAYA | 1 | Mitratel | 2018-01-26 | 2028-01-25 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Extend Tower | 0 | 0 | 0 | Extend 3m
450 | Area 2 | R03 Jabotabek Inner | 3 | JSX016 | JSX016 | 24TS09B0439 | Jabat | 0 | 24TS09B0439 | 24TS09B0439 | #N/A | ALAMSEGAR5DMT | 106.782 | -6.268 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SUMBERSOLUSINDO HITECH |  | Mitratel | 2015-02-27 | 2025-02-26 | 2025-05-27 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 10.Cancel |  | Terminate | Terminate | Terminate |  | Terminate |  | GF | Monopole | 30
451 | Area 2 | R03 Jabotabek Inner | 3 | JSX345 | JSX345 | 24TS10B0025 | Jabat | #N/A | #N/A | 24TS10B0025 | #N/A | JALANKUMBANGDMT | 106.7763 | -6.2976 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | PT SINERGI REKTA DENTA |  | Mitratel | 2016-04-13 | 2026-04-12 |  |  |  |  | Plan ≥ 2026 |  | 10.Cancel |  | Need DRM | Need DRM | OG |  |  |  | GF | Monopole | 32
452 | Area 2 | R03 Jabotabek Inner | 3 | JTX107 | JTX107 | 25TS08N2051 | Jabat | #N/A | #N/A | 25TS08N2051 | #N/A | RELOKSUPERINDODMT | 106.8911 | -6.1848 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | PT SINERGI REKTA DENTA |  | Mitratel | 2016-04-20 | 2026-04-19 |  |  |  |  | Plan ≥ 2026 |  | 10.Cancel |  | Need DRM | Need DRM | OG |  |  |  | GF | Monopole | 32
453 | Area 1 | R10 Sumbagteng | 10 | PBR385 | PBR385 | 25TS05Z0001 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0001 | #N/A | PBR385HL1_SIMPANGTIGA2DMT | 101.4536 | 0.46395 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-07-10 | 2025-07-09 | 2025-10-07 | 2025-08-26 | 42 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-5 | RFI | RFI | RFI |  | done
454 | Area 1 | R10 Sumbagteng | 10 | PBR968 | PBR968 | 25TS05Z0002 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0002 | #N/A | PBR968HL1_JALANDURIANDMT | 101.437 | 0.51648 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-07-20 | 2025-07-19 | 2025-10-17 | 2025-08-26 | 52 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-5 | RFI | RFI | RFI |  | done
455 | Area 1 | R10 Sumbagteng | 10 | PAD381 | PAD381 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0003 | #N/A | STOPADANGAYANI3 | 100.3546 | -0.94294 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-07-22 | 2025-07-21 | 2025-10-19 | 2026-01-31 | -104 | Out SLA | Plan ≤ 2025 | #N/A | 11.Hold | Type-5 | RFC | RFC | OG | 4.12 Proposed ke Type 1 dari type 5 [30/10/25] Hold , Outstanding ELD [20/10/25] [19/09/25] Proses KPKNL , penentuan harga [08/08/2025] [28/07/2025] lahan TNI, need survey validasi |  | Type-5 =>Type-1
456 | Area 1 | R10 Sumbagteng | 10 | PAD684 | PAD684 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0005 | #N/A | PAD684HWD_STO_PADANG_GANTING_2 | 100.3709 | -0.95687 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-07-22 | 2025-07-21 | 2025-10-19 | 2026-01-31 | -104 | Out SLA | Plan ≤ 2025 | #N/A | 11.Hold | Type-5 | RFC | RFC | OG | 4.12 Proposed ke Type 1 dari type 5 [30/10/25] Hold , Outstanding ELD [20/10/25] [08/08/2025] rehunting, lahan pemko, Survei Sept W4 [28/07/2025] Proses BAN/BAK,lahan pemko, need survey, lahan pemko, need survey, proses BAN/BAK |  | Type-5 =>Type-1
457 | Area 1 | R10 Sumbagteng | 10 | BTM846 | BTM846 | 25TS05Z0006 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0006 | #N/A | TIBANKAMPUNG1 | 103.986 | 1.1093 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-05 | 2025-08-04 | 2025-11-02 | 2026-01-31 | -90 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | SIS/SES | Validasi | OG | [14/11/25] [04/11/25] IW OG [29/10/25] Validasi Tenant OG [13/10/25] [22/08/25] Rehunting [08/08/2025] Rehunting, lokasi NOM berada di kawasan rumah liar, tidak bisa diakuisisi, propose 300m luar nom [28/07/2025] rehunting | 30 Feb 26 | BTR
458 | Area 1 | R10 Sumbagteng | 10 | PBR971 | PBR971 | 25TS05Z0007 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0007 | #N/A | PBR971HW1_BUKITBARISAN5DMT | 101.4866 | 0.49124 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-05 | 2025-08-04 | 2025-11-02 | 2026-01-31 | -90 | Out SLA | Plan ≤ 2025 | #N/A | 08.SIS | Type-5 | RFC | RFC | OG | 4.12 Proposed ke Type 1 dari type 5 [05/11/25] Hold- Change Type-1 [30/10/25] Hold ; Potensi Propose Change Type-1 [20/10/25] Rehunting ; Gagal IW Kandidat S [01/10/25] Gagal IW Kandidat S [19/09/25] Validasi Kandidat S [22/08/2025] Reject Kandidat R, Rehunting sesuai arahan RTPE [08/08/2025] Rehunting, gagal IW [28/07/2025] validasi ulang, kandidat Q |  | Type-5 =>Type-1
459 | Area 1 | R10 Sumbagteng | 10 | PBR973 | PBR973 | 25TS05Z0008 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0008 | #N/A | PBR973HW1_UNIVERSITASMUHAMMADIYAHRIAUDMT | 101.4143 | 0.49993 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-05 | 2025-08-04 | 2025-11-02 | 2025-11-30 | -28 | Out SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-5 | RFI | RFI | RFI | 05. RFI | done
460 | Area 1 | R10 Sumbagteng | 10 | PBR386 | PBR386 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0042 | #N/A | PBR386HL1_DELIMA4DMT | 101.4053 | 0.47181 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-06 | 2025-08-05 | 2025-11-03 | 2025-11-30 | -27 | Out SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-5 | RFI | RFI | RFI | 05. RFI | done
461 | Area 1 | R10 Sumbagteng | 10 | PBR427 | PBR427 | 25TS05Z0009 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0009 | #N/A | PBR427HL1_KAWASANUIR2DMT | 101.4476 | 0.43935 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-06 | 2025-08-05 | 2025-11-03 | 2025-08-26 | 69 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-5 | RFI | RFI | RFI |  | done
462 | Area 1 | R10 Sumbagteng | 10 | PBR389 | PBR389 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0010 | #N/A | PBR389HL1_JALANPAJAR2DMTHL1 | 101.4081 | 0.51428 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-07 | 2025-08-06 | 2025-11-04 | 2025-11-30 | -26 | Out SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-5 | RFI | RFI | RFI | 05. RFI | done
463 | Area 1 | R10 Sumbagteng | 10 | PBR426 | PBR426 | 25TS05Z0011 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0011 | #N/A | PBR426HL1_AIRDINGIN3DMT | 101.4598 | 0.44664 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-12 | 2025-08-11 | 2025-11-09 | 2026-01-31 | -83 | Out SLA | Plan ≤ 2025 | #N/A | 08.SIS | Type-5 | RFC | RFC | OG | 4.12 Proposed ke Type 1 dari type 5 [05/11/25] Hold ; Change Type-1 [30/10/25] Hold ; Potensi Propose Change Type-1 [20/10/25] Rehunting ; [19/09/25] IW Done, Plan koordinasi ke TSEL (Tidak bisa dibangun 30m) [22/08/2025] IW DONE, Pole 18m (Lokasi NOM sudah pemekaran 2016 menjadi Kel. Air Dingin, Lokasi Urban ketinggian pole 18m maks Perwako) [08/08/2025] [28/07/2025] Rehunting, Lokasi arahan TSEL |  | Type-5 =>Type-1
464 | Area 1 | R10 Sumbagteng | 10 | PBR438 | PBR438 | 25TS05Z0012 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0012 | #N/A | PBR438HL1_ARIFINAHMAD5DMT | 101.4338 | 0.47966 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-13 | 2025-08-12 | 2025-11-10 | 2025-11-30 | -20 | Out SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-5 | RFC | RFC | OG | [14/11/25] Mounting; Rak Gendong Plan W3 Nov PKU --> Remark Meeting: Propose Plan PLN Connect W3 Nov [30/10/25] Plan W1 Des PLN Connect ; Eksekusi W2 Des 19/07/25 Dok. RFIN Done Plan dibuatkan RFI Notice | 2025-12-18
465 | Area 1 | R10 Sumbagteng | 10 | BTM848 | BTM848 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0013 | #N/A | RUSUNPEMDA | 103.954 | 1.1136 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-14 | 2025-08-13 | 2025-11-11 | 2026-01-31 | -81 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | SITAC | 19. IP Proses | OG | [25/11/25] IP Proses ; Baseframe OG Check [03/10/25] [22/08/25] Rekom camat OG ; Material Pickup Ready [08/08/2025] [28/07/2025] Proses BAN/BAK, Lahan BP Batam jarak kandidat 5 m dari eksisting, lokasi lahan BP batam, proses persetujuan BP | 30 Feb 26 | BTR
466 | Area 3 | R06 Jawa Timur | 6 | MLG084 | MLG084 |  | R06 Jawa Timur | 0 | #N/A | NY | #N/A | GERLAKANGUB | 112.6132 | -7.9561 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-07 | 2025-10-06 | 2026-01-04 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate | Possibility B2R | Terminate
467 | Area 1 | R10 Sumbagteng | 10 | BTM844 | BTM844 | 25TS05Z0014 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0014 | #N/A | BTM844HWD_STO_BATAM_CENTER_ALEXANDRIA | 104.0446 | 1.1157 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-20 | 2025-08-19 | 2025-11-17 | 2026-01-31 | -75 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | SITAC | REKOM | OG | [04/11/25] IW OG [28/10/25] Validasi Kandidat Done ; Reheight 30m [03/10/25] Kandidat Q ditolak BP Batam karna kena rencana pembangunan [19/09/25] Validasi Ulang [25/08/2025] [08/08/2025] BAN/BAK, Lahan BP Batam, FU Developer lahan [08/08/2025] BAN/BAK, Lahan BP Batam, Wait persetujuan BP Batam [28/07/2025] validasi | 30 Feb 26 | BTR
468 | Area 3 | R06 Jawa Timur | 6 | MLG965 | MLG965 | 24TS08N0298 | R06 Jawa Timur | #N/A | #N/A | 24TS08N0298 | #N/A | PETERNAKANUBHBTSDMT | 112.611 | -7.951 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-01-17 | 2027-01-16 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
469 | Area 1 | R10 Sumbagteng | 10 | PBR384 | PBR384 | 25TS05Z0043 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0043 | #N/A | PBR384HL1_KAWASANUNRI6DMT | 101.3854 | 0.4718 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-22 | 2025-08-21 | 2025-11-19 | 2026-01-31 | -73 | Out SLA | Plan ≤ 2025 | #N/A | 08b.SIS Done | Type-5 | RFC | RFC | OG | 4.12 Proposed ke Type 1 dari type 5 [05/11/25] Hold ; Change Type-1 [30/10/25] Hold ; Potensi Propose Change Type-1 [29/10/25] Rehunting [01/10/25] Gagal IW Kandidat Q [19/09/25] [22/08/2025] Rehunting, validasi kandidat Q [08/08/2025] Rehunting, gagal IW [28/07/2025] rehunting, gagal IW, kandidat P |  | Type-5 =>Type-1
470 | Area 1 | R10 Sumbagteng | 10 | PBR440 | PBR440 | 25TS05Z0044 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0044 | #N/A | PBR440ML1_SIMPANGSKPDDMT | 101.4496 | 0.56053 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-22 | 2025-08-21 | 2025-11-19 | 2025-08-26 | 85 | In SLA | Plan ≤ 2025 | #N/A | 02.BAUK | Type-5 | RFI | RFI | RFI |  | done
471 | Area 1 | R10 Sumbagteng | 10 | PBR388 | PBR388 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0045 | #N/A | PBR388HL1_KAWASANUNRIREKTORATDMT | 101.3879 | 0.45805 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-27 | 2025-08-26 | 2025-11-24 | 2025-12-31 | -37 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | RFI | RFI | RFI |  | done
472 | Area 3 | R06 Jawa Timur | 6 | MLG961 | MLG961 | 24TS08N0299 | R06 Jawa Timur | #N/A | #N/A | 24TS08N0299 | #N/A | ARSITEKTURUBHBTSDMT | 112.6129 | -7.9486 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-02-09 | 2027-02-08 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
473 | Area 2 | R03 Jabotabek Inner | 3 | JSX257 | JSX257 |  | Jabat | #N/A | #N/A | 25TS11B0012 | #N/A | JERUKPURUTDALAMDMT | 106.8143 | -6.2845 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SINERGI REKTA DENTA |  | Mitratel | 2015-10-16 | 2025-10-15 | 2026-01-13 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate |  | 0 | 0 | 32
474 | Area 1 | R10 Sumbagteng | 10 | BTM851 | BTM851 | 25TS05Z0015 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0015 | #N/A | INDAHINDUSTRIALPARK | 104.0231 | 1.1374 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-01 | 2025-08-31 | 2025-11-29 | 2025-11-30 | -1 | Out SLA | Plan ≤ 2025 | #N/A | 02.BAUK | Type-5 | RFI | RFI | RFI | type rubah type 6, bangun site baru/collo site terdekat | done
475 | Area 1 | R10 Sumbagteng | 10 | PAD685 | PAD685 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0016 | #N/A | STOTELUKBAYURTELUKBAYUR3 | 100.3878 | -0.9856 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-04 | 2025-09-03 | 2025-12-02 | 2026-01-31 | -60 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | SITAC | IW | OG | [17/11/25] [14/11/25] IW OG [20/10/2025] [28/07/2025] Proses BAN/BAK, lahan pemko, Survei Sept W4 lahan pemko, need survey | 30 Feb 26 | BTR
476 | Area 1 | R10 Sumbagteng | 10 | PBR394 | PBR394 | 25TS05Z0017 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0017 | #N/A | PBR394HW1_PEKANBARUKOTA10DMT | 101.4227 | 0.52697 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-04 | 2025-09-03 | 2025-12-02 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 11.Hold | Type-5 | Terminate | Terminate | Terminate |  | Terminate
477 | Area 1 | R10 Sumbagteng | 10 | BTM352 | BTM352 | 25TS05Z0018 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0018 | #N/A | STOSAGULUNGBATUAJIAVIARI | 103.9717 | 1.0492 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-07 | 2025-09-06 | 2025-12-05 | 2026-01-31 | -57 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | SITAC | IW | OG | [25/11/25] [22/08/25] IW OG ; HARD IW [08/08/2025] Proses BAN/BAK, Lahan BP Batam [28/07/2025] Proses BAN/BAK, Lahan Pemko lahan pemko, need survey | 30 Feb 26 | BTR
478 | Area 1 | R10 Sumbagteng | 10 | PAD663 | PAD663 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0019 | #N/A | PAD663DDSITEB | 100.3723 | -0.89426 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-07 | 2025-09-06 | 2025-12-05 | 2026-01-31 | -57 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | SITAC | BAN/BAK | OG | [17/11/25] [19/09/25] BAN/BAK ; Proses KPKNL , penentuan harga [25/08/2025] [28/07/2025] Proses BAN/BAK, Lahan TNI, waiting survey lahan pemko, need survey | 30 Feb 26 | BTR
479 | Area 1 | R10 Sumbagteng | 10 | PBR972 | PBR972 | 25TS05Z0020 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0020 | #N/A | PBR972HM1_UNIVERSITASRIAUGOBAHDMT | 101.4526 | 0.52467 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-09 | 2025-09-08 | 2025-12-07 | 2025-11-30 | 7 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-5 | RFI | RFI | RFI | type 5 itu extend | done
480 | Area 3 | R06 Jawa Timur | 6 | MLG963 | MLG963 |  | R06 Jawa Timur | #N/A | #N/A | NY | #N/A | PEREMPATANSAINSUINDMT | 112.6074 | -7.9514 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-02-14 | 2027-02-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
481 | Area 1 | R10 Sumbagteng | 10 | PBR392 | PBR392 | 25TS05Z0046 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0046 | #N/A | PBR392HM1_PERUMGRIYAARYADMT | 101.3861 | 0.45347 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-10 | 2025-09-09 | 2025-12-08 | 2025-12-31 | -23 | Out SLA | Plan ≤ 2025 | #N/A | 09.Pro.Cancel | Type-5 | DROP | 32. Cancelled by Tenant | Proposed Drop | [07/11/25] [30/10/25] Drop by Tenant Hasil Meeting 30/10 [20/10/25] IW OG [03/10/25] Rehunting; joint survey dengan pak Fery [19/09/25] IW OG ; 100m dari tower TBG [08/08/2025] Rehunting Gagal IW [28/07/2025] validasi ulang kandidat Q Kandidat terlalu dekat site eksisting DMT | drop
482 | Area 4 | R08 Kalimantan | 8 | BBR223 | BBR223 | 24TS02C0002 | R08 Kalimantan | 0 | 24TS02C0002 | 24TS02C0002 | #N/A | MTH_UNLAM_BANJARBARU2 | 114.8412 | -3.4447 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-07-22 | 2025-07-21 | 2025-10-19 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate | Blacksite | Terminate
483 | Area 1 | R10 Sumbagteng | 10 | PBR983 | PBR983 | 25TS05Z0021 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0021 | #N/A | PBR983HL1_BANDAACEH3DMT | 101.4721 | 0.50049 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-12 | 2025-09-11 | 2025-12-10 | 2025-11-30 | 10 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-5 | RFI | RFI | RFI |  | done
484 | Area 4 | R08 Kalimantan | 8 | BJM314 | BJM314 | 25TS05N0087 | R08 Kalimantan | 0 | 24TS02C0001 | 25TS05N0087 | #N/A | MT_UNLAM_BANJARMASIN2 | 114.5859 | -3.2978 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-11 | 2025-08-10 | 2025-11-08 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate | Blacksite | Terminate
485 | Area 1 | R10 Sumbagteng | 10 | BTM405 | BTM405 | 25TS05Z0022 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0022 | #N/A | STOKABILSMPSHARAPANUTAMA | 104.1235 | 1.0709 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-13 | 2025-09-12 | 2025-12-11 | 2025-11-30 | 11 | In SLA | Plan ≤ 2025 | #N/A | 04.CME | Type-5 | CME | Excavation | OG | [26/11/25] [04/11/25] Galian OG - Hold issue ahli waris ; Baseframe bawah [02/11/25] Galian OG [27/10/25] [03/10/25] Rekom Lurcam og [19/09/25] IW Done, Wait Invoice & PKS Lahan BP BATAM [25/08/2025] [08/08/2025] Proses BAN/BAK, Lahan BP BATAM, Paralel IW Done [28/07/2025] validasi Negosiasi penambahan space | 2025-12-30 | BTR
486 | Area 4 | R08 Kalimantan | 8 | SMR434 | SMR434 |  | R08 Kalimantan | 0 | 24TS08Z0003 | 24TS08Z0003 | #N/A | MTH_GUBERNURANSMD1 | 117.1484 | -0.49436 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-22 | 2025-10-21 | 2026-01-19 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate | Blacksite | Terminate
487 | Area 1 | R10 Sumbagteng | 10 | BTM853 | BTM853 | 25TS05Z0023 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0023 | #N/A | STOBATAMCENTERWALAKAKAIPARK | 104.0475 | 1.1091 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-13 | 2025-09-12 | 2025-12-11 | 2026-01-31 | -51 | Out SLA | Plan ≤ 2025 | #N/A | 04.CME | Type-5 | CME | HILTI | OG | [25/11/25] Hilti OG ; MOS [03/10/25] Rekom lurcam OG [19/09/25] [08/08/2025] IW OG [28/07/2025] Validasi | 2025-12-30 | BTR
488 | Area 1 | R10 Sumbagteng | 10 | PAD661 | PAD661 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0024 | #N/A | STOPADANGCENTERHOTELIBIS | 100.3632 | -0.92947 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-13 | 2025-09-12 | 2025-12-11 | 2026-01-31 | -51 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | SITAC | BAN/BAK | OG | [17/11/25] [19/09/25] Waiting Survei Pemprov [25/08/25] [28/07/2025] Proses BAN/BAK, Lahan Pemprov lahan pemko, need survey | 2026-01-30 | BTR
489 | Area 1 | R10 Sumbagteng | 10 | BTM859 | BTM859 | 25TS05Z0025 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0025 | #N/A | BTM859HWD_STO_KABIL_KABIL_INDUSTRIAL_ESTATE | 104.1326 | 1.1121 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-29 | 2025-09-28 | 2025-12-27 | 2025-11-30 | 27 | In SLA | Plan ≤ 2025 | #N/A | 04.CME | Type-5 | CME | 13. Rebaring | OG | [30/11/25] [26/11/25] Rebaring og, Wait Angkur & Tamplate onsite [23/11/25] [14/11/25] Lantai Kerja Done, Waiting Material Tower Onsite [13/11/25] Lantai Kerja Done, Rebaring og [09/11/25] Galian Bored Pile 9/9 Titik Done, Pembesian BP og [04/11/25] [02/11/25] Site Opening & Bowplank [03/10/25] Rekom lurcam OG [19/09/25] [28/07/25] validasi ulang, kandidat S Negosiasi proposed MT 20 meter | 2025-12-24 | BTR
490 | Area 4 | R08 Kalimantan | 8 | BBR225 | BBR225 |  | R08 Kalimantan | #N/A | #N/A | NY | #N/A | MTH_LAPMURJANI1 | 114.8307 | -3.4425 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-08-02 | 2026-08-01 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
491 | Area 1 | R10 Sumbagteng | 10 | PAD384 | PAD384 | 25TS05Z0026 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0026 | #N/A | PAD384HWD_STO_PADANG_CENTRUM_KAMPUNG_NIAS_2 | 100.3712 | -0.964 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-05 | 2025-10-04 | 2026-01-02 | 2026-01-31 | -29 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | SITAC | BAN/BAK | OG | [28/11/2025] Propose change to type-1 temporary [17/11/2025] [28/07/2025] Proses BAN/BAK, Lahan Pemko, Plan survei W4 lahan pemko, need survey | 2026-01-30 | BTR
492 | Area 1 | R10 Sumbagteng | 10 | PAD666 | PAD666 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0027 | #N/A | STOPADCENTRUMUNIVPUTRAINDONESIA | 100.3972 | -0.96005 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-05 | 2025-10-04 | 2026-01-02 | 2026-01-31 | -29 | Out SLA | Plan ≤ 2025 | #N/A | 11.Hold | Type-5 | RFC | RFC | OG | 4.12 Proposed ke Type 1 dari type 5 [30/10/25] Hold by tenant [29/10/25] Rehunting [19/09/25] Proses IW di site Existing [08/08/2025] Rehunting, Gagal IW [28/07/2025] Gagal IW, Kandidat Q, Rehunting |  | Type-5 =>Type-1
493 | Area 1 | R10 Sumbagteng | 10 | PBR970 | PBR970 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0028 | #N/A | PBR970HL1_NANGKA5DMT | 101.4428 | 0.50815 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-05 | 2025-10-04 | 2026-01-02 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 11.Hold | Type-5 | Terminate | Terminate | Terminate |  | Terminate
494 | Area 1 | R10 Sumbagteng | 10 | PBR967 | PBR967 | 25TS05Z0029 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0029 | #N/A | N_PBR967ML1_MASJIDALIRSYADDMT | 101.4448 | 0.52753 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-06 | 2025-10-05 | 2026-01-03 | 2025-11-30 | 34 | In SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-5 | RFI | RFI | RFI | 05. RFI | done
495 | Area 1 | R10 Sumbagteng | 10 | BTM308 | BTM308 |  | R10 Sumbagteng | 0 | #N/A | NY | #N/A | STOSAGULUNGTOP100BATUAJI | 103.9999 | 1.0401 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-07 | 2025-10-06 | 2026-01-04 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
496 | Area 1 | R10 Sumbagteng | 10 | BTM856 | BTM856 | 25TS05Z0030 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0030 | #N/A | BTM856HWD_BATAMCENTER_EXECUTIVE_INDUSTRIAL_PARK | 104.0585 | 1.1153 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-07 | 2025-10-06 | 2026-01-04 | 2026-01-31 | -27 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | SITAC | REKOM | OG | [25/11/25] [03/10/25] Rekom lurcam OG [19/09/25] IW OG [25/08/2025] [22/08/2025] Validasi kandidat S. Paralel BAN BAK & IW [21/08/2025] Validasi Kandidat P [08/08/2025] Rehunting, [28/07/2025] validasi | 2026-01-30 | BTR
497 | Area 1 | R10 Sumbagteng | 10 | BTM350 | BTM350 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0031 | #N/A | STOBATUAMPARSIMPANGMELCEM | 104.0213 | 1.172 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-13 | 2025-10-12 | 2026-01-10 | 2026-01-31 | -21 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | SITAC | 19. IP Proses | OG | [25/11/25] [20/10/25] Rekom Lurcam OG [23/09/25] IW Done [19/09/25] IW OG [22/08/2025] Rehunting [28/07/2025] rehunting, lokasi greenfield | 2026-01-30 | BTR
498 | Area 4 | R09 Sulawesi | 9 | UPD703 | UPD703 | 24TS02Z0008 | R09 Sulawesi | 0 | 24TS02Z0008 | 24TS02Z0008 | #N/A | BHT_UPD_BANDANG | 119.4202 | -5.1288 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-26 | 2025-10-25 | 2026-01-23 | 2025-05-15 | 253 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI |  | RFI | RFI | RFI |  | done
499 | Area 2 | R03 Jabotabek Inner | 3 | JPX050 | JPX050 |  |  | #N/A | #N/A | NY | #N/A | PROKLAMASICIKINIDMT | 106.846 | -6.2003 | Non MKT | Non MKT | #N/A |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-05-13 | 2027-05-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | #N/A |  |  | #N/A | #N/A | #N/A
500 | Area 1 | R10 Sumbagteng | 10 | PAD664 | PAD664 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0032 | #N/A | STOULAKKARANGUNIVBUNGHATTA | 100.3555 | -0.9106 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-13 | 2025-10-12 | 2026-01-10 | 2026-01-31 | -21 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | SITAC | IW | OG | [17/11/25] [14/11/25] IW OG ; Lahan Pemko [20/10/25] Proses Bank/Bak ; Lahan Pemko [03/10/25] Surat Permohonan survey pemanfaatan media jalan untuk pembangunan menara sdh submit list nya ke PU. Dan saat ini waiting feedback dari PU. Sesuai aturan yg diinfo oleh PU bahwa utk dilahan fasum, dan selama posisi tower yg akan dibangun masih di posisi yg berdekatan, maka masih diperbolehkan. [19/08/2025] [28/07/2025] Proses BAN/BAK, lahan pemko, Survei Sept W4 lahan pemko, need survey | 30 Feb 26 | BTR
501 | Area 1 | R10 Sumbagteng | 10 | PAD678 | PAD678 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0033 | #N/A | STOPADANGPURUS | 100.3514 | -0.9392 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-13 | 2025-10-12 | 2026-01-10 | 2026-01-31 | -21 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | SITAC | IW | OG | [17/11/25] [14/11/25] IW OG; Lahan Pemko [20/10/25] [03/10/25] Proses BAN/BAK, lahan pemko [19/08/2025] [28/07/2025] Proses BAN/BAK, lahan pemko, Survei Sept W4 lahan pemko, need survey | 30 Feb 26 | BTR
502 | Area 1 | R10 Sumbagteng | 10 | PAD679 | PAD679 | 25TS05Z0034 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0034 | #N/A | STOULAKARANGTABING3 | 100.348 | -0.88678 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-13 | 2025-10-12 | 2026-01-10 | 2025-11-03 | 68 | In SLA | Plan ≤ 2025 | #N/A | 02.BAUK | Type-5 | RFI | RFI | RFI |  | done
503 | Area 1 | R10 Sumbagteng | 10 | PAD681 | PAD681 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0035 | #N/A | STOSITEBAPASARSITEBA2 | 100.361 | -0.88951 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-13 | 2025-10-12 | 2026-01-10 | 2026-01-31 | -21 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | SITAC | IW | OG | [17/11/25] [14/11/25] IW OG [20/10/25] [03/10/25] Proses BAN/BAK, lahan pemko [19/08/2025] [28/07/2025] Proses BAN/BAK, lahan pemko, Survei Sept W4 lahan pemko, need survey | 30 Feb 26 | BTR
504 | Area 4 | R09 Sulawesi | 9 | UPD756 | UPD756 | 24TS02Z0012 | R09 Sulawesi | 0 | 24TS02Z0012 | 24TS02Z0012 | #N/A | BHT_UPD_KARTINI1 | 119.4106 | -5.136 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-27 | 2025-10-26 | 2026-01-24 | 2025-05-15 | 254 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI |  | RFI | RFI | RFI |  | done
505 | Area 4 | R09 Sulawesi | 9 | UPD767 | UPD767 | 25TS08N1269 | R09 Sulawesi | 0 | 24TS01B0628 | 25TS08N1269 | #N/A | BHT_UPD_AYANI1 | 119.4071 | -5.1326 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-12-14 | 2025-12-13 | 2026-03-13 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 11.Hold |  | Terminate | Terminate | Terminate |  | Terminate
506 | Area 1 | R10 Sumbagteng | 10 | PBR976 | PBR976 | 25TS05Z0036 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0036 | #N/A | PBR976HL1_RUMAHSAKITAYANIDMT | 101.4555 | 0.49608 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-13 | 2025-10-12 | 2026-01-10 | 2025-11-30 | 41 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI | Type-5 | RFI | RFI | RFI |  | done
507 | Area 4 | R09 Sulawesi | 9 | UPD771 | UPD771 | 25TS08U0739 | R09 Sulawesi | 0 | 24TS02B0002 | 25TS08U0739 | #N/A | BHT_UPD_BULUSARAUNG | 119.4156 | -5.1323 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-12-14 | 2025-12-13 | 2026-03-13 | 2025-08-22 | 203 | In SLA | Plan ≤ 2025 | #N/A | 03.RFI |  | RFI | RFI | RFI |  | done
508 | Area 1 | R10 Sumbagteng | 10 | PBR377 | PBR377 |  | R10 Sumbagteng | 0 | #N/A | NY | #N/A | PBR377HW1_PASARARENGKADMT | 101.4179 | 0.46371 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-14 | 2025-10-13 | 2026-01-11 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
509 | Area 1 | R10 Sumbagteng | 10 | PBR378 | PBR378 | 25TS05Z0037 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0037 | #N/A | PBR378HL1_JALANRIAU4DMT | 101.4204 | 0.541 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-14 | 2025-10-13 | 2026-01-11 | 2026-01-31 | -20 | Out SLA | Plan ≤ 2025 | #N/A | 08.SIS | Type-5 | RFC | RFC | OG | 4.12 Proposed ke Type 1 dari type 5 [05/11/25] Hold ; Change Type-1 [30/10/25] Hold ; Potensi Propose Change Type-1 [20/10/25] [28/07/25] rehunting, Lokasi arahan TSEL akan menemui pihak developer |  | Type-5 =>Type-1
510 | Area 1 | R10 Sumbagteng | 10 | PAD670 | PAD670 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0038 | #N/A | STOPADANGCENTRUMDOBI2 | 100.3575 | -0.96114 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-27 | 2025-10-26 | 2026-01-24 | 2026-01-31 | -7 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC | Type-5 | SITAC | BAN/BAK | OG | [17/11/25] [14/11/25] BAN/BAK, Lahan Pemko [20/10/2025] [28/07/2025] Proses BAN/BAK, lahan pemko, Survei Sept W4 lahan pemko, need survey | 30 Feb 26 | BTR
511 | Area 1 | R10 Sumbagteng | 10 | PBR990 | PBR990 |  | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0039 | #N/A | PBR990HL1_JALANTIUNGDMT | 101.4292 | 0.50916 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-11-09 | 2025-11-08 | 2026-02-06 | 2025-11-30 | 68 | In SLA | Plan ≤ 2025 | #N/A | 04.SRFI | Type-5 | RFI | RFI | RFI | 05. RFI | done
512 | Area 1 | R10 Sumbagteng | 10 | PAD688 | PAD688 | 25TS05Z0040 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0040 | #N/A | PAD688HWD_STO_TELUK_BAYUR_SPLIT_PEGAMBIRAN | 100.3921 | -0.96841 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-12-21 | 2025-12-20 | 2026-03-20 | 2025-11-30 | 110 | In SLA | Plan ≤ 2025 | #N/A | 04.CME | Type-5 | CME | Excavation | OG | [21/11/25] [14/10/25] HOLD Sementara - Pemuda Setempat [11/09/25] Pek. DPT, Dinding penahan tanah done, Plan Lantai kerja og [07/09/2025] Pek. DPT mengatasi longsor og [02/09/2025] GalianTapak pondasi og, Terkendala longsor, Perubahan APD, Material Tower Onsite [29/08/2025] [22/08/2025] Galian manual tapak pondasi og, Barbending og, Material Tower Delivery [21/08/2025] Galian Bored Pile 3/5 og, Material Tower Delivery [19/08/2025] Tim CME & Tim Bored pile Onsite, Pembongkaran Dapur LL [18/08/2025] Plan start CME 19/8 [16/08/2025] Plan start CME 18/8 [11/08/2025] [26/07/2025] Site Opening, Bouwplank Done | Hold, Commcase | BTR
513 | Area 1 | R10 Sumbagteng | 10 | PAD668 | PAD668 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0038 | STOPADANGCENTRUMSTASIUNPADANG | 100.3738 | -0.94215 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT INFINITI LAUTAN ARTHA |  | Mitratel | 2016-01-04 | 2026-01-03 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
514 | Area 1 | R10 Sumbagteng | 10 | PAD680 | PAD680 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0035 | PAD680DDGULA2 | 100.3887 | -0.95603 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT SANJIWAHANA PERSADA |  | Mitratel | 2016-01-20 | 2026-01-19 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
515 | Area 1 | R10 Sumbagteng | 10 | PBR379 | PBR379 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0009 | PBR379HW1_MAJESTICHOTELDMT | 101.4468 | 0.54066 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT KONCERFO SUKSES CEMERLANG |  | Mitratel | 2016-01-20 | 2026-01-19 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to MCP
516 | Area 1 | R10 Sumbagteng | 10 | PBR997 | PBR997 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0014 | PBR997ML1_JLPEMBANGUNAN2DMT | 101.4377 | 0.56378 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT Rayateh Utama Teladan Canggih |  | Mitratel | 2016-01-20 | 2026-01-19 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
517 | Area 1 | R10 Sumbagteng | 10 | PAD687 | PAD687 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0034 | STOTELUKBAYUR4 | 100.3851 | -0.99458 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT SANJIWAHANA PERSADA |  | Mitratel | 2016-01-21 | 2026-01-20 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
518 | Area 1 | R10 Sumbagteng | 10 | PAD689 | PAD689 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0031 | STOTELUKBAYURRAWANGJONDUL2 | 100.3793 | -0.98531 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT SANJIWAHANA PERSADA |  | Mitratel | 2016-01-21 | 2026-01-20 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
519 | Area 1 | R10 Sumbagteng | 10 | BTM843 | BTM843 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0020 | #N/A | PERUMPJB | 103.9451 | 1.0448 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-03-04 | 2026-03-03 |  |  |  |  | Plan ≥ 2026 |  | 03.RFI | Type-1 | Need DRM |  | OG | Add 3 RF Add 12 RRU Final Sow Rescope: Type-1 |  | Type-1
520 | Area 1 | R10 Sumbagteng | 10 | BTM524 | BTM524 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0010 | #N/A | KAWASANINDUSTRIBERIKAT | 103.9224 | 1.0604 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-05-25 | 2026-05-24 |  |  |  |  | Plan ≥ 2026 |  | 06.SITAC | Type-5 | SITAC | SITAC | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro |  | BTR
521 | Area 1 | R10 Sumbagteng | 10 | BTM526 | BTM526 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0011 | #N/A | STOBATAMCENTREMARCELIA2 | 104.0326 | 1.1119 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-06-10 | 2026-06-09 |  |  |  |  | Plan ≥ 2026 |  | 08b.SIS Done | Type-5 | SIS/SES | SIS | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
522 | Area 1 | R10 Sumbagteng | 10 | PBR395 | PBR395 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0030 | PBR395HW1_UNRI1DMT | 101.3777 | 0.47473 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT SIDOMA JAYA MANDIRI |  | Mitratel | 2016-06-14 | 2026-06-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
523 | Area 1 | R10 Sumbagteng | 10 | PBR988 | PBR988 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0032 | PBR988HL1_UNRI2DMT | 101.3791 | 0.47818 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT SIDOMA JAYA MANDIRI |  | Mitratel | 2016-06-14 | 2026-06-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 9 RRU Final Sow Rescope: B2R to Mini Macro
524 | Area 1 | R10 Sumbagteng | 10 | PBR994 | PBR994 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0011 | PBR994HW1_DELIMA8DMT | 101.4124 | 0.4837 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT KONCERFO SUKSES CEMERLANG |  | Mitratel | 2016-06-15 | 2026-06-14 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-1 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
525 | Area 1 | R01 Sumbagut | 1 | BJI352 | BJI352 |  | R01 Sumbagut | #N/A | #N/A | NY | #N/A | MCPERINTISKEMERDEKAANDMT | 98.4945 | 3.6268 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-05-01 | 2026-04-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 6 RRU Remove 6 RRU Final Sow Rescope: 1. B2R to Mini Macro
526 | Area 1 | R10 Sumbagteng | 10 | BTM356 | BTM356 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09R0004 | #N/A | PERUMHANGLEKIR2 | 104.0489 | 1.1054 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-08 | 2026-07-07 |  |  |  |  | Plan ≥ 2026 |  | 04.CME | Type-5 | Need DRM |  | OG | Add 3 RF Add 3 RRU Final Sow Rescope: Type-6 (Same TP)
527 | Area 4 | R09 Sulawesi | 9 | UPD912 | UPD912 |  | R09 Sulawesi | #N/A | #N/A | NY | #N/A | DMT BHT MINASAUPA | 119.4592 | -5.1798 | Non MKT | Non MKT | #N/A |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-28 | 2026-07-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | #N/A
528 | Area 1 | R10 Sumbagteng | 10 | BTM720 | BTM720 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0001 | #N/A | BTM720HW_PERUM_PERMATA_HIJAU | 103.9594 | 1.0444 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-08 | 2026-07-07 |  |  |  |  | Plan ≥ 2026 |  | 03.RFI | Type-1 | RFI | RFI | RFI | Add 3 RF Add 8 RRU Final Sow Rescope: Type-1 |  | Type-1
529 | Area 1 | R10 Sumbagteng | 10 | BTM798 | BTM798 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0015 | #N/A | POLRESBATAM | 104.0174 | 1.1194 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-08 | 2026-07-07 |  |  |  |  | Plan ≥ 2026 |  | 06.SITAC | Type-5 | Need DRM |  | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
530 | Area 1 | R10 Sumbagteng | 10 | BTM897 | BTM897 | 25TS02Z0001 | R10 Sumbagteng | #N/A | #N/A | 25TS02Z0001 | #N/A | STOSAGULUNGTAMANSISWA | 103.9811 | 1.0511 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-08 | 2026-07-07 |  |  |  |  | Plan ≥ 2026 |  | 02.BAUK | Type-5 | RFI | RFI | RFI | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
531 | Area 1 | R10 Sumbagteng | 10 | PAD463 | PAD463 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0024 | PAD463HWD_STO_TELUK_BAYUR_BANUARAN_7 | 100.385 | -0.9753 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT MITRA SISTEMATIKA GLOBAL |  | Mitratel | 2016-07-08 | 2026-07-07 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-1 | Need DRM |  | OG | Add 3 RF Add 8 RRU Final Sow Rescope: Type-1 |  | Type-1
532 | Area 2 | R12 Jabotabek Outer | 12 | KRW846 | KRW846 |  | Eastern Jabodetabek | #N/A | #N/A | 25TS01B0011 | #N/A | KIS11DMT | 107.3325 | -6.3907 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT AGUNGMAS PRIMA SEMPURNA |  | Mitratel | 2016-06-22 | 2026-06-21 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS |  | SIS/SES | BAN/BAK | OG | Add 3 RF Add 6 RRU Final Sow Rescope: BTR to Macro |  |  | GF | SST | 42
533 | Area 1 | R10 Sumbagteng | 10 | PBR516 | PBR516 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0023 | N_PBR516HL1_AIRHITAMDMT | 101.3685 | 0.49975 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT SIDOMA JAYA MANDIRI |  | Mitratel | 2016-07-08 | 2026-07-07 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-1 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
534 | Area 1 | R10 Sumbagteng | 10 | PBR530 | PBR530 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0022 | PBR530HW1_POISMKKANSAIPEKANBARUDMT | 101.4001 | 0.46797 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT SIDOMA JAYA MANDIRI |  | Mitratel | 2016-07-08 | 2026-07-07 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
535 | Area 1 | R10 Sumbagteng | 10 | PBR531 | PBR531 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0050 | PBR531HL1_PTINDOFOODDMT | 101.439 | 0.42582 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT PRASETIA DWIDHARMA |  | Mitratel | 2016-07-08 | 2026-07-07 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
536 | Area 1 | R10 Sumbagteng | 10 | PBR538 | PBR538 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0018 | PBR538HL1_SMAN9PKUDMT | 101.4591 | 0.52753 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT Rayateh Utama Teladan Canggih |  | Mitratel | 2016-07-08 | 2026-07-07 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
537 | Area 1 | R10 Sumbagteng | 10 | PBR542 | PBR542 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0017 | PBR542HL1_JLPAUSDMT | 101.438 | 0.48912 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT Rayateh Utama Teladan Canggih |  | Mitratel | 2016-07-08 | 2026-07-07 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-1 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
538 | Area 1 | R10 Sumbagteng | 10 | BTM854 | BTM854 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0002 | #N/A | STOLUBUKBAJAMALINDO | 104.0122 | 1.1657 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-08 | 2026-07-07 |  |  |  |  | Plan ≥ 2026 |  | 03.RFI | Type-1 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
539 | Area 1 | R10 Sumbagteng | 10 | PAD464 | PAD464 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0054 | STOULAKKARANGBELIBIS2 | 100.3476 | -0.90118 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT INDOTEKNIK TJANDRA UTAMA |  | Mitratel | 2016-07-11 | 2026-07-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 8 RRU Final Sow Rescope: B2R to Mini Macro
540 | Area 1 | R10 Sumbagteng | 10 | BTM506 | BTM506 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0021 | #N/A | BTM506GDBKBR2 | 104.0336 | 1.1675 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-14 | 2026-07-13 |  |  |  |  | Plan ≥ 2026 |  | 03.RFI | Type-1 | RFI | RFI | RFI | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
541 | Area 1 | R10 Sumbagteng | 10 | PAD484 | PAD484 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0052 | ULAKKARANG3 | 100.3474 | -0.90666 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT INDOTEKNIK TJANDRA UTAMA |  | Mitratel | 2016-07-14 | 2026-07-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
542 | Area 1 | R10 Sumbagteng | 10 | BTM353 | BTM353 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0004 | #N/A | BTM353HWD_STO_SAGULUNG_PT_ASL | 103.9041 | 1.0822 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-19 | 2026-07-18 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS | Type-5 | SIS/SES | SIS | OG | Add 3 RF Add 9 RRU Final Sow Rescope: B2R to Mini Macro
543 | Area 1 | R10 Sumbagteng | 10 | BTM858 | BTM858 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0022 | #N/A | PANBILINDUSTRIALESTATE | 104.0262 | 1.0771 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-19 | 2026-07-18 |  |  |  |  | Plan ≥ 2026 |  | 03.RFI | Type-1 | RFI | RFI | RFI | Add 3 RF Add 9 RRU Final Sow Rescope: Type-1 |  | Type-1
544 | Area 1 | R10 Sumbagteng | 10 | PAD386 | PAD386 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0040 | JATI4 | 100.3693 | -0.93969 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT INFINITI LAUTAN ARTHA |  | Mitratel | 2016-07-25 | 2026-07-24 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
545 | Area 1 | R10 Sumbagteng | 10 | PAD667 | PAD667 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0016 | STOPDGCENTRUMRSUMDJAMIL | 100.3703 | -0.94304 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT LIMA INTI SINERGI |  | Mitratel | 2016-07-25 | 2026-07-24 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-1 | Need DRM |  | OG | Add 3 RF Add 7 RRU Final Sow Rescope: Type-1 |  | Type-1
546 | Area 1 | R10 Sumbagteng | 10 | PAD487 | PAD487 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0051 | STOULAKKARANGUNP2 | 100.3485 | -0.89466 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT INDOTEKNIK TJANDRA UTAMA |  | Mitratel | 2016-08-08 | 2026-08-07 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
547 | Area 1 | R10 Sumbagteng | 10 | PAD468 | PAD468 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0055 | STOPADCENTRUMKANTORPOLDASUMBAR | 100.3609 | -0.93658 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT INDOTEKNIK TJANDRA UTAMA |  | Mitratel | 2016-08-09 | 2026-08-08 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
548 | Area 1 | R10 Sumbagteng | 10 | BTM520 | BTM520 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0023 | #N/A | STONONGSAKAMPUNGPANGLONG | 104.1195 | 1.1435 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-08-14 | 2026-08-13 |  |  |  |  | Plan ≥ 2026 |  | 03.RFI | Type-1 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
549 | Area 1 | R10 Sumbagteng | 10 | PBR517 | PBR517 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0019 | PBR517HW1_AURAJAWALIDMT | 101.4361 | 0.45848 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT PASIFIK MORA TAMA |  | Mitratel | 2016-08-14 | 2026-08-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
550 | Area 1 | R10 Sumbagteng | 10 | PBR390 | PBR390 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0033 | PBR390MM1_CIPTAKARYA3DMT | 101.3964 | 0.43969 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT INDOTEKNIK TJANDRA UTAMA |  | Mitratel | 2016-09-12 | 2026-09-11 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 10 RRU Final Sow Rescope: B2R to Mini Macro
551 | Area 1 | R10 Sumbagteng | 10 | BTM521 | BTM521 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0009 | #N/A | STOSAGULUNGKAPLINGKAMBOJA | 103.9447 | 1.0362 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-09-19 | 2026-09-18 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS | Type-5 | SIS/SES | SIS | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
552 | Area 1 | R10 Sumbagteng | 10 | PAD665 | PAD665 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0039 | STOULKKRGUNIVERSITASNEGERIPADANG | 100.3509 | -0.89928 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT INFINITI LAUTAN ARTHA |  | Mitratel | 2016-10-13 | 2026-10-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 9 RRU Final Sow Rescope: B2R to Mini Macro
553 | Area 1 | R10 Sumbagteng | 10 | BTM301 | BTM301 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0003 | #N/A | LEGENDABALI2 | 104.0237 | 1.1229 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-10-24 | 2026-10-23 |  |  |  |  | Plan ≥ 2026 |  | 06.SITAC | Type-5 | SITAC | SITAC | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
554 | Area 1 | R10 Sumbagteng | 10 | BTM895 | BTM895 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0050 | #N/A | STOLUBUKBAJASTPIETER | 104.0146 | 1.1352 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-10-24 | 2026-10-23 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS | Type-5 | Need DRM |  | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
555 | Area 1 | R10 Sumbagteng | 10 | PBR534 | PBR534 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0021 | PBR534HL1_SMACENDANAPEKANBARUTEL | 101.4378 | 0.56897 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT SIDOMA JAYA MANDIRI |  | Mitratel | 2016-10-24 | 2026-10-23 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
556 | Area 1 | R10 Sumbagteng | 10 | BTM510 | BTM510 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0006 | #N/A | STOBATAMCENTERCITRALAND | 104.0625 | 1.1261 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-11-01 | 2026-10-31 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS | Type-5 | SIS/SES | SIS | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
557 | Area 2 | R03 Jabotabek Inner | 3 | JPX172 | JPX172 |  |  | #N/A | #N/A | NY | #N/A | JLHAJIFACHRUDINDMT | 106.8181 | -6.1836 | Non MKT | Non MKT | #N/A |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-06-29 | 2026-06-28 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | #N/A |  |  | #N/A | #N/A | #N/A
558 | Area 1 | R10 Sumbagteng | 10 | PBR382 | PBR382 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0013 | PBR382HL1_JALANRAYAPEKANBARU7TEL | 101.4454 | 0.52191 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT Rayateh Utama Teladan Canggih |  | Mitratel | 2016-12-07 | 2026-12-06 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 9 RRU Final Sow Rescope: Type-1 |  | Type-1
559 | Area 1 | R10 Sumbagteng | 10 | BTM511 | BTM511 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0007 | #N/A | STONONGSACITRAMASINDAH | 104.1281 | 1.155 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-12-07 | 2026-12-06 |  |  |  |  | Plan ≥ 2026 |  | 06.SITAC | Type-5 | SITAC | SITAC | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
560 | Area 1 | R10 Sumbagteng | 10 | BTM509 | BTM509 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0005 | #N/A | BUNGARAYAUJUNG | 103.9994 | 1.1398 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-12-09 | 2026-12-08 |  |  |  |  | Plan ≥ 2026 |  | 06.SITAC | Type-5 | SITAC | SITAC | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
561 | Area 1 | R10 Sumbagteng | 10 | BTM505 | BTM505 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0024 | #N/A | STOLUBUKBAJAASTON | 104.0207 | 1.1424 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-12-21 | 2026-12-20 |  |  |  |  | Plan ≥ 2026 |  | 03.RFI | Type-1 | Need DRM |  | OG | Add 3 RF Add 3 RRU Final Sow Rescope: Type-1 |  | Type-1
562 | Area 1 | R10 Sumbagteng | 10 | BTM790 | BTM790 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0014 | #N/A | STOLUBUKBAJAPERUMVALENCIA | 104.0905 | 1.1223 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-12-21 | 2026-12-20 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS | Type-5 | SIS/SES | SIS | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
563 | Area 1 | R10 Sumbagteng | 10 | PBR537 | PBR537 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0049 | PBR537HW1_SMAN12PEKANBARUTEL | 101.3622 | 0.49066 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT PRASETIA DWIDHARMA |  | Mitratel | 2016-12-21 | 2026-12-20 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 10 RRU Final Sow Rescope: B2R to Mini Macro
564 | Area 1 | R10 Sumbagteng | 10 | PBR396 | PBR396 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0015 | PBR396HW1_JALANDUYUNG2TEL | 101.4347 | 0.48832 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT Rayateh Utama Teladan Canggih |  | Mitratel | 2016-12-31 | 2026-12-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 3 RRU Final Sow Rescope: Type-1 |  | Type-1
565 | Area 1 | R10 Sumbagteng | 10 | PBR543 | PBR543 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0020 | PBR543HW1_MIEACEHAA2TEL | 101.4451 | 0.48085 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT PASIFIK MORA TAMA |  | Mitratel | 2017-01-30 | 2027-01-29 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 7 RRU Final Sow Rescope: Type-1 |  | Type-1
566 | Area 1 | R10 Sumbagteng | 10 | BTM929 | BTM929 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0018 | #N/A | STOBUKITDANGASHARAPANSEKUPANG | 103.9428 | 1.1059 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-03-22 | 2027-03-21 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS | Type-5 | SITAC | SITAC | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
567 | Area 1 | R10 Sumbagteng | 10 | PAD469 | PAD469 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0026 | PAD469HWD_STO_ULAK_KARANG_KANTOR_WALIKOTA_PDG | 100.3556 | -0.92666 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT GLOBAL COMTECH SEJAHTERA |  | Mitratel | 2017-04-05 | 2027-04-04 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 8 RRU Final Sow Rescope: B2R to Mini Macro
568 | Area 1 | R10 Sumbagteng | 10 | BTM924 | BTM924 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0025 | #N/A | SUPRAPTOAJI | 103.9838 | 1.0437 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-04-27 | 2027-04-26 |  |  |  |  | Plan ≥ 2026 |  | 03.RFI | Type-1 | Need DRM |  | OG | Add 3 RF Add 9 RRU Final Sow Rescope: Type-1 |  | Type-1
569 | Area 1 | R10 Sumbagteng | 10 | PAD470 | PAD470 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0028 | PAD470HWD_STO_PADANG_CENTRUM_KELAWI_BARAT_2 | 100.3943 | -0.91805 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT GLOBAL COMTECH SEJAHTERA |  | Mitratel | 2017-05-03 | 2027-05-02 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 9 RRU Final Sow Rescope: B2R to Mini Macro
570 | Area 1 | R10 Sumbagteng | 10 | PBR987 | PBR987 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0012 | PBR987MW1_JLTULIPTEL | 101.4371 | 0.51954 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT KONCERFO SUKSES CEMERLANG |  | Mitratel | 2017-06-26 | 2027-06-25 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
571 | Area 1 | R10 Sumbagteng | 10 | PAD472 | PAD472 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0025 | PAD472HWD_STO_LUBUK_BUAYA_PADANG_SARAI_2 | 100.3153 | -0.80889 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT GLOBAL COMTECH SEJAHTERA |  | Mitratel | 2017-06-26 | 2027-06-25 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
572 | Area 1 | R10 Sumbagteng | 10 | BTM921 | BTM921 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0026 | #N/A | BTM921HWD_STO_SAGULUNG_BATU_AJI_MARINA_3 | 103.9347 | 1.0627 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-07-06 | 2027-07-05 |  |  |  |  | Plan ≥ 2026 |  | 03.RFI | Type-1 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
573 | Area 2 | R03 Jabotabek Inner | 3 | JTX086 | JTX086 | 25TS08N1980 | Jabat | #N/A | #N/A | 25TS08N1980 | #N/A | WIRABAKTICIPINANGDMT | 106.911 | -6.2517 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT SINERGI REKTA DENTA |  | Mitratel | 2015-10-14 | 2025-10-13 | 2026-01-11 | 2026-01-31 | -20 | Out SLA | Plan ≤ 2025 | 08.BAN/BAK | 08.SIS |  | SITAC | BAN/BAK | OG | 4.12 proses negosiasi sewa lahan, nilai 400 jt/5 thn, issue High capex | 2026-02-24 | BTR | GF | Monopole | 36
574 | Area 1 | R10 Sumbagteng | 10 | PAD499 | PAD499 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0048 | PAD499HWD_STO_LUBAY_SC_PAD104W_LESTARI_BUAYA | 100.315 | -0.8197 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT INDOTEKNIK TJANDRA UTAMA |  | Mitratel | 2017-07-31 | 2027-07-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 8 RRU Final Sow Rescope: B2R to Mini Macro
575 | Area 1 | R10 Sumbagteng | 10 | PAD524 | PAD524 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0047 | PAD524HWD_STO_LUBUK_BUAYA_LUBAY_3 | 100.328 | -0.82539 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT INFINITI LAUTAN ARTHA |  | Mitratel | 2017-07-31 | 2027-07-30 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 8 RRU Final Sow Rescope: B2R to Mini Macro
576 | Area 1 | R10 Sumbagteng | 10 | PBR564 | PBR564 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0044 | PBR564ML1_RAYAKUBANGTEL | 101.4301 | 0.41413 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT MITRA SISTEMATIKA GLOBAL |  | Mitratel | 2017-08-04 | 2027-08-03 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 9 RRU Final Sow Rescope: B2R to Mini Macro
577 | Area 1 | R10 Sumbagteng | 10 | PBR573 | PBR573 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0042 | PBR573MW1_PEPUTRA2TEL | 101.4694 | 0.44966 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT TRANSDATA SATKOMINDO |  | Mitratel | 2017-08-04 | 2027-08-03 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
578 | Area 1 | R10 Sumbagteng | 10 | PBR569 | PBR569 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0046 | PBR569MW1_PERUMAHANTAMANRAYARUSSELIATEL | 101.4666 | 0.57085 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT PRASETIA DWIDHARMA |  | Mitratel | 2017-08-09 | 2027-08-08 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
579 | Area 1 | R10 Sumbagteng | 10 | PBR574 | PBR574 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0045 | PBR574MW1_PEMUDACITYWALKTEL | 101.4146 | 0.54386 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT PRASETIA DWIDHARMA |  | Mitratel | 2017-08-11 | 2027-08-10 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
580 | Area 4 | R09 Sulawesi | 9 | UPD760 | UPD760 |  | R09 Sulawesi | #N/A | #N/A | NY | 25TS12Z0004 | BHT_UPD_RATULANGI2 | 119.4163 | -5.1519 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT AJIAN TRI SUKSES |  | Mitratel | 2016-03-21 | 2026-03-20 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG | Add 3 RF Remove 3 RF Add 3 RRU Remove 6 RRU Final Sow Rescope: B2R To MCP
581 | Area 1 | R10 Sumbagteng | 10 | PBR568 | PBR568 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0043 | PBR568MW1_SIDODAIMAHARATUDMT | 101.4294 | 0.4428 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT PRASETIA DWIDHARMA |  | Mitratel | 2017-09-26 | 2027-09-25 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
582 | Area 1 | R10 Sumbagteng | 10 | PBR570 | PBR570 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0041 | CENDANA3DMT | 101.4454 | 0.56405 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT TRANSDATA SATKOMINDO |  | Mitratel | 2017-11-02 | 2027-11-01 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
583 | Area 1 | R10 Sumbagteng | 10 | PAD479 | PAD479 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0027 | PAD479HWD_STO_TELUK_BAYUR_PEGAMBIRAN_4 | 100.3997 | -0.98228 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT GLOBAL COMTECH SEJAHTERA |  | Mitratel | 2018-01-02 | 2028-01-01 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
584 | Area 1 | R10 Sumbagteng | 10 | PAD471 | PAD471 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0053 | PAD471HWD_STO_ULAK_KARANG_LINGGAR_JATI_2 | 100.3391 | -0.86819 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT INDOTEKNIK TJANDRA UTAMA |  | Mitratel | 2018-01-02 | 2028-01-01 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
585 | Area 1 | R10 Sumbagteng | 10 | BTM598 | BTM598 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0012 | #N/A | N_BTM598MDDPTEP | 104.1112 | 1.1349 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2018-02-01 | 2028-01-31 |  |  |  |  | Plan ≥ 2026 |  | 08.SIS | Type-5 | SITAC | SITAC | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
586 | Area 1 | R10 Sumbagteng | 10 | PAD669 | PAD669 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0036 | PAD669HWD_ST_SITEBA_TERMINAL_REGIONAL_BINGKUANG | 100.3868 | -0.87579 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT SANJIWAHANA PERSADA |  | Mitratel | 2018-02-28 | 2028-02-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
587 | Area 1 | R10 Sumbagteng | 10 | PAD475 | PAD475 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0010 | N_PAD475MDDPRUS | 100.3506 | -0.93072 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT LIMA INTI SINERGI |  | Mitratel | 2018-02-28 | 2028-02-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-1 | Need DRM |  | OG | Add 3 RF Add 8 RRU Final Sow Rescope: Type-1 |  | Type-1
588 | Area 1 | R10 Sumbagteng | 10 | PAD458 | PAD458 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0029 | PAD458HWD_STO_PADANG_CENTRUM_AMPANG_INDAH_2 | 100.3842 | -0.92032 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT SANJIWAHANA PERSADA |  | Mitratel | 2018-06-06 | 2028-06-05 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
589 | Area 2 | R03 Jabotabek Inner | 3 | JKB865 | JKB865 |  | Jabat | 0 | #N/A | NY | #N/A | JALANMERUYAUTARADMT | 106.7396 | -6.2002 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-03-17 | 2025-03-16 | 2025-06-14 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A | Reengineering | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
590 | Area 2 | R03 Jabotabek Inner | 3 | JTX476 | JTX476 |  | Jabat | #N/A | #N/A | NY | #N/A | KEMANDORAN7DMT | 106.9367 | -6.2059 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INFRAKO DAYAMITRA | 0 | 0 | Mitratel | 2017-05-05 | 2027-05-04 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | collo | 0 | 0 | 0 | Reloc Ke Tower terdekat DMT (106.9368333 -6.20561115)
591 | Area 2 | R03 Jabotabek Inner | 3 | JSX745 | JSX745 |  |  | #N/A | #N/A | NY | #N/A | PERDATAMTERUSANDMT | 106.7681 | -6.2437 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-06-05 | 2027-06-04 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
592 | Area 1 | R10 Sumbagteng | 10 | PAD659 | PAD659 | 25TS05Z0004 | R10 Sumbagteng | #N/A | #N/A | 25TS05Z0004 | #N/A | PAD659HWD_STO_PADANG_HOTEL_AXANA | 100.359 | -0.9539 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-07-22 | 2025-07-21 | 2025-10-19 | 2026-01-31 | -104 | Out SLA | Plan ≤ 2025 | #N/A | 11.Hold | Type-5 | RFC | RFC | OG | 4.12 Proposed ke Type 1 dari type 5 [30/10/25] Hold , Outstanding ELD [20/10/25] Ban/bak lahan pemko [19/09/25] [08/08/25] rehunting dengan pemko, arahan TSEL, krn lokasi mendekati existing [28/07/2025] rehunting, lokasi kandidat terlampau dekat dengan eksisting, reject by RTPE |  | Type-5 =>Type-1
593 | Area 2 | R03 Jabotabek Inner | 3 | JSX535 | JSX535 |  | Jabat | #N/A | #N/A | NY | 25TS12B0051 | PEMUKIMANPASARMINGGUDMT | 106.8421 | -6.2924 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT SUMBERSOLUSINDO HITECH | PT AGUNGMAS PRIMA SEMPURNA | 0 | Mitratel | 2017-06-05 | 2027-06-04 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | B2S | 0 | 0 | 0 | 150m arah 330 degree
594 | Area 2 | R03 Jabotabek Inner | 3 | JBX211 | JBX211 |  |  | #N/A | #N/A | NY | #N/A | JLKUMBANGRAYADMT | 106.697 | -6.1411 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-06-13 | 2027-06-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
595 | Area 1 | R10 Sumbagteng | 10 | BTM928 | BTM928 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0017 | #N/A | TIBANKOPERASISTOBUKITDANGAS | 103.9648 | 1.1053 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-04-03 | 2027-04-02 |  |  |  |  | Plan ≥ 2026 |  | 06.SITAC | Type-5 | SITAC | SITAC | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
596 | Area 2 | R12 Jabotabek Outer | 12 | BOO471 | BOO471 |  | Eastern Jabodetabek | 0 | #N/A | NY | #N/A | PASADENADMT | 106.8844 | -6.5835 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-01-08 | 2025-01-07 | 2025-04-07 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A | Reengineering | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
597 | Area 2 | R12 Jabotabek Outer | 12 | BOO472 | BOO472 | #N/A | Eastern Jabodetabek | 0 | #N/A | NY | #N/A | KEDATONDMT | 106.8929 | -6.59 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-01-08 | 2025-01-07 | 2025-04-07 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A | Reengineering | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
598 | Area 2 | R12 Jabotabek Outer | 12 | BOO783 | BOO783 | 25TS08N0746 | Eastern Jabodetabek | 0 | #N/A | 25TS08N0746 | #N/A | BEVERLYDMT | 106.8928 | -6.5823 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-01-12 | 2025-01-11 | 2025-04-11 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A | Reengineering | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
599 | Area 2 | R03 Jabotabek Inner | 3 | JTX314 | JTX314 |  | Jabat | #N/A | #N/A | NY | 25TS12B0045 | ELANGMALINDOMKSDMT | 106.9086 | -6.2524 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT DYEVA DIGITAL SELULAR | PT DYEVA DIGITAL SELULAR | 1 | Mitratel | 2017-06-14 | 2027-06-13 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | B2S | 0 | 0 | 0 | BTR
600 | Area 1 | R10 Sumbagteng | 10 | PAP223 | PAP223 |  | R10 Sumbagteng | #N/A | #N/A | NY | #N/A | PAP223GDLEAN1 | 100.3383 | -0.48423 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-07-28 | 2027-07-27 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-1 | Need DRM |  | OG | Add 3 RF Add 6 RRU Final Sow Rescope: Type-1 |  | Type-1
601 | Area 1 | R10 Sumbagteng | 10 | PBR418 | PBR418 |  | R10 Sumbagteng | 0 | #N/A | NY | #N/A | PBR418HL1_JALANHASANUDINDMT | 101.4565 | 0.53385 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-07-13 | 2025-07-12 | 2025-10-10 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
602 | Area 1 | R10 Sumbagteng | 10 | BTM862 | BTM862 |  | R10 Sumbagteng | 0 | #N/A | NY | #N/A | BUKITDANGASKOMPLEKRUKOSEIHARAPAN | 103.9527 | 1.1101 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-07-27 | 2025-07-26 | 2025-10-24 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
603 | Area 2 | R03 Jabotabek Inner | 3 | JTX412 | JTX412 |  |  | #N/A | #N/A | NY | #N/A | CIBUBURRAYADMT | 106.8692 | -6.3423 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-12-04 | 2027-12-03 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
604 | Area 1 | R10 Sumbagteng | 10 | BTM839 | BTM839 |  | R10 Sumbagteng | 0 | #N/A | NY | #N/A | BTM839HWD_STO_SAGULUNG_SAGUBA | 103.9492 | 1.0388 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-11 | 2025-09-10 | 2025-12-09 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
605 | Area 1 | R10 Sumbagteng | 10 | PBR989 | PBR989 |  | R10 Sumbagteng | 0 | #N/A | NY | #N/A | PBR989HL1_JALANRAYAPEKANBARU8DMT | 101.3858 | 0.46204 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-09-12 | 2025-09-11 | 2025-12-10 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
606 | Area 2 | R12 Jabotabek Outer | 12 | KRW819 | KRW819 |  | Eastern Jabodetabek | 0 | #N/A | NY | #N/A | KIIC15DMT | 107.2942 | -6.3794 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-06-28 | 2025-06-27 | 2025-09-25 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
607 | Area 2 | R03 Jabotabek Inner | 3 | JBX385 | JBX385 | #N/A | Jabat | #N/A | #N/A | NY | 25TS12B0027 | ANGKETAMBORADMT | 106.8082 | -6.1582 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT NAER TUNAS INDONESIA | PT NAER TUNAS INDONESIA | 1 | Mitratel | 2018-06-04 | 2028-06-03 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | BTR Arah 50m 180 Degree
608 | Area 2 | R03 Jabotabek Inner | 3 | JBX405 | JBX405 |  | Jabat | #N/A | #N/A | NY | 25TS12B0061 | JLRAYAPREPEDANDMT | 106.7067 | -6.1154 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | PT INTERTEL MEDIA PRIMA | PT INTERTEL MEDIA PRIMA | 1 | Mitratel | 2018-08-03 | 2028-08-02 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | BTR | 0 | 0 | 0 | 225' 250m
609 | Area 1 | R10 Sumbagteng | 10 | BTM863 | BTM863 |  | R10 Sumbagteng | 0 | #N/A | NY | #N/A | PELABUHANINTERNASIONALSEKUPANG | 103.9257 | 1.1259 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-09 | 2025-10-08 | 2026-01-06 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
610 | Area 2 | R03 Jabotabek Inner | 3 | JTX490 | JTX490 |  |  | #N/A | #N/A | NY | #N/A | KOMPANGGREKLOKADMT | 106.8991 | -6.3456 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2018-08-17 | 2028-08-16 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
611 | Area 1 | R10 Sumbagteng | 10 | BTM841 | BTM841 |  | R10 Sumbagteng | 0 | #N/A | NY | #N/A | STOLUBUKBAJAIBNUSINA | 104.0166 | 1.1448 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-13 | 2025-10-12 | 2026-01-10 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
612 | Area 2 | R03 Jabotabek Inner | 3 | JTX491 | JTX491 |  |  | #N/A | #N/A | NY | #N/A | PAMITRANCIJANTUNGDMT | 106.8571 | -6.3217 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2018-08-20 | 2028-08-19 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG |  |  |  | #N/A | #N/A | #N/A
613 | Area 2 | R12 Jabotabek Outer | 12 | BOO782 | BOO782 |  | Eastern Jabodetabek | 0 | #N/A | NY | #N/A | BALIHILDMT | 106.889 | -6.5872 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2014-07-29 | 2024-07-28 | 2024-10-26 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A | Reengineering | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
614 | Area 2 | R12 Jabotabek Outer | 12 |  | BOO784 | #N/A | Eastern Jabodetabek | 0 | #N/A | NY | #N/A | PARAHYANGAN | 107.6239 | -6.9225 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2012-08-14 | 2022-08-13 | 2022-11-11 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A | Reengineering | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
615 | Area 2 | R12 Jabotabek Outer | 12 | BOO470 | BOO470 | #N/A | Eastern Jabodetabek | 0 | #N/A | NY | #N/A | HELIPEDPLANNED2013 | #N/A | #N/A | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-08-14 | 2023-08-13 | 2023-11-11 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A | Reengineering | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
616 | Area 2 | R12 Jabotabek Outer | 12 | BOO837 | BOO837 |  | Eastern Jabodetabek | 0 | #N/A | NY | #N/A | HELIPADNORTHBRIDGEDMT | 106.877 | -6.5821 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2013-08-14 | 2023-08-13 | 2023-11-11 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A | Reengineering | Terminate | Terminate | Terminate |  | Terminate |  | #N/A | #N/A | #N/A
617 | Area 1 | R10 Sumbagteng | 10 | BTM517 | BTM517 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0008 | #N/A | BTM517HWD_JEMBATAN_BARELANG_2 | 104.0366 | 0.98303 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-08-14 | 2027-08-13 |  |  |  |  | Plan ≥ 2026 |  | 06.SITAC | Type-5 | SIS/SES | SIS | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
618 | Area 1 | R10 Sumbagteng | 10 | PAD674 | PAD674 |  | R10 Sumbagteng | #N/A | #N/A | NY | 25TS12Z0037 | STOPACENTRUMANDURINGEXSITEBA3 | 100.3882 | -0.93482 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT INFINITI LAUTAN ARTHA |  | Mitratel | 2016-10-07 | 2026-10-06 |  |  |  |  | Plan ≥ 2026 |  | #N/A | Type-5 | Need DRM |  | OG | Add 3 RF Add 3 RRU Final Sow Rescope: B2R to Mini Macro
619 | Area 1 | R10 Sumbagteng | 10 | PBR439 | PBR439 |  | R10 Sumbagteng | 0 | #N/A | NY | #N/A | PBR439HL1_SUKAKARYA2DMT | 101.3842 | 0.43724 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-13 | 2025-10-12 | 2026-01-10 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
620 | Area 1 | R10 Sumbagteng | 10 | BTM787 | BTM787 |  | R10 Sumbagteng | #N/A | #N/A | NY | #N/A | BTM787HWD_STO_BATAM_CENTER_MY_MART | 104.0471 | 1.1297 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-08 | 2026-07-07 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
621 | Area 2 | R03 Jabotabek Inner | 3 | JSX469 | JSX469 |  |  | #N/A | #N/A | NY | #N/A | TEBETBARATBUKITDURIDMT | 106.8654 | -6.2212 | Non MKT | Non MKT | #N/A |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-06-07 | 2027-06-06 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM | Need DRM | OG | #N/A |  |  | #N/A | #N/A | #N/A
622 | Area 1 | R10 Sumbagteng | 10 | BTM518 | BTM518 |  | R10 Sumbagteng | #N/A | #N/A | NY | #N/A | STOLUBUKBAJAJODOHAREA | 104.0094 | 1.1601 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-12-02 | 2026-12-01 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
623 | Area 1 | R10 Sumbagteng | 10 | PBR541 | PBR541 |  | R10 Sumbagteng | #N/A | #N/A | NY | #N/A | N_PBR541HL1_WATERBOOMLABERSATEL | 101.4773 | 0.4476 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-12-12 | 2026-12-11 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
624 | Area 4 | R09 Sulawesi | 9 | UPD762 | UPD762 | 24TS01B0625 | R09 Sulawesi | 0 | 24TS01B0625 | 24TS01B0625 | #N/A | BHT_UPD_RATULANGI4 | 119.4187 | -5.1647 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-26 | 2025-10-25 | 2026-01-23 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | 11.Hold |  | Terminate | Terminate | Terminate |  | Terminate
625 | Area 1 | R10 Sumbagteng | 10 | BTM608 | BTM608 |  | R10 Sumbagteng | #N/A | #N/A | 25TS09Z0013 | #N/A | STOSAGULUNGPERUMAVIARI | 103.9588 | 1.0499 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-07-08 | 2026-07-07 |  |  |  |  | Plan ≥ 2026 |  | 06.SITAC | Type-5 | SITAC | SITAC | OG | Add 3 RF Add 6 RRU Final Sow Rescope: B2R to Mini Macro
626 | Area 1 | R10 Sumbagteng | 10 | BTM926 | BTM926 |  | R10 Sumbagteng | #N/A | #N/A | NY | #N/A | YANINIAGA | 104.0367 | 1.0996 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-06-13 | 2027-06-12 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
627 | Area 2 | R04 Jawa Barat | 4 | BDK533 | BDK533 |  | R04 Jawa Barat | 0 | #N/A | NY | #N/A | KEBONTERONG | 107.7169 | -6.9342 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-08-22 | 2025-08-21 | 2025-11-19 | Terminate |  | Terminate | Plan ≤ 2025 | #N/A | #N/A |  | Terminate | Terminate | Terminate |  | Terminate
628 | Area 1 | R10 Sumbagteng | 10 | PAD523 | PAD523 |  | R10 Sumbagteng | #N/A | #N/A | NY | #N/A | PAD523HWD_STO_LUBUK_BUAYA_SAPEK_RAYA | 100.3304 | -0.83753 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-12-27 | 2027-12-26 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
629 | Area 2 | R12 Jabotabek Outer | 12 | KRW831 | KRW831 | 25TS01B0008 | Eastern Jabodetabek |  | 25TS01B0008 | 25TS01B0008 | #N/A | KIM9DMT | 107.3083 | -6.3859 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | PT. Samanta Fibra Abadi |  | Mitratel | 2015-06-22 | 2025-06-21 | 2025-09-19 | 2026-01-31 | -134 | Out SLA | Plan ≤ 2025 | #N/A | 06.SITAC |  | SITAC | BAN/BAK | OG | 4.12. plan macronisasi di site existing, upgrade perangkat (swap) type 1, per tahun per pole 300 Juta, need special price | 2026-02-24 |  | GF | SST | 42
630 | Area 2 | R12 Jabotabek Outer | 12 | KRW185 | KRW185 | 25TS01B0001 | Eastern Jabodetabek | #N/A | #N/A | 25TS01B0001 | #N/A | KIS4DMT | 107.3328 | -6.4067 | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 |  | MITRATEL | #N/A | PT AGUNGMAS PRIMA SEMPURNA |  | Mitratel | 2016-11-10 | 2026-11-09 |  |  |  |  | Plan ≥ 2026 |  | 06.SITAC |  | SITAC | BAN/BAK | OG | Add 3 RF Add 6 RRU Final Sow Rescope: BTR to Macro |  |  | GF | SST | 42
631 | Area 3 | R06 Jawa Timur | 6 | MLG083 | MLG083 | 24TS08N0294 | R06 Jawa Timur | #N/A | #N/A | 24TS08N0294 | #N/A | GLASSHOUSEUBMCP | 112.6128 | -7.9517 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-07 | 2025-10-06 | 2026-01-04 | 2025-12-31 | 4 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | SIS/SES | DRM | OG | UB Request Fasilitas Kampus (CSR), harus menyewa lahan yang didirikan bangunan fasum yang diatasnya dirikan tower | Hold
632 | Area 3 | R06 Jawa Timur | 6 | MLG085 | MLG085 | 24TS08N0297 | R06 Jawa Timur | #N/A | #N/A | 24TS08N0297 | #N/A | FAKULTASTEKNIKUBMCP | 112.6135 | -7.9498 | Non MKT | Non MKT |  |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2015-10-07 | 2025-10-06 | 2026-01-04 | 2025-12-31 | 4 | In SLA | Plan ≤ 2025 | #N/A | #N/A |  | SIS/SES | DRM | OG | UB Request Fasilitas Kampus (CSR), harus menyewa lahan yang didirikan bangunan fasum yang diatasnya dirikan tower | Hold
633 | Area 3 | R06 Jawa Timur | 6 | MLG940 | MLG940 |  | R06 Jawa Timur | #N/A | #N/A | NY | #N/A | MAHADPUTRAUINMCP | 112.6079 | -7.9504 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2016-09-09 | 2026-09-08 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
634 | Area 3 | R06 Jawa Timur | 6 | MLG960 | MLG960 |  | R06 Jawa Timur | #N/A | #N/A | NY | #N/A | GERLAKANGUB2HBTSDMT | 112.6152 | -7.9554 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-01-17 | 2027-01-16 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
635 | Area 3 | R06 Jawa Timur | 6 | MLG964 | MLG964 |  | R06 Jawa Timur | #N/A | #N/A | NY | #N/A | REKTORATUB2HBTSDMT | 112.6135 | -7.9526 | Non MKT | Non MKT | 0 |  | MITRATEL | #N/A | #N/A |  | Mitratel | 2017-01-17 | 2027-01-16 |  |  |  |  | Plan ≥ 2026 |  | #N/A |  | Need DRM |  | OG
Formulas:
ELD+3 Bulan = [ELD Update]+90

## PVTT
EOC | (All)
SoW Actual | BTSH
Column Labels
Row Labels | 1. SIS/SES | 2. SITAC | 3. RFC | 4. CME | 5. RFI | 6. PROPOSE DROP | 7. DROP | 8. Lock Trial | 2. PROPOSE DROP 1. SIS/SES | Grand Total
0004/MKT/DMT/XI/2025
Non MKT
Grand Total
#VALUE!
Status MKT | Non MKT
EOC | Plan ≤ 2025
SoW Actual | BTSH
Regional | (All)
SOW TENANT | (Multiple Items)
MILESTONE
Mitra Pleno MK | Mitra Pleno MKT | 1. SIS/SES | 2. SITAC | 3. RFC | 4. CME | 5. RFI | 6. PROPOSE DROP | 7. DROP | 8. Lock Trial | 2. PROPOSE DROP 1. SIS/SES | Grand Total
KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | PT AGUNGMAS PRIMA SEMPURNA
PT CIPTA KARSA ANUGERAH SEMESTA
PT JAGANATA SAKTI UNGGUL
PT MITRA SARANA KARYA BANGSA
PT SAMANTA FIBRA ABADI
PT SINERGI REKTA DENTA
PT SUMBERSOLUSINDO HITECH
KOPERASI JASA DAYAMITRA TELEKOMUNIKASI Total
PT ATRYA REKAYASA | PT AJIAN TRI SUKSES
PT ANUGERAH SELARAS RAYA
PT DENTRA MITRA ABADI
PT DYEVA DIGITAL SELULAR
PT NAER TUNAS INDONESIA
PT ATRYA REKAYASA Total
PT MULTI BMITRA SEJAHTERA | PT SUMBERSOLUSINDO HITECH
PT MULTI BMITRA SEJAHTERA Total
PT TRITECH CONSULT | PT GEAF SOLUSIANDA PRATAMA
PT INFRAKO DAYAMITRA
PT SAMANTA FIBRA ABADI
PT SINERGI REKTA DENTA
PT TRITECH CONSULT Total
Waspang | PT DENTRA MITRA ABADI
PT GEAF SOLUSIANDA PRATAMA
PT INFRAKO DAYAMITRA
PT SUMBERSOLUSINDO HITECH
Waspang Total
Grand Total
Status MKT | (All)
EOC | Plan ≥ 2026
SoW Actual | BTSH
Regional | (All)
SOW TENANT | (Multiple Items)
MILESTONE
Mitra Pleno MK | Mitra Pleno MKT | 1. SIS/SES | 2. SITAC | 3. RFC | 4. CME | 5. RFI | 6. PROPOSE DROP | 7. DROP | 8. Lock Trial | Grand Total
KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | PT AGUNGMAS PRIMA SEMPURNA
PT SAMANTA FIBRA ABADI
PT SINERGI REKTA DENTA
KOPERASI JASA DAYAMITRA TELEKOMUNIKASI Total
PT MULTI BMITRA SEJAHTERA | CV LUXLO KARYA GEMILANG
PT CIPTA KARSA ANUGERAH SEMESTA
PT DENTRA MITRA ABADI
PT DESATRIA ALARD MANDIRI
PT DYEVA DIGITAL SELULAR
PT INDOJAR MULIA ABADI
PT LAYTON ENTER PRISE
PT MANDAU JAYA KONTRINDO
PT MITRA SARANA KARYA BANGSA
PT MULTI BAGASANTI MAHDY
PT SAMANTA FIBRA ABADI
PT SUMBERSOLUSINDO HITECH
PT MULTI BMITRA SEJAHTERA Total
PT TRITECH CONSULT | PT AGUNGMAS PRIMA SEMPURNA
PT AJIAN TRI SUKSES
PT ANUGERAH SELARAS RAYA
PT CELEBES KONTRUKSINDO
PT DENTRA MITRA ABADI
PT GEAF SOLUSIANDA PRATAMA
PT INFRAKO DAYAMITRA
PT INTERTEL MEDIA PRIMA
PT JAGANATA SAKTI UNGGUL
PT MULTI BAGASANTI MAHDY
PT NAER TUNAS INDONESIA
PT SAMANTA FIBRA ABADI
PT SINERGI REKTA DENTA
PT SUMBERSOLUSINDO HITECH
PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS
PT TRIPUTRA SURYA SEJAHTERA
PT VALUE TELECOMMUNICATION
PT TRITECH CONSULT Total
WO PROSES | WO PROSES
WO PROSES Total
Waspang | PT SINERGI REKTA DENTA
Waspang Total
PT TUNAS GEOTEKNIK INDONESIA | PT SINERGI REKTA DENTA
PT TUNAS GEOTEKNIK INDONESIA Total
Grand Total

## JABODETABEB RESCOPING ALL 309
|  | 3 | 3 |  |  | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 2 | 2 | 1 | 3 | 3 | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
NO | AREA | SITE ID BARU | Regional | Status WO Project | Status MKT | MKT | Tanggal MKT | SoW Actual | PID | SITE ID BARU | Name Site | EOC | SOW TENANT | Remarks | MILESTONE | General Status | Detail Progress | Not Optimis/ Optimis | Target RFI | General Status | Target Mitra | FORCAST | Mitra Pleno MKT | Mitra Pleno MK | UPDATE DRM BTSH (CRM) | Arahan NBAE | Long (Eksisting) | Lat (Eksisting) | Alamat (Eksisting) | Long (New) | Lat (New) | Alamat (New) | Tower Eksisting | Lahan Eksisting | Tipe Tower (New) | PROGRAM UPDATE | Luas Lahan | Harga Lahan (Total) | Remarks | Tower | Jenis Tower | Panjang Lahan | Lebar Lahan | Total Lahan | DRM EXTEND | STATUS UPDATE PROGRAM 04/03/2026
240 | Area 2 | JTX207 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0129 | JTX207 | JLMAKASARJAKTIMDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Rehunting | 08.04 : Hard Cand Hard SITAC (Not Optimis) 13.01 : Keluarga LL Menolak Untuk Extend (Alasan Keamanan), OG Hunting SAR 200m 1.19.12 (LL Meminta Kompensasi / waiting nilai kompensasi) | Not Optimis | 2026-01-29 | Add 3 RF Add 11 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | CV LUXLO KARYA GEMILANG | PT MULTI BMITRA SEJAHTERA | BTR | Continue Renewal Eksisting (perizinan Bandara) | 106.8774 | -6.2691 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 3m | Adit | 082123012385 |  | Tubular | Flange Luar | 1.5 | 1.5 | 3 |  | BTR
219 | Area 2 | JTX215 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0127 | JTX215 | ARABIKA8DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Proposed Drop | Proposed Drop 08.04 : Need Validasi Cand B (-6.22855 ; 106.94360) 13.01 Validasi NOK, Rehunting 22.12 Need Validasi Cand : 22/12/2025 (Cand A -6.23006 ;106.94315) 19.12 (LL Tidak Menginginkan Extend 3m Issue Tower eksisting) >> Rehunting Extend | Optimis | 2026-01-29 | Add 3 RF Add 6 RRU Final Sow Rescope: 3. reheight tower | 2026-05-25 | Mei | CV LUXLO KARYA GEMILANG | PT MULTI BMITRA SEJAHTERA | Extend Pole | Extend 3m | 106.9437 | -6.2291 |  |  |  |  | Monopole 20 1Leg | Privat |  | Extend 6m | Adit | 082123012385 | Lahan Tidak Cukup Untuk Extend | Tubular | Flange Dalam | 3 | 3 | 6 | Extend 6m | Extend 6m
242 | Area 2 | JKT417 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0030 | JKT417 | MASJIDANNURBUARANDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 7. DROP | Justifikasi Report | 07/01: Area proposed penolakan warga satu RW, 25.02 : proposed extend | Not Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT CIPTA KARSA ANUGERAH SEMESTA | PT MULTI BMITRA SEJAHTERA | BTR | 100m arah Selatan | 106.9211 | -6.2189 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Terminate |  |  |  | Tubular | Flange Luar | 1.5 | 1.5 | 3 | HOLD By Tsel (Propose DROP) | HOLD By Tsel (Propose DROP)
164 | Area 2 | JTX041 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0091 | JTX041 | INSPEKSIKAYUTINGGIDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Rehunting | 21.01 : Candidat A NOK 19.01 : Need Validasi Cand A (-6.18075 ; 106.94456) 07/01: Hunting OG, plan submit datek 09/01 25.02: | Not Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT CIPTA KARSA ANUGERAH SEMESTA | PT MULTI BMITRA SEJAHTERA | BTR | Arah 250m 350 degree | 106.9445 | -6.1808 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR |  |  |  | Tubular | Flange Luar | 3 | 3 | 6 |  | BTR
163 | Area 2 | JTX084 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0087 | JTX084 | KAVALERICIPINANGDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW | 08.04 : Extend 6 m, IW OG 6 KK (Plan Done 13/04) 07/01: kawasan proposed adalah area Perumahan KODAM3 perlu Surat pengajuan ke KODAM3, plan extend PKS 1. 18.12 Padat Penduduk Space lahan tidak ada HARD CANDIDAT 25.02: OG PKS | Optimis | 2026-03-20 | Add 3 RF Add 4 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-10 | Mei | PT CIPTA KARSA ANUGERAH SEMESTA | PT MULTI BMITRA SEJAHTERA | Extend 6m | 150m utara | 106.9153 | -6.2491 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 6m |  |  |  | Tubular | Flange Luar | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
241 | Area 2 | JTX206 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0047 | JTX206 | JLMUSACIPINANGMUARADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 08.04 : BAN/BAK Waiting Aproval HQ (Harga 40jt/Tahun) 19.02 : Extend 6 m Not Posibble, Cand BTR Wait Validasi(-6.22355 ; 106.88942) 21.01 : Validasi OK CAN A 19.01 : Need Validasi Cand A (-6.22354 ; 106.88919) 07/01: area prooposed hard candidat kawasan elit 1. 18.12 KOMPLEK ELITE HARD CANDIDAT 25.02 : proses submit harga sewa lahan | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-29 | Mei | PT CIPTA KARSA ANUGERAH SEMESTA | PT MULTI BMITRA SEJAHTERA | BTR | 150m arah 270 degree | 106.8893 | -6.2238 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR |  |  |  | Tubular | Flange Luar | 1.5 | 1.5 | 3 |  | BTR
615 | Area 2 | BOO470 | Eastern Jabodetabek |  | Non MKT | Non MKT |  | BTSH | NY | BOO470 | HELIPEDPLANNED2013 | Plan ≤ 2025 | BTS HOTEL |  | 7. DROP | Drop | 7. DROP | Not Optimis | Drop | Propose Drop Terminate |  |  | NY | NY | Terminate |  | #N/A | #N/A |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Terminate
596 | Area 2 | BOO471 | Eastern Jabodetabek |  | Non MKT | Non MKT |  | BTSH | NY | BOO471 | PASADENADMT | Plan ≤ 2025 | BTS HOTEL |  | 7. DROP | Drop | 7. DROP | Not Optimis | Drop | Propose Drop Terminate |  |  | NY | NY | Terminate |  | 106.8844 | -6.5835 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Terminate
597 | Area 2 | BOO472 | Eastern Jabodetabek |  | Non MKT | Non MKT |  | BTSH | NY | BOO472 | KEDATONDMT | Plan ≤ 2025 | BTS HOTEL |  | 7. DROP | Drop | 7. DROP | Not Optimis | Drop | Propose Drop Terminate |  |  | NY | NY | Terminate |  | 106.8929 | -6.59 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Terminate
360 | Area 2 | JTX341 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0102 | JTX341 | TMII9DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | Site Opening | 08.04 : Menunggu APD Rilis 10/04 19.02 : Validasi Cand A OK, BAN/BAK OG 19.01 : Need Validasi Cand A (-6,30392 ; 106,89010) 24.12 Menunggu Perizinan Lahan Cand (Plan 07/01) 25.02 : Proses IW | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-22 | Mei | PT CIPTA KARSA ANUGERAH SEMESTA | PT MULTI BMITRA SEJAHTERA | BTR |  | 106.8901 | -6.3039 |  |  |  |  | Monopole 20 1Leg | Fasum TMII |  | BTR |  |  | Lahan Tidak Cukup Untuk Extend | Tubular | Flange Luar | 1.5 | 1.5 | 3 |  | BTR
376 | Area 2 | BOO570 | Eastern Jabodetabek | In Hand | Non MKT | Non MKT |  | BTSH | WO OG | BOO570 | IPBDARMAGAREKTORAT | Plan ≤ 2025 | IBS To Macro |  | 2. SITAC | BAN/BAK | 27/04/26 : Plan Kamis-Jum'at eksekusi perangkat Waiting Permit IPB | Optimis | 2026-01-07 | 12.12 plan jovis dengan pihak universitas, proses BAN/BAK ke pihak IPB | W1 2026 |  | PT DENTRA MITRA ABADI | PT MULTI BMITRA SEJAHTERA | IBS To Macro |  | 106.7226 | -6.5566 |  |  |  |  | Pole 3 1Leg |  |  | IBS | [9 empty] | IBS
613 | Area 2 | BOO782 | Eastern Jabodetabek |  | Non MKT | Non MKT |  | BTSH | NY | BOO782 | BALIHILDMT | Plan ≤ 2025 | BTS HOTEL |  | 7. DROP | Drop | 7. DROP | Not Optimis | Drop | Propose Drop Terminate |  |  | NY | NY | Terminate |  | 106.889 | -6.5872 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Terminate
598 | Area 2 | BOO783 | Eastern Jabodetabek | In Hand | Non MKT | Non MKT |  | BTSH | 25TS08N0746 | BOO783 | BEVERLYDMT | Plan ≤ 2025 | BTS HOTEL |  | 7. DROP | Drop | 7. DROP | Not Optimis | Drop | Propose Drop Terminate |  |  | NY | NY | Terminate |  | 106.8928 | -6.5823 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Terminate
614 | Area 2 | BOO784 | Eastern Jabodetabek |  | Non MKT | Non MKT |  | BTSH | NY | BOO784 | PARAHYANGAN | Plan ≤ 2025 | BTS HOTEL |  | 7. DROP | Drop | 7. DROP | Not Optimis | Drop | Propose Drop Terminate |  |  | NY | NY | Terminate |  | 107.6239 | -6.9225 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Terminate
616 | Area 2 | BOO837 | Eastern Jabodetabek |  | Non MKT | Non MKT |  | BTSH | NY | BOO837 | HELIPADNORTHBRIDGEDMT | Plan ≤ 2025 | BTS HOTEL |  | 7. DROP | Drop | 7. DROP | Not Optimis | Drop | Propose Drop Terminate |  |  | NY | NY | Terminate |  | 106.877 | -6.5821 |  |  |  |  | Monopole 12 1Leg |  |  | Terminate | [9 empty] | Terminate
366 | Area 2 | CPT251 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 25TS09Z0031 | CPT251 | TERATAIPUTIHDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Validasi OG | 22/04/26 : Need validasi cand S 16/04/26 : Need validasi cand S 08/04/26 : Need validasi cand S 01/04/26 : Need validasi Cand Q (Lat : -6.27869 Long : 106.75505) 16/03/26 : Need validasi U/F (Lat : -6.27869 Long : 106.75505) 25/02/26 : plan submit datek 25/2/26, paralel proposed extend 6m site eksisting 3. 28/1/26 : Proposed drop 2. 07.01.26 : Validasi NOK , Rehunting new Cand 1. 16.12.25 Submit Datek | Not Optimis |  | 12.12 gagal IW rehunting 10.12 IW OG | DROP |  | PT GEAF SOLUSIANDA PRATAMA | PT TRITECH CONSULT | BTR |  | 106.7561 | -6.2775 |  |  |  |  | Monopole 20 1Leg |  | mp 32 | Terminate | 4x4 | [7 empty] | Extend 3m OG | Extend 3m
384 | Area 2 | BOO572 | Eastern Jabodetabek | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS09Z0035 | BOO572 | IPBDRAMAGAFAKPERTANIAN | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 4. CME | Fabrikasi OG | 16/03/2026 : Pabrikasi Mounting, Upgrade PLN | Optimis | 2026-03-20 | Add 3 RF Add 13 RRU Final Sow Rescope: reheight tower |  | Apr | PT DENTRA MITRA ABADI | PT MULTI BMITRA SEJAHTERA | BTR |  | 106.7313 | -6.5569 |  |  |  |  | Pole 3 1Leg |  |  | Contine with Macro | [9 empty] | Contine with Macro
139 | Area 2 | JBX008 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0414 | JBX008 | JALANHDAUDDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 4. CME | Pabrikasi | 21/04/26 : Tim aset DMT akan ke lokasi, plen extend 6m PABRIKASI POLE 3 METER | Optimis | 2026-01-29 | 10.12 plan extend 3m 4.12 LL berubah pikiran tidak bersedia di extend | W2 2026 | Mar | PT JAGANATA SAKTI UNGGUL | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Extend Pole |  | 106.7758 | -6.2052 |  |  |  |  | Monopole 20 1Leg |  |  | Extend 3m |  | 722222222 | [6 empty] | Extend 3m OG | Extend 3m
124 | Area 2 | JBX016 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0424 | JBX016 | GLOBALNUSANTARASCHOOLDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI Notice | PABRIKASI POLE 3 METER | Optimis | 2026-01-29 | 12.12 proses pabrikasi, target done material 26 Dec, Target RFI 10 Jan 10.12 pabrikasi OG | W2 2026 | Mar | PT JAGANATA SAKTI UNGGUL | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Extend Pole |  | 106.739 | -6.1919 |  |  |  |  | Monopole 18 1Leg |  |  | Extend 3m | [8 empty] | Extend 3m OG | Extend 3m
123 | Area 2 | JBX021 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0454 | JBX021 | KEMBANGANBARUDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | Lock Trial | HARD CANDIDAT Propose DROP | Not Optimis | 2026-02-13 | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial |  |  | PT JAGANATA SAKTI UNGGUL | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Lock Trial |  | 106.7501 | -6.1804 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
336 | Area 2 | JBX034 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 25TS09B0009 | JBX034 | TAMANKEDOYABARUDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 9. Propose Drop | Re-survey | 22/04/26 : DMT meminta mitra possibility 3 m 08/04/26 : DMT minta mitra possibility extend 3m 01/04/26 : Drop 16/03/26 : Drop by Tsel 04/03/26 : Rehunting, minta arahan dari DMT 25/02/26: Rehunting issue hard candidat paralel pembuatan JR, paralel proposed extend 6M site eksisting 13/02/26 : Validasi NOK Cand D (near existing) 22/01/26 : Waiting Approval Kand ( -6.1829 106.76524) dan C (-6.18678 106.76014) HARD SITAC ISSUE,PROPOSE RETURN | NOT Optimis | 2026-03-20 | 12.12 mash hunting 4.12 hard kandidat, Hard Sitac, plan BTR gagal IW, hunting kandidat ke 4 | Survey : 10/4/26 REASSESMENT | Apr | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | BTR |  | 106.7615 | -6.1853 |  |  |  |  | Monopole 18 1Leg |  |  | Extend 3m |  |  | trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 3m OG | Extend 3m
122 | Area 2 | JBX042 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0425 | JBX042 | PRISMARAYADMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 9. Propose Drop | BAN/BAK OG | 10/3/26: Plan Penjajakan extend 6m lahan eksisting(fasum kompleks), high price HARD SITAC ISSUE,PROPOSE RETURN | Optimis | 2026-01-29 | 4.12 hard kandidat, Hard Sitac, lahan pemda tdk ada ijin, existing 20m extend to 3m | REASSESMENT | Apr | PT JAGANATA SAKTI UNGGUL | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Extend Pole |  | 106.7584 | -6.1938 |  |  |  |  | Monopole 20 1Leg |  |  | Extend 6m | [8 empty] | Extend 6m | Extend 6m
115 | Area 2 | JBX052 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0427 | JBX052 | KOMPLEKMIGASDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | Lock Trial | HARD CANDIDAT Propose DROP | Not Optimis | 2026-02-14 | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial |  |  | PT JAGANATA SAKTI UNGGUL | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Lock Trial |  | 106.7695 | -6.2027 |  |  |  |  | Monopole 18 1Leg |  |  | BTR | [9 empty] | Lock Trial
131 | Area 2 | JBX060 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0419 | JBX060 | ARTABOGAPALMERAHDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 9. Propose Drop | Justifikasi Report | HARD SITAC ISSUE,PROPOSE RETURN | Optimis | 2026-03-20 | REASSESMENT | REASSESMENT |  | PT JAGANATA SAKTI UNGGUL | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 106.7907 | -6.204 |  |  |  |  | Monopole 20 1Leg |  |  | Extend 3m | [8 empty] | Extend 3m OG | Extend 3m
42 | Area 2 | JBX077 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 25TS08N2053 | JBX077 | PURIBETAUTARA | Plan ≤ 2025 | BTS HOTEL |  | 7. DROP | Drop | 7. DROP | Not Optimis | Drop | Propose Drop Terminate |  |  | NY | NY | Terminate |  | 106.7243 | -6.2237 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [9 empty] | Terminate
129 | Area 2 | JBX084 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0421 | JBX084 | KOTABAMBUSELATANDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 4. CME | Erection OG | 21/04/26 : Wait PBG, GF 32 m WAITING PAYMENT, START ACTIVITY 24 DESEMBER 2025 (GF MONOPOLE 32 METER) | Optimis | 2026-02-28 | 12.12 BA overcapex proses sirkulir, sewa lahan Rp 388 jt/10 thn 4.12 excavation stop LL minta DP sewa lahan, monopole 32m, Lanjut B2R, NOD done | W4 2026 | Mar | PT JAGANATA SAKTI UNGGUL | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 106.8021 | -6.1869 |  |  |  |  | Monopole 18 1Leg |  |  | BTR |  | 3888888889 | [7 empty] | BTR
200 | Area 2 | JBX164 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JBX164 | SUPENOPERMATAHIJAUDMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial |  | 106.777 | -6.2178 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
94 | Area 2 | JBX165 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JBX165 | DURISELATANTAMBORA3DMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial |  | 106.7953 | -6.1521 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
119 | Area 2 | JBX167 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JBX167 | JLNANGKEJAYA10DMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial |  | 106.7939 | -6.1479 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
180 | Area 2 | JBX170 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0102 | JBX170 | PALMERAHBARAT4JAKARTADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW OG | 22/04/26 : IW kurang 3 kk, selesai Sabtu 25/4/26, rekom lurcam OK, soil test minggu 26/4/26 08/04/26 : BAN BAK OK (39jt/thn), IW OG (kurag 5 kk dari 25 kk) 1/4/26: IW target done 5/4/26 16/03/26 : IW OK (25kk setuju, 10 sudah ttd 15 ingin pembayaran lsg), Di lanjutkan setelah hari Raya 04/03/26 : IW OG (5 pemilik ruko) 25/02/26: IW OG 19/02/26 : BAN 39jt/th 26/1/26 : IW OG, Proses BAN BAK 15/1/26 : Proses negosiasi dgn LL 14/1/26 : Validasi NBAE OK (CAn P) Lanjut BAN/BAK 29/12 Need Validasi CAN P (106.78618 -6.20641) GF 25m 20/11 : IW OG | Optimis | 2026-03-20 | Add 3 RF Add 7 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | RFI : 25/5/26 IW : 12/4/26 | Apr | PT SUMBERSOLUSINDO HITECH | PT TRITECH CONSULT | BTR |  | 106.7862 | -6.2064 |  | 106.7862 | -6.2064 | Jl. pal merah bar. II- A. 20 Rt.003/010Kelurahan Palmerah, Kecamatan Palmerah, Kota Jakarta Barat, Provinsi jakarta pusat | Monopole 20 1Leg | Privat | Mp 25m | BTR | 3x3 | 433333333.3333 | Lahan LL terbatas | Tubular | Flenge Luar | 1.5 | 1.5 | 3 |  | BTR
191 | Area 2 | JBX171 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0105 | JBX171 | KSTUBUNSLIPIDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | APD OG | 27/04/26 : Pabrikasi 22/4/26, start cme w1 Mei 2026 22/04/26 : Review APD ke soleng 08/04/26 : Soil test ulang (soil test sebelumnya salah posisi) 1/4/26: APD OG (target 3/4/26) 16/03/26 : APD OG (target 18/03/26) 10/03/26 : APD OG (plan RFD 4/4/26) 04/03/26 : IW done, Rekom lurah OK 25/02/26 : Plan extend 6m , OG IW (6kk) target IW done 27/02/26 26/01/26 : Validasi NOK, Rehunting 14/01/26 : Validasi NBAE NOK (Can P) rehunting 29/12/25 : Need Validasi CAN P (106.80335 -6.19243) GF 25m 07/11/25 : Soswar dengan warga terkait IW (15 warga) 8/11/2025, BAN/BAK OG, LL minta waktu 5 hari | Optimis | 2026-03-20 | Add 3 RF Add 4 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | RFI : 20 Mei 2026 RFI : 6 Mei 2026 | Apr | PT SUMBERSOLUSINDO HITECH | PT TRITECH CONSULT | BTR |  | 106.804 | -6.1914 |  |  |  |  | Monopole 20 1Leg | Fasum | extend 6m | Extend 6m |  |  | trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
224 | Area 2 | JBX178 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0125 | JBX178 | JALANDAANMOGOTDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | ATP | 03/05/26 : PLN done,Platform BTS dan Panel KWH dan ACPDB Done 30/04/26 : Mitra submit undangan ATP 22/04/26 : Reposisi antena, koordinasi dgn pak Arizal 10/4/26: Pouring done, curing time 08/04/26 : Pouring done 1 kaki, koordina dgn konsultan untuk next step 07/04/26 : Plan pouring Rabu, 08 April 2026 1/4/26:Galian OG 28/3/26: Galian OG 16/03/26 : Pabrikasi OK. pekerjaan di lanjutkan setelah hari Raya 04/03/26 : Pabrikasi OG, plan finish 10/3/26 25/02/26: Proses pabrikasi material extend 3m (start pabrikasi 19/02/26) target finish 3/03/26 6. 04/02/26 : Proses kordinasi design extend tower ke bagian SOLENG 5. 22/01/26 : Proses Design Extend tower 3 meter - Done 4. 22/01/26 : Paralel proses kordinasi dengan dinas terakit penambahan ketinggian menara - Done 3. 22/01/26 : Menunggu review konsultan - Done 2. 22/01/26 : Proses survey Kand untuk Extend - Done 1. JOVIS Konsultan OG 05/01/2026 | Optimis | 2026-01-29 | Add 3 RF Add 7 RRU Final Sow Rescope: 3. reheight tower | Koordinasi : 8/4/26 W4 April 26 | Mar | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | Extend Pole |  | 106.7187 | -6.1531 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 3m |  |  | TAMAN | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 3m OG | Extend 3m
202 | Area 2 | JBX194 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0108 | JBX194 | HJPEENGDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 05/05/26 : Plan collo di Tower radio sdng koordinasi dgn pak riza 22/04/26 : Masih menunggu info dari pak Riza 08/04/26 : Menunggu Informasi dari Pak Riza mengenai ketersedian lahan untuk di sewa 01/04/26 : Reminder ke DMT (pak Riza) mengenai sewa tower radio 16/03/26 : Mitra koordinasi dgn pak Riza mengenai sewa tower radio 04/03/26 : Waiting approval BAN BAK (75jt/thn) 25/02/26: Rehunting issue highprice, plan proposed extend 6m 6. 09/01.26 : Need aproval BAN/BAK (75jt/th) 5. 07/01 Plan rehunting Can P issue HIGHprice(80jt/th) 4. 05/01/26: BAN/BAK waiting pertemuan LL plan 05/01/2026 3. BAN BAK 2. Validasi NBAE OK : 23/12/2025 (Cand P : -6.1982,106.7773 ) 1. 18.12 Need Validasi CAN P ( 106.7773 -6.1982) GF 32m (tower eksisting 60m) | Optimis | 2026-03-20 | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Reminder pak Riza : 8/4/26 Reminder : 1/4/26 | Apr | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | BTR |  | 106.7766 | -6.1983 |  | 106.7773 | -6.1982 |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | trotoar | Tubular | Flenge Dalam | 2 | 2 | 4 |  | BTR
211 | Area 2 | JBX195 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 25TS08N1992 | JBX195 | POSPALMERAHBARATDMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Lock Trial |  |  |  | NY | NY | Lock Trial |  | 106.7969 | -6.2081 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
225 | Area 2 | JBX197 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0109 | JBX197 | BUDHIBATUSARIDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 9. Propose Drop | Proposed DROP | 22/04/26 : Drop 08/04/26 : Drop 01/04/26 : Proposed Drop, JR sudah di submit 30/03/26 : Hard cand, lokasi padat penduduk, proposed extend 6m (cek lokasi dgn konsultan dan PEMDA) 16/03/26 : Proposed Drop 08/03/26 : plan check fisik consultan perencanaan 10 Mar 2026 25/2/26 : Koordinasi dgn pemda utk extend 6 m, plan soswar 27/2/26 09/2/26 : Submitt JR ke DMT done 19/1/26 : Mitra submit JR Paralel siapkan JR terkait issue penolakan radius Plan submit datek 31.12.2025 Proses rehunting lokasi padat penduduk | NOT Optimis | 2026-03-20 | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  |  | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | BTR |  | 106.7817 | -6.1878 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 3m |  |  | trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 3m OG | Extend 3m
227 | Area 2 | JBX200 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0126 | JBX200 | PURILINGKARLUARDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | Koordinasi Pemda | 22/04/26 : Reminder ke kelurahan mengenai status lahan 22/4/26 08/04/26 : Menunggu info dari kelurahan mengenai status lahan 01/04/26 : Reminder ke PEMDA 2/4/26, mengenai status lahan 16/03/26 : Koordinasi dengan PEMDA perihal status lahan 10/03/26 : Koordinasi dengan PEMDA mengenai status lahan 04/03/26 : Pengecekan IPPT, mitra req. IPPT ke DMT (pak Riza) 25/02/26: Cek IPPT 3. 11/01/26 : Mediasi dgn RW extend pole 3m, paralel hunting new cand 2. 05/01/26: plan submit datek 07/01/2026 1. Hunting, submit 31.12.2025 | Optimis | 2026-01-29 | Add 3 RF Add 10 RRU Final Sow Rescope: 3. reheight tower | Reminder kelurahan : 9/4/26 Reminder : 2/4/26 | Apr | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | Extend Pole |  | 106.736 | -6.1911 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 6m |  |  | taman | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
222 | Area 2 | JBX202 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0110 | JBX202 | JLMERUYAILIRRAYAUTARADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 9. Propose Drop | Proposed DROP | 22/04/26 : Drop 08/04/26 : Drop 01/04/26 : Proposed drop, JR sudah di submit 30/03/26 : Hard cand, lokasi existing di median jalan (tidak ada space buat extend 16/03/26 : Kandidat BTR gagal dan extend tidak memungkinkan (gagal BTR dan extend) 08/03/26 : Koordinasi ke PEMDA, kondisi Site Existing Dipinggir Jalan tidak ada space untuk struktur extend 6m check fisik konsultan perencanaan 10 Mar 2026 25/2/26 : LL cand P belum bisa di temui, option extend 6m, cek luas lahan eksisting (hunting new cand belum dapat) 09/02/26 : Proses Rehunting belum dapat Candidate baru , proses Submitt JR done Plan submit CAN B 8/01/2026 BAN BAK (120jt/tahun), paralel hunting cand. B Validasi NBAE OK : 23/12/2025 (Cand P : -6.19767,106.7521) 22/12/25 : Need Validasi CAN A ( 106.75210 -6.19767) RT 7m +18m | NOT Optimis | 2026-03-20 | Add 3 RF Add 12 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  |  | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | BTR |  | 106.7533 | -6.1975 |  | 106.7521 | -6.19767 | Jl Raya taman aries RT 004/008,Kel serengseng, Kec kembangan,Jakarta barat | Monopole 20 1Leg | Fasum |  | Extend 3m |  |  | TAMAN | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 3m OG | Extend 3m
223 | Area 2 | JBX207 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0111 | JBX207 | SATUMARETKALIDERESDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 3. RFC | BOQ | 30/04/26 : APD done . Menunggu dari DMT NOD pole 30 Std Baru (Resquest sudah diajukan) 29/04/26 : Waiting info NOD 27/04/26 : Mitra submit BA High Capex (BAN, BAK, BOQ) 22/04/26 : Wait approved BAN BAK (45jt/thn), IW OK (kompensasi total 68jt 15kk) 08/04/26 : Eskalasi IW (high price), submit BOQ sitac 14/04/26, joint survey asset 10/4/26, dismantle dan relok perangkat di lakukan mitra dan menjadi add work, untuk BTR Platform by DMT (MCP) 01/04/26 : BA dismantle blm ada, APD review by MK, plan BTS menggunakan baseframe, plan rekom lurcam done tgl 9/4/26 30/03/26 : Waiting APD, req.NOD 18/3/26, 16/03/26 : BAN BAK, IW done, status APD OG, ada permintaan 6 bulan setelah tower berdiri tower eksisting dismantle, ada permintaan eskalasi warga 08/03/26 : Plan Soil test 9 Maret 2026 25/2/26 : BAN BAK OG, IW done 24/02/26 : IW Done, pengajuan NOD 25/2/26 18/02/26 : Validasi OK Cand S -6.12830,106.70278 , Lanjut BAN/BAK 02/02/26 : Need Validasi Cand S ( -6.12830,106.70278) sesuai arahan Jovis dengan Tsel 30/01/26 : Validasi OK Cand R 28/01/26 : Need Validasi Cand R (-6.12857 106.70456) 27/01/26 : Submit Cand R 21/01/26 : Mitra submit BA LAPANGAN perihal perpanjangan sewa lahan atau penempatan baru 13/01/26: Validasi NBAE NOK (CAN P) Rehunting 30.12 Need Validasi CAN P (106.70164 -6.12946) GF 25m Plan submit datek 30.12.2025 Proses hunting, pemukiman padat penduduk, masih koordinasi dengan RT RW karena space terbatas | Optimis | 2026-03-20 | Add 3 RF Add 7 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Rekom Lurcam 9/4/26 APD : 18/03/26 NOD : 10/4/26 | Mar | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | BTR |  | 106.7038 | -6.1291 |  | 106.7028 | -6.1283 | Mall taman palem lantai 3 blok D/9B Jl.kamal raya outer ringroad Cengkareng Jakarta barat | Monopole 20 1Leg | Fasum | MP 30 | BTR | 4x4 | 50000000 | trotoar (berbatas dgn warung) | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | MP30 m | BTR
594 | Area 2 | JBX211 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JBX211 | JLKUMBANGRAYADMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.697 | -6.1411 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
190 | Area 2 | JBX232 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 25TS08N1975 | JBX232 | NUHRAYAASPARAGUSDMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Lock Trial |  |  |  | NY | NY | Lock Trial |  | 106.7765 | -6.2109 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
197 | Area 2 | JBX234 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0106 | JBX234 | JLNLINGKARLUARDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 3. RFC | Skom done | 30/04/26 : Untuk Lingkar Luar extend 3 M --> Done ---> Siap Pabrikasi for cutting a. Untuk Yang extend 6 M --> Karena disainnya Non Standart MItratel masih di reviews Sol Eng b. Standart Mounting dan Plat dapat digunakan 29/04/26 : Plan Pabrikasi 14 Mei 2026 22/04/26 : SKOM 23/4/26, target RFI 15/5/26 08/04/24 : APD OK 01/04/26 : Plan submit APD ke sol eng 2/4/26, need BA perubahan dari BTR menjadi extend 6m 30/03/26 : Extend 6 m, APD OG (submitted to sol eng 18/3/26) 16/03/26 : APD OG (target 18/03/26) 10/03/26 : Soiltest done, APD OG 08/03/26 : IW Done, Rekom OG, Soiltest 10 Mar 2026 25/02/26 : IW OK (extend 6m), penambahan lahan menjadi 3x3m 09/02/26 : Waiting Arahan dari DMT Mitra submit BA LAPANGAN perihal penambahan tinggi tower 19/01/26 : Can P gagal, ada penolakan warga 13/01/26 : Validasi OK, lanjut BAN BAK 24/12/25 : Need Validasi CAN P ( 106.72843 -6.14722) GF 25m | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | RFI : 15/5/26 | Apr | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | BTR |  | 106.7284 | -6.1472 |  | 106.7284 | -6.1472 | Jl.outer ringroad Cengkareng RT 002 RW.06 kel.cengkareng Timur kec.cengkareng,jakarta barat prov.Dki jakarta | Monopole 20 1Leg | Fasum | extend 6m | Extend 6m |  |  | TAMAN | Tubular | Flenge Luar | 3 (1.5) | 3 (1.5) | 9 (2.25) | Extend 6m | Extend 6m BTR
221 | Area 2 | JBX235 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0123 | JBX235 | BANDENGANUTARAGEDONGDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | JR | 22/04/26 : Proposed submit JR 08.04/26 : Hard candidate, proposed JR 1/4:26: Rehunting OG, target submit 7/4/26 16/03/26 : Rehunting dgn NOM baru 04/03/26 : Hunting cand B, cand A permintaan warga balai RW (200jt) 9. 02/03/26 : Cand A cancel krn permintaan warga tinggi (200jt), hunting cand B sesuai dengan arahan dari DMT (Pak Ihsan) 8. 25/02/26 : IW OG( potensi KK 7. 04/02/26 : IW OG 6. 30/01/26 : BAN Submit 32jt/th 5. 22/01/26 : Penjadwalan pertemua dengan LL 22/01 4.13/01/26: BAN/BAK OG pertemuan LL reschedule 3. BAN/BAK OG menunggu pertemuan LL 06/01/2026 2. Validasi NBAE OK:31/12/2025 (Cand A : -6.13557,106.80424) 1. 18.12 Need Validasi CAN A ( 106.80424 -6.13557 ) RT 9m + Pole 20 M 2. 18.12 Need Validasi CAN B (106.80286 -6.13588 ) RT 12m + Pole 15 M ( sudah ada eksisting Pole) | Optimis | 2026-03-20 | Add 3 RF Add 12 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | JR : 9/4/26 | Apr | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | BTR |  | 106.8037 | -6.1348 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 |  | BTR
248 | Area 2 | JBX239 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0096 | JBX239 | CITRAGARDENCITYSECTOR6DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 9. Propose Drop | Proposed DROP | 22/04/26 : Submit JR 08/04/26 : Submit JR 01/04/26 : Submit JR 16/03/26 : Hunting 04/03/26 : Hunting new cand, extend gagal LL tidak mau perpanjang 26/02/26: Extend ditolak LL(yayasan) dan rencana tidak mau perpanjang sewa berikutnya 3. Proses diskusi internal yayasan (H. Rohmat) 2. 05/01/26: plan submit datek 07/01/2026 1. Hunting, submit 31.12.2025 | NOT Optimis | 2026-01-29 | [30/10/25] Plan Eksekusi W4 Nov [9/09/25] Proses Fabrikan Ring mounting + Rack Gendong + Bracket Panel KWH + ACPDB [20/07/2025] Submit Dok.RFIN done |  | Apr | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | Extend Pole | Extend 3m | 106.7158 | -6.1284 |  |  |  |  | Monopole 20 1Leg | Privat |  | Extend 3m |  |  | Lahan LL terbatas | Tubular | FLenge Luar | 2 | 2 | 4 | Extend 3m OG | Extend 3m
244 | Area 2 | JBX262 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0013 | JBX262 | GOLDENARCHYSAKTIDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | Validasi OG | 22/04/26 : Wait validasi cand S ( -6.15571,106.76186) 16/04/26 : Cand R gagal IW, submit Datek cand S ( -6.15571,106.76186) 08/04/26 : Final IW 8/4/26 (kurang 2kk dari 16kk), paralel rehunting 01/04/26 : IW OG (sisa 3kk dari 16kk), plan IW 4/4/26 done 16/3/26: IW OG(20 KK, done 4 kk) lanjut IW setelah lebaran 04/03/26 : BAN 75jt/thn selama 5 tahun, lanjut IW 25/02/26: Plan pertemuan LL pembahasan BAN 21/02/26 : masih menunggu rembukan keluarga ya pak mengenai harga sewa. 18/02/26 : Validasi OK Cand R 03/02/26: Need Validasi Can R (106.76136 -6.15463) GF 32m, Can Q gagal IW 6. 24/01/26 : submit BAN 35jt/th 5. 23/01/26 : Cand Q validasi OK 4. 05/01/26 Need Validasi : CAN Q(106.76222 -6.15304) RT 12m + Pole 15m (BAN price 45jt/th) 3. Masih menunggu pertemuan pihak Yayasan, Rehunting terkendala lahan sekitar lahan pemerintahan. 2. Rehunting cand. Q (tanah milik Yayasan, plan meeting 2-3 hari) 1. Validasi NBAE OK : 18/12/2025 (Cand P : -6.15368,106.7629) | Optimis | 2026-03-20 | 1. 18.12 BAN/BAK OG | W4 Mei 2026 | Apr | PT JAGANATA SAKTI UNGGUL | PT TRITECH CONSULT | BTR | BTR Ruko | 106.7628 | -6.1539 |  | 106.7614 | -6.1546 | Jl. Komp. Departemen Agama RT.004 RW.003 Kel.Kedaung Kaliangke Kec Cengkareng Jakarta Barat | Monopole 20 1Leg | Fasum | MP 32M | BTR |  |  | trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 |  | BTR
258 | Area 2 | JBX263 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JBX263 | PASARDARURATKAPUKDMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.7441 | -6.1358 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
289 | Area 2 | JBX266 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0074 | JBX266 | KEBONJERUKINDAHUTAMADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW OG, validasi OG | 22/04/26 : Wait validasi cand R 16/04/26 : Cand Q gagal IQ, submit datek cand R ( -6.20337,106.76200), paralel nego ulang IW cand Q 08/04/26 : Final IW 8/4/26 (kurang 12 kk dari 27kk), paralel hunting 01/04/26 : Need approved BAN BAK OG (35jt/thn), Warga minta kompensasi dulu baru bersedia tanda tangan (2/4/26) 16/3/26: IW OG (16kk dari 27) lanjut setelah lebaran radius terkena 2RW 04/03/26 : BAN nego (35jt/thn), IW OG (14kk ok dari 27 kk) 25/02/26: Waiting approval BAN, paralel koordinasi RT terkait radius IW 17/01/26: BAN OG (high price 35jt/th) waiting approval 4. 15/01/26 : Hari Jumat (16/1/26) LL meminta janjian dengan team Mengenai harga sewa lahan. 3. 13/01/26 : Validasi cand Q OK, lanjut BAN/BAK 2. 23/12/25 : Need Validasi (Cand Q : -6.20316,106.76064), Cand P Issue High price (1,5M) 1. Validasi NBAE OK : 18/12/2025 (Cand P : -6.20349,106.76017) | Optimis | 2026-03-20 | 1. 18.12 BAN/BAK OG | W4 Mei 2026 IW :8/4/26 IW : 2/4/26 | Apr | PT JAGANATA SAKTI UNGGUL | PT TRITECH CONSULT | BTR | 0 degree Arah 100m | 106.7609 | -6.2032 |  | 106.7606 | -6.2032 | Jalan Lapangan Bola No.4 RT.04 RW.05 Kel.Srengseng Kec.Kembangan Jakarta Barat | Monopole 20 1Leg | Fasum | MP 32M | BTR |  |  | bahu jalan kecil(issue space pondasi) | Tubular | Flenge luar | 2 | 2 | 4 |  | BTR
294 | Area 2 | JBX268 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0068 | JBX268 | KPSALOKEMBANGANDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 8. Lock Trial | Lock Trial | 2. LOCKTRIAL : 22/12/2025 NBAE 1. 18.12 Validasi NBAE OG : 18/12/2025 | Not Optimis | 2026-03-20 | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  |  | PT JAGANATA SAKTI UNGGUL | PT TRITECH CONSULT | Lock Trial | BTR Arah 50m 310 degree | 106.7541 | -6.1635 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | Lahan LL terbatas | Tubular | Flenge Luar | 2 | 2 | 4 |  | Lock Trial
267 | Area 2 | JBX271 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0020 | JBX271 | TAMANKOTAPEDONGKELANDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | DP lahan, Skom done | 22/04/26 : Wait dp lahan 16/04/26 : Menunggu BA high CAPEX 09/04/26 : Menunggu BA high CAPEX 08/04/26 : Reminder DMT mengenai DP lahan 01/04/26 : Reminder DMT mengenai DP lahan 16/3/26: Implementasi Menunggu DP, Mitra paralel menyiapkan estimasi BOQCME/SITAC sebagai bahan justifikasi 13/03/26 : BAN/BAK 40jt/thn 04/3/26: Menunggu realisasi DP, NOD request done 25/02/26: Implementasi menunggu DP 8. 15/02/26 : SKOM Done 7. 13/02/26 : Mitra submit TSSR SITE Taman Kota 6. 06/02/26 : REKOM CAMAT DONE 5. 03/02/26 : REKOM LURAH DONE, REKOM CAMAT OG, Paralel Soil OG 4. 15/01/26 : IW on going, Dari 31 KK tinggal 5 KK yang belum ttd, estimasi minggu ini done. 3. BAN /BAK OG (issue high Price 70jt/thn) 2. Validasi NBAE OK: 29/12/2025 (Cand P : -6.15897,106.75981) 1. 18.12 Need Validasi CAN P ( 106.75981 -6.15897) GF 32m | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | RFI : W1 Mei 2026 | Mar | PT JAGANATA SAKTI UNGGUL | PT TRITECH CONSULT | BTR | 170m arah 150 degree | 106.7583 | -6.1598 |  | 106.7598 | -6.159 | Pesing Garden Rt. 015/002 ‎Kelurahan Kedoya Utara ‎Kecamatan Kebon Jeruk ‎Jakarta Barat | RT 14m + Pole 9m = 23m | Fasum | MP 32M | BTR |  |  | street view NA | [6 empty] | BTR
63 | Area 2 | JBX273 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0075 | JBX273 | CENDRAWASIHKEDAUNGKALIANGKEDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 22/04/26 : Wait approved sewa lahan (30jt/thn) 16/04/26 : Ahli waris meminta kenaikan sewa lahan 30jt/tahun, sewa lahan sisa 1 tahun 08/04/26 : Hasil negosiasi sewa lahan 35jt/thn, sisa lahan 1 tahun, IW OG 01/04/26 : Ahli waris meminta biaya kompensasi penambahan ketinggian 45jt/thn, sisa masa sewa 1 tahun lagi 16/03/26 : Proposed extend di tower eksisting, Nego BAN dilanjutkan Tim Asset DMT 04/03/26 :Waiting Approval BAN 40jt/th 25/02/26: Waiting approval BAN, paralel penjajakan IW (16-20 KK) 23/01/26 : BAN 40jt/th waiting approval 19/01/26: Pengajuan BAN LL 40jt/th 15/01/26 : LL meminta waktu sampai hari jumat (16/1/26) untuk berembuk terlebih dahulu dengan keluarga mengenai harga Sewa lahan. 14/01/26: validasi NBAE OK (Can A) lanjut BAN/BAK Waiting Validasi CAN A , issue High price (45jt/th) 29.12 Need Validasi CAN A ( 106.72515 -6.14523) GF 32m | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | W2 Mei 2026 Submit BAN : 10/4/26 | Apr | PT JAGANATA SAKTI UNGGUL | PT TRITECH CONSULT | Extend 6m | BTR Arah 100m 285 degree | 106.725 | -6.1453 |  | 106.7251 | -6.1452 | jl.cendrawasih V RT. 005/RW.006 kel.cengkareng Barat Kec Cengkareng,jakarta | Monopole 20 1Leg | Fasum | MP 32M | BTR |  |  | Lahan LL | Tubular | Flenge luar | 2 | 2 | 4 | Extend 6m | Extend 6m
236 | Area 2 | JBX286 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0025 | JBX286 | JLPANJANGKODAYATURDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | LOCK TRIAL | 08/04/26 : Lock Trial 06/04/26 : Lock Trial by DMT 01/04/26 : Extend 6m, di bantu oleh RT (belum datang), IPPT sudah expired (habis berlakunya) 16/03/26 : extend tower eksisting terkendalan keberatan Pihak showroom BYD, Proses pendekatan ke BYD akan dibantu RT (info RT warga lingkungan tidak keberatan), 10. 10/03/26 : Pengajuan extend 6m, koordinasi dengan ketua RW setempat 9. 04/3/26: Rehunting OG, extend 6m 8. 26/02/26 : Validasi Cand Q NOK 7. 25/02/26: Need Validasi Can R ( -6.16259,106.76274) 6. 18/02/26 : LL meminta 800jt/th, Rehunting, Need Validasi Cand R ( -6.16259,106.76274) MP 32 M 5. 05/02/26 : Validasi OK Cand Q 4. 30/01/26 : Mitra submit JR (warga menolak dibangun tower), rehunting, Need Validasi Cand Q ( -6.16259,106.76274) RT 10+Pole 20M 3. 15/01/26 : LL bertemu tim hari Jum'at 16/1/26 2. 14/01/26: Validasi NBAE OK (Can P) Lanjut BAN/BAK 1. 23.12 Need Validasi CAN P ( 106.76255 -6.16215) GF 32m | Not Optimis | 2026-03-20 | Add 3 RF Add 4 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT JAGANATA SAKTI UNGGUL | PT TRITECH CONSULT | BTR | 170m arah 230 degree | 106.7631 | -6.162 |  | 106.7627 | -6.1626 | jl. Pesing Koneng RT.012/002..Kel.Kedoya Utara, ,kec. kebon Jeruk ,kota Jakarta Barat, Jawa Barat | Monopole 20 1Leg | Fasum | MP 32M | BTR |  |  | trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 |  | BTR
259 | Area 2 | JBX288 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0018 | JBX288 | JLHSUAIBKBJERUKDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 22/04/26 : Wait aprroved BAN BAK (70jt/thn), IW done kompensasi 1jt/kk total 10kk 08/04/26 : Waiting approval BAN(70jt), issue kompensasi IW 1jt/KK(10 kk) 1/4/26: Waiting approval BAN(70jt), issue Potensi kompensasi IW 1-1,5jt/KK(10 kk) 16/3/26: Waiting Approval BAN(70jt/th) 10/03/26 : High Sitac, permintaan LL 70jt/thn 25/02/26: hasil jovis plan extend 6m di esksisting , waiting Approval BAN(70jt/th) 6. 16/02/26 : IW Done 5. 28/1/26 : Plan JOVIS 30/1/26 4. 23/01/26 : Submit Berita Acara belum ditemukan LL yang sesuai, menunggu arahan lebih lanjut 3. 20/1/26 : Rehunting, ada penolakan warga di sekitar tikor NOM 2. plan 9/01/2026 1. Plan submit Datek 31.12.25 | Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT NAER TUNAS INDONESIA | PT TRITECH CONSULT | BTR | 180m arah 270 degree | 106.7725 | -6.2005 |  |  |  |  | Monopole 20 1Leg | Fasum | extend 6m | Extend 6m |  |  | Lahan warga | Tubular | Flenge Luar | 2 | 2 | 4 | Extend 6m | Extend 6m
254 | Area 2 | JBX290 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0097 | JBX290 | JLJERUKSEGARDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | Pabrikasi OG | 27/04/26 : Pabrikasi OG, target 30/4/26 22/04/26 : Pabrikasi OG 08/04/26 : Star Pabrikasi 15/4/28 01/04/26 : Issue pabrikasi start 15/4/26 16/03/26 : Pabrikasi OG plan finish 30/3/26 09/03/26 : plan start pabrikasi 10 Mar 26 estimasi selesai 30 Mar 26 25/02/26: Pabrikasi material extend 3m( start pabrikasi 26/02/26 18/02/26 : Mitra submit BA penolakan warga perihal penambahan ketinggian tower 6m, mitra izin extend 3m menunggu arahan, lanjut extend 3m 28/1/26 : konfirmasi PKS ke pak Riza 20/1/26 : Negosiasi ulang, LL meminta 25jt untuk extend pole 05/01/26 : IW OG, (BA permintaan kompensasi extend tower dari LL 30jt) Eksisting area lahan pekarangan LL, IW OG | Optimis | 2026-01-29 | Add 3 RF Add 7 RRU Final Sow Rescope: 3. reheight tower | RFI : 14/5/26 W1 mei 26 | Apr | PT NAER TUNAS INDONESIA | PT TRITECH CONSULT | Extend Pole | Extend 3m | 106.736 | -6.2034 |  |  |  |  | Monopole 20 1Leg | Privat |  | Extend 3m |  |  | taman | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 3m OG | Extend 3m
295 | Area 2 | JBX292 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0069 | JBX292 | SURWAWIDURIKEDOYADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW OK | 27/04/26 : Lanjut 22/04/26 : Wait approved eskalasi untuk warga dan lurcam (114jt untuk 17kk) 08/04/26 : Mitra mengajukan add work kompensasi warga 10/4/26 01/04/26 : Proses realisasi kompensasi warga, Soil test setelah reaslisasi 5/4/26 16/3/26: Proses Revisi BAK untuk kelanjutan, Soil test menunggu proses BAK 25/02/26: BAN (35jt.th) approve BAK OG, 6. 28/1/26 : Plan submit BAN/BAK 29/1/26, IW OK 5. 20/1/26 : Proses submit BAN, IW done 4. Submit BAN 09/01/26 (40jt/th), BAK & IW OG 3. BAN/BAK OG plan konfirmasi LL (05/01/2026) 2. Validasi NBAE OK: 29/12/2025 (Cand P : -6.17627,106.76287) 1. 18.12 Need Validasi ( 106.76287 -6.17627) GF 32m | Optimis | 2026-03-20 | Add 3 RF Add 4 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | W4 Mei 26 | Mar | PT NAER TUNAS INDONESIA | PT TRITECH CONSULT | BTR | BTR Arah Sekolah Ichtus dan arah utara 150m ketinggian 30m | 106.7627 | -6.1766 |  | 106.76287 | -6.17627 |  | Monopole 20 1Leg | Fasum | MP 32M | BTR | 5x5 | 388888888.8889 | street view NA |  |  | 1 | 2 | 3 |  | BTR
255 | Area 2 | JBX293 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0026 | JBX293 | JLBENDAKAMALDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 3. RFC | APD OG | 22/04/26 : Soiltest done, APD 25/4/26 14/04/26 : Plan Soil test 15/04/26 08/04/26 : Plan soil test 10/4/26, IW OK 1/4/26: Plan soswar 3/4/26 ( nilai kompensasi sudah ok) 16/3/26: Proses negosiasi nilai kompensasi warga, plan 19/3/26 10/03/26 : Proses Negosiasi (permintaan kompensasi warga) 25/02/26 : IW Done 23/2, menunggu realisasi plan 27/02 03/02/26 : Validasi NBAE OK (Can Q -6.10774 106.69894) Lanjut BAN/BAK 28/01/26 : Need Validasi cand Q ( -6.10774 106.69894) 20/01/26 : Need validasi cand Q, cand P cancel 14/01/26 : Validasi NBAE OK (Can P) Lanjut BAN/BAK 05/01/2026 Need Validasi CAN P (106.69845 -6.10795) GF 30m Plan submit Datek 31.12 | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | RFI : 18 Mei 2026 RFI : W1 Mei 2026 | Mar | PT NAER TUNAS INDONESIA | PT TRITECH CONSULT | Extend 6m | 150m arah 0 degree | 106.6992 | -6.1091 |  | 106.6989 | -6.10774 |  | Monopole 20 1Leg | Fasum | MP 32M | BTR | 4x4 | 277777777.7778 | Lahan LL | Tubular | Flenge Luar | 2 | 2 | 4 | MP 32m Extend 6m | Extend 6m
250 | Area 2 | JBX294 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0021 | JBX294 | DEPLUJOGLOJAKBARDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW OK | 22/04/26 : luas lahan 1,2x3 m, mitra akan konsultasi dgn konsultan mengenai desain perkuatan dan extend 6m 08/04/26 : Cek luas lahan 10/4/26 01/04/26 : Plan realisasi kompensasi warga 4/4/26, plan soil test 7/4/26 16/03/26 : Pembayaran IW setelah hari Raya 04/03/26 : Permintaan dana OK, IW done, extend 3 m 25/02/26 : Waiting approval Dana Renov permintaan DKM (pengganti nilai BAN) 19/02/26 : Mitra submit BA BERITA ACARA LAPANGAN Permintaan DKM dan Warga BAN BAK 80jt/thn 13/01/26: BAN OG (issue high price(80jt/th) Menunggu pertemuan dgn RW, perihal bantuan IW (masjid minta bantuan dana pembangunan) 23.12 : Proses Sosialisasi (IW OG) | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | RFI : 15 Mei 2026 | Apr | PT SUMBERSOLUSINDO HITECH | PT TRITECH CONSULT | BTR | Need Survey Extend | 106.7328 | -6.2185 |  |  |  |  | Monopole 20 1Leg | Privat | extend 6m | Extend 3m |  |  | street view NA |  |  | 1.5 | 1.5 | 3 |  | BTR
386 | Area 2 | JBX370 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS09Z0028 | JBX370 | KAMALKALIDERES16DMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 4. CME | Curing time OK | 29/04/26 : OG Redesign pondasi (Tunas) plan 30 April 2026 22/04/26 : Koordinasi Mitra-MK- Konsultan mengenai desain APD 22/4/26 (ganti konsultan) 08/04/26 : Pekerjaan di hold karena LL minta DP lahan, DMT mengirim email untuk talangan DP, eskalasi high capex 01/04/26 : Curing time done, sortir material 6/4/26 (sesuai NOD), back fill masih negosiasi dgn LL perihal ijin mulai kerja 30/03/26 : Curing time, Pabrikasi Done 18 Maret 2026 16/03/26 : Curing time 1 day, LL memberi ijin masuk lokasi 21/4/26 15/03/26: Pouring done curing time OG 10/03/26 : Pouring borepile done 09/03.26 : Prose penyediaan material alam yang belum lengkap, pouring borepile OG 08/03/26 : NOD Done, Proses pengecoran Bore Pile 09 Mar 26 15/2/26: Start CME Galian OG 14/2/26 : SKOM done, RFC menunggu DP dan NOD rilis 09/02/26 : waiting NOD Proses Rekom Camat, pihak kecamatan masih fokus penanganan banjir , APD done 05/01/2026 : Waiting Rekom KKOP(need signed BAN/BAK) plan 9/01/2026, APD submit 07/01/26 29/12 : Soil test done, APD submit 31.12.2025, Rekom otoritas bandara (KKOP), lurcam OG 24/12 : Plan Soil tes 26 des 2025 03/12 : IW 4 warga OK, IW 2 corp OG 01/12 : IW OG, RT menyarankan 4 warga di masukkan dalam IW (sebelumnya sudah termasuk LL), 2 Corp. masih review management 26/11 : CAND C IW kurang 2 (corporate) meminta surat pemebritahuan secara tertulis, target 29/11/2025, cand D (hotel Prima) blm ada jawaban dari pihak MB hotel 20/11 : IW OG 19/11 : Soswar OG, BAN 30jt, alternatif kandidat dihotel D'Prima, kandidat 2 07/11 : Soswar dengan warga terkait IW (15 warga) 8/11/2025, BAN/BAK OG, LL minta waktu 5 hari | Optimis | 2026-03-20 | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Sortir material : 6/4/26 NOD : 18/04/26 | Mar | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | BTR |  | 106.6872 | -6.1287 |  |  |  |  | Monopole 20 1Leg |  | MP 30 | BTR | 3x3 |  | Lahan LL terbatas | Tubular | Flenge Luar | 1.5 | 1.5 | 3 |  | BTR
607 | Area 2 | JBX385 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0027 | JBX385 | ANGKETAMBORADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 04/05/26 : LL meminta 60jt/5th, ll khawatir tinggi tower 20m karena akan berpengaruh dengan berat tower yg juga ada di rooftopnya (tower milik STP). 22/04/26 : Menunggu jawaban LL perihal penawaran DMT 08/04/26 : Menunggu jawaban LL mengenai harga yg di tawarkan DMT , cek kebutuhan lahan untuk pole 20m 1/4/26: Proses pengajuan BAN ke LL( BM Gedung), Plan submit 3/4/26 16/3/26: Proses BAN OG plan 19/3/26 25/02/26: proses BAN OG 5. 30/1/26 : Validasi OK Cand P 4. 28/1/26 : Plan JOVIS 3/2/26, submit datek cand P (-6.15819 106.80796) 3. 20/1/26 : menunggu keputusan LL perihal rooftop mau disewakan atau tidak 2. plan submit Datek 07/01/2026 1. Plan submit Datek 31.12.25 | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Reminder : 10/4/26 | Apr | PT NAER TUNAS INDONESIA | PT TRITECH CONSULT | BTR | BTR Arah 50m 180 Degree | 106.8082 | -6.1582 |  | 106.808 | -6.1582 | Jl.KH.Moh.Mansyur, Kel.Duri Selatan Kec. Tambora Jakarta Barat | Monopole 20 1Leg | Fasum | RT 11 M + pole 20 | BTR | 5x5 |  | trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | RT 11m +Pole 20m | BTR
226 | Area 2 | JBX386 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0022 | JBX386 | STADIONCENDRAWASIHDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 7. DROP | Proposed Drop | 08/04/26 : Drop 01/05/26 : Proposed drop, mitra submit JR 16/3/26: Proposed Drop 25/02/26: Rehunting OG , paralel proposed extend 6m 5. 30/1/26 : Validasi NOK 4. 28/1/26 : Need Validasi cand P 3. 15/01/26 : Submit cand P ( -6.14211 106.720602) Need validation . Plan submit Datek 05/01/2026 1. Plan submit Datek 31.12 | Not Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT NAER TUNAS INDONESIA | PT TRITECH CONSULT | BTR | 310' 150m | 106.7211 | -6.1442 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Terminate |  |  | trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | HOLD By Tsel (Propose DROP) | HOLD By Tsel (Propose DROP)
310 | Area 2 | JBX389 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0063 | JBX389 | JOGLORAYAKEMBANGANDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 22/04/26 : Reminder aset DMT mengenai sewa lahan 08/04/26 : Mitra akan menginformasikan ke asset mengenai sewa lahan yg mau habis 1/4/26: Perlu konfirmasi kelanjutan negosiasi sisa sewa lahan (berakhir 2026) 16/03/26 : Wait approved BAN BAK (50jt/th), IW 14kk 10/03/26 : Nego sewa lahan (habis 2026) 04/03/26 : BAN OK (50jt/thn), extend 6m 25/02/26 : Hasil jovis proposed extend 6m, Waiting approval BAN(50jt/th) lahan 3x4 26/01/26 : Hunting OG 13/01/26 : Hunting OG 07/01/26 : Rehunting cand Q, plan submit datek 07.01.2026 31/12/25 : Valindasi NBAE Not OK : 31/12/2025 (rehunting as noted) 24/12/25 :Need Validasi CAN P (106.73977 -6.21960) GF 30m | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Info ke Aset : 8/4/26 | Apr | PT SUMBERSOLUSINDO HITECH | PT TRITECH CONSULT | BTR | BTR Arah 100m 10 degree | 106.7402 | -6.2195 |  |  |  |  | Monopole 20 1Leg | Fasum | extend 6m | Extend 6m |  |  | street view NA |  |  | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
315 | Area 2 | JBX390 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0098 | JBX390 | TANAHTAMBORADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 22/04/26 : Menunggu balasan LL periha kompensasi perluasan lahan 08/04/26 : Info Pak Riza sewa lahan habis 2/5/28, croscek ke LL 1/4/26: Perlu FU dari tim ASet DMT 16/3/26: Perlu FU dari tim Aset DMT 4. 28/1/26 : Konfirmasi PKS ke pak RIza 3. 20/1/26 : LL minta kejelasan perpanjangan kontrak 2. Proses kroscek lingkungan terlkait proposed extend pole 12m 1. Plan submit Datek 31.12 | Optimis | 2026-01-29 | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Croscek : 13/4/26 | Apr | PT NAER TUNAS INDONESIA | PT TRITECH CONSULT | Extend Pole | Extend 12 m (Rooftop) | 106.8117 | -6.1513 |  |  |  |  | Monopole 20 1Leg | Privat |  | Extend 3m |  |  | Rooftop | Pole | Pole | 2,5 | 2,5 |  | Extend 3m OG | Extend 3m
328 | Area 2 | JBX391 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0133 | JBX391 | JLKALIANYARTAMBORADMTHL | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Hammer test | 05/05/26 : Plan hari ini Soil Test 27/04/26 : Test Hammer 22/04/26 : Test hammer 24/4/26 08/04/26 : Survey OG, extend 6m 02/04/26 : Gagal survey karena LL tidak ada dilokasi, plan 06/04/26 mendapat jawaban dari LL 1/4/26: Plan survey extend di Site eksisting 2/4/26 26/03/26 : JR Submit Cand P and Q 16/3/26: Plan extend di lahan eksisting, konfirmasi LL OG, 04/03/26: rehunting OG, paralel cek extend 6m di site eksisting (kondisi RT14m+pole 6M) 25/02/26: Hard candidat proposed Extend 6m site eksisting 23/02/26: CAN Q gagal BAN (DKM menolak) Rehunting OG 13/02/26 : BAN Plan 16 Feb 2026 11/02/26 : Verifikasi Cand Q OK lanjut BAN 09/02/26 : Need Validasi Cand Q ( -6.15734,106.79743) 03/02/26: Validasi NBAE NOK rehunting as noted 09/01/26 : Need Validasi cand P ( 106.79874 -6.15958) RT 12m + Pole 19m Plan submit DATEK 05/01/2026 Plan submit datek 30/12/2025 | Optimis | 2026-01-29 | Add 3 RF Add 8 RRU Final Sow Rescope: 3. reheight tower |  | Apr | PT INTERTEL MEDIA PRIMA | PT TRITECH CONSULT | Extend Pole | 150m 300 degree | 106.7988 | -6.1581 |  | 106.7974 | -6.1573 | Jl. Kalianyar V | RT 14m + Pole 6m = 20m | Fasum | Extend 6m | Extend 3m |  |  | Rooftop | Pole | Pole | 3 | 5 | 8 | extend 6m | Extend 3m
303 | Area 2 | JBX393 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0023 | JBX393 | JLJAYA25CENGKARENGDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG, IW OK | 22/04/26 : Negosiasi harga untuk perpanjangan sewa lahan dan extend 6m 08/04/26 : BAN OG, plan soil test 1/4/26: OG BAK, IW 80%, Plan RFC 6/4/26 16/3/26: BAK OG plan 17/3/26, IW OG 04/03/26 : Need approved BAN (32jt/thn), IW OK 25/02/26: menunggu approval BAN, IW OK 6. 28/1/26 : Plan submit BAN/BAK fisik 29/1/26, IW menunggu BAN/BAK 5. 27/01/26 : Soswar Done 4. 21/01/26 : Paralel soswar progress 3. 19/01/26: BAN OG ( 32jt/th) waiting approval 2.13/01/26: Validasi NBAE OK Lanjut BAN/BAK 1. 29.12 Need Validasi CAN P (106.72248 -6.12950) GF 30m | Optimis | 2026-03-20 | Add 3 RF Add 7 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | W4 april 26 | Apr | PT INTERTEL MEDIA PRIMA | PT TRITECH CONSULT | BTR | 260' 90m | 106.7232 | -6.1288 |  | 106.7225 | -6.1295 |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | Lahan LL terbatas | Tubular | Flenge luar | 1.5 | 1.5 | 3 |  | BTR
327 | Area 2 | JBX397 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0110 | JBX397 | DANAWIJAYAKESUMADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 3. RFC | Skom done | 30/04/26 : Untuk Yang extend 6 M --> karena disainnya Non Standart MItratel masih di reviews Sol Eng, Standart Mounting Tidak dapat digunakan karean pakai disain Selubung 29/04/26 : Plan Pabrikasi 14 mei 2026 22/04/26 : APD done, SKOM 23/04/26 08/04/26 : APD OG review sol eng 01/04/26 : APD Waiting approved by Sol eng 30/03/26 : APD OG (submitted to sol eng 18/3/26) 16/03/26 : APD OG (target 18/03/26) 10/03/26 : Soiltest done, APD OG 08/03/26 : IW Done, Rekom OG, Soiltest 10 Mar 2026 25/2/26 : Tim sitac soswar untuk extend 6m, penambahan luas lahan menjadi 3x3m 05/01/2026 Plan JOVIS konsultan untuk desain extend 07/01/2026 SIK buat tim survey belum bisa rilis, OF error IW done, need PKS eksissting | Optimis | 2026-01-29 | Add 3 RF Add 7 RRU Final Sow Rescope: 3. reheight tower | RFI : 15/5/26 APD : 02/04/26 | Mar | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | Extend Pole | Extend 3m | 106.7695 | -6.16 |  |  |  |  | Monopole 20 1Leg | Fasum | extend 6m | Extend 3m |  |  | taman | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 6m Extend 3m OG | Extend 6 m Extend 3m
329 | Area 2 | JBX398 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0073 | JBX398 | GREENGARDENKEDOYADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 22/04/26 : Menunggu approved BAN BAK (35jt/thn) 08/04/26 : Menunggu approved BAN (45jt), IW OG 1/4/26: Need Aproval BAN 16/3/26: Need Approval BAN (45jt/th) 04/03/26 : Need approved BAN (45jt/thn) 25/02/26 : menunggu approval BAN, IW OK 6. 28/1/26 : Plan submit BAN/BAK fisik 29/1/26, IW menunggu BAN/BAK 5. 27/01/26 : Soswar Done 4. 21/01/26 : Waiting approval BAN & Paralel soswar progress 3. 12/01/26: BAN submited (45jt/th) IW OG 2. 05/01/26 : Validasi NBAE OK Can P(-6.17231 106.7556) 1. 02/01/2026 Need Validasi CAN P (106.7556 -6.17231) GF 30m plan submit datek 29/12/2025 | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | W1 Mei 2026 | Apr | PT INTERTEL MEDIA PRIMA | PT TRITECH CONSULT | BTR | 350' 100m | 106.756 | -6.1728 |  | 106.7556 | -6.1723 |  | Monopole 20 1Leg | Fasum |  | BTR | 5x5 | 500000000 | street view NA |  |  | 1.5 | 1.5 | 3 | MP32m | BTR
608 | Area 2 | JBX405 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0061 | JBX405 | JLRAYAPREPEDANDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 22/04/26 : IW OG (kurang 5 kk dari 20 IW 08/04/26 : LL OK utk extend, soil test 11/4/26 1/4/26: plan survey extend 4/4/26 26/03/26 : on progress negosiasi kembali ke NOM dg extend 6meter 16/3/26: Proses koordinasi LL untuk proses Ekstend di tower eksisting 04/03/26 : Plan extend 6m, 25/02/26: Proposed extend 6m 23/02/26: Can P gagal BAN, plan ke NOM extend ke 25M 13/02/26 : BAN Plan 16 Feb 2026 12/02/26 : Need Validasi Cand P ( -6.11557,106.70657), Validasi OK Cand P 27/01/26 : Need Re Assesment 25m 05/01/26 Need Validasi CAN P (106.70657 -6.11557) GF 30m Plan submit DATEK 05/01/2026 plan submit datek 30/12/2025 | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | W1 Mei 2026 | Apr | PT INTERTEL MEDIA PRIMA | PT TRITECH CONSULT | BTR | 225' 250m | 106.7067 | -6.1154 |  | 106.7066 | -6.1156 | Jl. Prepedan dalam | Monopole 20 1Leg | Fasum | Extend 6m | Extend 6m | 4x4 |  | street view NA | Tubular | Flenge luar | 1.5 | 1.5 | 3 | extend 6m | BTR
304 | Area 2 | JBX407 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0028 | JBX407 | JLPELOPORTEGALALURDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 22/04/26 : IW OG, soil test 27/4/26 08/04/26 : OG BAK, IW 100%, plan RFC 8/4/26, soil test 1/4/26: OG BAK, IW 80%, plan RFC 8/4/26 16/3/26: BAK OG Plan 17/3/26, IW OG 04/03/26 : Need Approved BAN (32jt/thn), IW OK 25/02/26: menunggu approval BAN, IW OK 6. 28/1/26 : Plan submit BAN/BAK fisik 29/1/26, IW menunggu BAN/BAK 5. 27/01/26 : Soswar Done 4. 21/01/26 : Paralel soswar progress 3. 19/01/26: BAN OG (32jt/th) waiting approval 2. 13/01/26: Validasi NBAE OK (can P) lanjut BAN/BAK 1. 29.12 Need Validasi CAN P (106.7171 -6.1237) | Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | W1 Mei 2026 | Apr | PT INTERTEL MEDIA PRIMA | PT TRITECH CONSULT | BTR | BTR Arah 60m 220 Degree | 106.7169 | -6.1232 |  | 106.7171 | -6.1237 |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | street view NA | Tubular | Flenge luar | 1.5 | 1.5 | 3 |  | BTR
148 | Area 2 | JKB863 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 25TS08N2018 | JKB863 | INTERSECTIONPSANGGRAHANDMT | Plan ≤ 2025 | BTS HOTEL |  | 7. DROP | Drop | 7. DROP | Not Optimis | Drop | Propose Drop Terminate |  |  | NY | NY | Terminate |  | 106.756 | -6.1904 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [9 empty] | Terminate
161 | Area 2 | JKB864 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 25IS08N0109 | JKB864 | JALANARJUNAUTARADMT | Plan ≤ 2025 | BTS HOTEL |  | 7. DROP | Drop | 7. DROP | Not Optimis | Drop | Propose Drop Terminate |  |  | NY | NY | Terminate |  | 106.7831 | -6.1856 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Terminate
589 | Area 2 | JKB865 | Jabat |  | Non MKT | Non MKT |  | BTSH | NY | JKB865 | JALANMERUYAUTARADMT | Plan ≤ 2025 | BTS HOTEL |  | 7. DROP | Drop | 7. DROP | Not Optimis | Drop | Propose Drop Terminate |  |  | NY | NY | Terminate |  | 106.7396 | -6.2002 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [9 empty] | Terminate
158 | Area 2 | JKB874 | Jabat |  | Non MKT | Non MKT |  | BTSH | NY | JKB874 | SIMPANGCIDENGTIMURDMT | Plan ≤ 2025 | BTS HOTEL |  | 7. DROP | Drop | 7. DROP | Not Optimis | Drop | Propose Drop Terminate |  |  | NY | NY | Terminate |  | 106.8121 | -6.1757 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [9 empty] | Terminate
159 | Area 2 | JKB895 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 23TS03Z0021 | JKB895 | FACHERUDINDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 15/08/2023 | 0 | RFI | Done RFI | PT GEAF SOLUSIANDA PRATAMA | Waspang | Contine with Macro |  | 106.8151 | -6.1848 |  |  |  |  | Monopole 18 1Leg |  |  | Contine with Macro | [9 empty] | Contine with Macro
264 | Area 2 | JKB919 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0024 | JKB919 | JLJATI1DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 22/04/26 : Proses IWke warga, BAN BAK already submit to DMT 09/04/26 : Need approval BAN/BAK 25jt/thn 08/04/26 : Plan negosiasi BAN 9/4/26 1/4/26: Plan pertemenuan negosiasi dengan pihak Carolus 26/03/26 : Pengajuan harga sewa 25jt/th untuk 5 tahun 16/3/26: Proses BAN 17/3/26 04/03/26 : Menunggu approval BAN (15jt/thn) 23/02/26: Need Validasi Can Q2 (LL CAN Q meminta pergeseran titik sejauh 20m 13/02/26 : BAN Plan 16 Feb 2026 09/02/26 : Waiting konfirm LL 30/01/26 : Validasi OK Cand R, Validasi OK Cand Q 28/1/26 : Need validasi Kandidat Q (-6.14689 106.73511) & R (-6.14747 106.73653) 21/01/26 : Need validasi Kandidat Q (-6.14689 106.73511) & R (-6.14747 106.73653), submit datek done Validasi NBAE NOK (can P) rehunting Need Validasi cand P (106.7376 -6.1466) 29.12 Need Validasi CAN P (106.7376 -6.1466) RT (mesjid) 10 m + Minaret 15m 24.12 Need Validasi CAN Q (106.7376 -6.1466) GF 30m | Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | RFI : W1 Mei 2026 | Apr | PT INTERTEL MEDIA PRIMA | PT TRITECH CONSULT | BTR | 150m arah 90 degree | 106.7361 | -6.1464 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | trotoar | Tubular | Flenge Luar | 2 | 2 | 4 |  | BTR
355 | Area 2 | JKP203 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 23TS03Z0015 | JKP203 | DIPONEGOROMENTENG2DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | Minus RFI NOTICE (need ATP) | Optimis | RFI : 22/12/2025 | Lanjut Extend 3m | W4 DESEMBER 2025 | Done RFI | PT INFRAKO DAYAMITRA | Waspang | Extend Pole |  | 106.8354 | -6.2006 |  |  |  |  | Monopole 18 1Leg |  |  | Extend 3m | [8 empty] | Extend 3m OG | Extend 3m
153 | Area 2 | JKP219 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 23TS03Z0017 | JKP219 | PENJERNIHANMAKRODMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 11/05/2023 | 0 | RFI | Done RFI | PT INFRAKO DAYAMITRA | Waspang | Contine with Macro |  | 106.8052 | -6.204 |  |  |  |  | Monopole 18 1Leg |  |  | Contine with Macro | [9 empty] | Contine with Macro
251 | Area 2 | JKP231 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0029 | JKP231 | CEMPAKABARUBARATDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OK | 22/04/26 : Reminder negosiasi ke LL 22/4/26 08/04/26 : BAN BAK negosiaisi (400jt/thn), IW OG 01/04/26 : BAN BAK OG ( nego 250jt/10), IW OG 16/03/26 : Wait approved BAN BAK (250jt/10thn), lanjut IW 07/03/26 : Validasi OK Cand R 04/03/26 : Need Validasi Cand R 25/02/26: Need Validasi CAN R(106.85910 -6.17169) RT 7m + Monopole 20m 5. 13/01/26: Validasi NBAE NOK (CAN Q) rehunting 4. 31.12 Need Validasi CAN Q ( 106.85847 -6.17178) GF 30m, CAN P cancel penolakan istri LL 3. 25.12 Need Validasi CAN P ( 106.85847 -6.17178) GF 30m 2. Validasi NBAE OK : 23/12/2025 ( Cand P : -6.17154,106.85910) 1. 18.12 Need Validasi CAN P ( 106.85910 -6.17154) RT 7m + Stacking 6m + Pole 12m | Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | BAN : 10/4/26 IW : 1/4/26 | Apr | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | BTR | 200m arah 90 degree | 106.8585 | -6.1716 |  | 106.8591 | -6.1717 | Jl Cempaka Sari I No 4 RT 005/06 Kel Cempaka Baru Kec Kemayoran Jakarta Pusat | RT 12m + Pole 9m = 21m | Fasum |  | BTR |  |  | Rooftop stacking | Pole | Stacking Pole | 3 | 5 | 8 |  | BTR
237 | Area 2 | JKP233 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0032 | JKP233 | CEMPAKAPUTIHRAYADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | Jovis | 22/04/26 : Plan Jovis, koordinasi dengan pak Arizal, submit foto2 lau out, mitra koordinasi dgn PEMDA ttg utility yg ada di bawah pole eksisting 08/04/26 : Mitra akan mencari informasi ke PEMDA terkait utility yg ada di bawah pole eksisting 01/04/26 : Extend MP 6 m, jovis dgn MK mengecek utilitas yg ada di bawah MP eksisting 6/4/26 04/03/26 : Plan extend MP eksisting 25/02/26: Rehunting Hardsitac di CAN Q ,plan proposed extend 6m site eksisting 4. 13/01/26: Validasi NBAE OK (can Q) lanjut BAN/BAK (500jt/thn) paralel rehunting 3. 29.12 Need Validasi CAN Q (106.86824 -6.17599) GF 30m 2. BAN BAK 1. Validasi NBAE OK : 18/12/2025 (Cand P : -6.17604,106.86834) | Optimis | 2026-03-20 | 1. 18.12 BAN/BAK OG | Info : 13/4/26 Survey : 6/4/26 | Apr | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | BTR | 150m arah 90 degree | 106.8679 | -6.1762 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | trotoar | Tubular | Flenge luar | 1.5 | 1.5 | 3 |  | BTR
70 | Area 2 | JKP368 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 25TS08N2032 | JKP368 | MASJIDALBINAGBK | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Lock Trial |  |  |  | NY | NY | Lock Trial | Locktrial | 106.8024 | -6.2221 |  |  |  |  | Monopole 25 1Leg |  |  | BTR | [9 empty] | Lock Trial
449 | Area 2 | JKP370 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0108 | JKP370 | PARKIRTIMURGBK | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | PKS | 22/04/26 : Menunggu jawaban management GBK 01/4/26 : Remind menunggu jawaban management GBK, surat penawaran DMT sudah disubmit 16/3/26: Menunggu jawaban management GBK, surat penawaran DMT sudah disubmit 25/02/26: Proses negosiasi DMT dan GBK OG 28/01/26 : Proses negosiasi DMT dan GBK OG 05/01/26 : Permit hold by GBK (OG Proses negosiasi DMT&GBK) SIK masih belum rilis, koordinasi dgn pak Riza untuk rilis SIK | Optimis | 2026-01-29 | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Mar | PT ANUGERAH SELARAS RAYA | PT TRITECH CONSULT | Extend Pole | Extend 3m | 106.8066 | -6.2181 |  |  |  |  | Monopole 25 1Leg | Fasum |  | Extend 3m |  |  | lahan ok | Tubular | Flenge luar | 1.5 | 1.5 | 3 | Extend 3m OG | Extend 3m
71 | Area 2 | JKP371 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0106 | JKP371 | STADIONRENANGGBK | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | PKS | 22/04/26 : Menunggu jawaban management GBK 1/4/26: Menunggu jawaban management GBK, surat penawaran DMT sudah disubmit 16/3/26: Menunggu jawaban management GBK, surat penawaran DMT sudah disubmit 25/02/26: Proses negosiasi DMT dan GBK OG 28/1/26 : Proses negosiasi DMT dan GBK OG 05/01/26 : Permit hold by GBK (OG Proses negosiasi DMT&GBK) SIK masih belum rilis, koordinasi dgn pak Riza untuk rilis SIK | Optimis | 2026-01-29 | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Mar | PT ANUGERAH SELARAS RAYA | PT TRITECH CONSULT | Extend Pole | Extend 3m | 106.806 | -6.2159 |  |  |  |  | Monopole 25 1Leg | Fasum |  | Extend 3m |  |  | lahan ok | Tubular | Flenge luar | 1.5 | 1.5 | 3 | Extend 3m OG | Extend 3m
59 | Area 2 | JKP372 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0109 | JKP372 | PINTUUTARAGBK | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | PKS | 22/04/26 : Menunggu jawaban management GBK 1/4/26: Menunggu jawaban management GBK, surat penawaran DMT sudah disubmit 16/3/26: Menunggu jawaban management GBK, surat penawaran DMT sudah disubmit 25/02/26: Proses negosiasi DMT dan GBK OG 28/1/26 : Proses negosiasi DMT dan GBK OG 05/01/26 : Permit hold by GBK (OG Proses negosiasi DMT&GBK) SIK masih belum rilis, koordinasi dgn pak Riza untuk rilis SIK | Optimis | 2026-01-29 | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Mar | PT ANUGERAH SELARAS RAYA | PT TRITECH CONSULT | Extend Pole | Extend 3m | 106.8018 | -6.2156 |  |  |  |  | Monopole 25 1Leg | Fasum |  | Extend 3m |  |  | lahan ok | Tubular | Flenge luar | 1.5 | 1.5 | 3 | Extend 3m OG | Extend 3m
152 | Area 2 | JKP917 | Jabat |  | Non MKT | Non MKT |  | BTSH | NY | JKP917 | TAMANSUROPATIDMT | Plan ≤ 2025 | BTS HOTEL |  | 7. DROP | Drop | 7. DROP | Not Optimis | Drop | Propose Drop Terminate |  |  | NY | NY | Terminate |  | 106.8327 | -6.1984 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [9 empty] | Terminate
151 | Area 2 | JKP920 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 23TS03Z0022 | JKP920 | CITIWALKSUDIRMANDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 03/06/2024 | 0 | RFI | Done RFI | PT GEAF SOLUSIANDA PRATAMA | Waspang | BTR |  | 106.8176 | -6.2091 |  |  |  |  | Monopole 18 1Leg |  |  | BTR | [9 empty] | BTR
150 | Area 2 | JKP921 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 23TS03Z0019 | JKP921 | HALTESALEMBAUIDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 15/08/2023 | 0 | RFI | Done RFI | PT INFRAKO DAYAMITRA | Waspang | Contine with Macro |  | 106.8251 | -6.1832 |  |  |  |  | Monopole 18 1Leg |  |  | Contine with Macro | [9 empty] | Contine with Macro
149 | Area 2 | JKP922 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 23TS03Z0018 | JKP922 | JALANTEUKUUMARDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 13/10/2025 | 0 | RFI | Done RFI | PT INFRAKO DAYAMITRA | Waspang | Extend Pole |  | 106.8331 | -6.1898 |  |  |  |  | Monopole 18 1Leg |  |  | Extend 3m | [8 empty] | Extend 3m OG | Extend 3m
157 | Area 2 | JKP965 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 23TS03Z0016 | JKP965 | SIRIHRAYARAVINDOEMAC | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 11/05/2023 | 0 | RFI | Done RFI | PT INFRAKO DAYAMITRA | Waspang | Contine with Macro |  | 106.8251 | -6.1832 |  |  |  |  | Monopole 18 1Leg |  |  | Contine with Macro | [9 empty] | Contine with Macro
155 | Area 2 | JKP968 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 23TS03Z0023 | JKP968 | DIPONEGOROMENTENGDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 06/01/2025 | 0 | RFI | Done RFI | PT SUMBERSOLUSINDO HITECH | Waspang | BTR |  | 106.8413 | -6.2016 |  |  |  |  | Monopole 18 1Leg |  |  | BTR | [9 empty] | BTR
154 | Area 2 | JKS399 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 23TS03Z0020 | JKS399 | KNGNPRSDASPRBLOCKDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 20/04/2023 | 0 | RFI | Done RFI | PT SUMBERSOLUSINDO HITECH | Waspang | Contine with Macro |  | 106.8334 | -6.2097 |  |  |  |  | Monopole 20 1Leg |  |  | Contine with Macro | [9 empty] | Contine with Macro
97 | Area 2 | JKT411 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0449 | JKT411 | MSJDTAUBAHKOMPSNDNGDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 9. Propose Drop | Justifikasi Report | HARD SITAC ISSUE,PROPOSE RETURN | Optimis | 2026-03-20 | 18.12.GAGAL IW ,12.12 ada penolakan dari warga terkait extend tower, BTR hard kandidat, proposed drop 4.12 waiting nilai kompensasi pihak DKM (high price), Waiting Approval nilai | DROP |  | PT CIPTA KARSA ANUGERAH SEMESTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 106.91 | -6.2142 |  |  |  |  | Monopole 18 1Leg |  |  | Extend 3m | [8 empty] | Extend 3m OG | Extend 3m
65 | Area 2 | JKT412 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 25TS11B0014 | JKT412 | BLOKBERAMASDMT | Plan ≤ 2025 | Rescoping tambahan WO | Tracker Project DMT_TSEL | 7. DROP | DROP | HARD CANDIDAT Propose DROP | Not Optimis | 2026-01-10 | Propose Drop Terminate |  | DROP | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | Terminate |  | 106.9465 | -6.2042 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [8 empty] | Terminate | Terminate
99 | Area 2 | JKT414 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0446 | JKT414 | INSPEKSIKALIMALANGDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 09/01/2025 | 0 | RFI | Done RFI | PT SINERGI REKTA DENTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 106.8987 | -6.2436 |  |  |  |  | Monopole 18 1Leg |  |  | BTR | [9 empty] | BTR
271 | Area 2 | JTX452 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0040 | JTX452 | LAPANGANGOLFCILANGKAPDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Rehunting | 08.04 : Rehunting Cand, Hari Ini Submit Data Teknis 16.03 : Datek Baru Submit Malam Ini, Need Validasi Cand (-6.31523 ; 106.8898) 21.01 : Kandidat P NOK 12.01 : Need Validasi Cand P (-6.31855 ; 106.8912) 11.01 : OG Submit Validasi Cand, Menunggu Konfirmasi Dari Manajemen Korea School Terkait Lahan Yang Bisa Disewakan 07/01: Plan submit Datek 07/01 25.02 : Kandidat sudah ada, tinggal menunggu ketua yayasan | Not Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-25 | Mei | PT DESATRIA ALARD MANDIRI | PT MULTI BMITRA SEJAHTERA | BTR | 200m arah 90 degree | 106.8916 | -6.3169 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Didin | 085286733390 |  | Tubular | Flange Luar | 1.5 | 1.5 | 3 | Propose BTR Utara (106.889183° -6.315678°) | BTR
66 | Area 2 | JKT424 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0441 | JKT424 | PERUMNASSUMARNODMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Drop | 18/12/2025 TERMINATE | Not Optimis | 2026-02-14 | Propose Drop Terminate |  | DROP | PT SINERGI REKTA DENTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Terminate |  | 106.9505 | -6.2101 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [9 empty] | Terminate
67 | Area 2 | JKT430 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0447 | JKT430 | TOLCAKUNGUTARADMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Justifikasi Report | 20/11 : Sinergi submit BAN/BAK (325jt/10th) | Not Optimis | 2026-02-14 | Propose Drop Terminate |  |  | PT SINERGI REKTA DENTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Terminate |  | 106.9425 | -6.1736 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [8 empty] | Terminate | Terminate
147 | Area 2 | JKT433 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0407 | JKT433 | GANGSADARDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Drop | 19/11 : Need Validation cand. B (-6.30311 106.91530) | Not Optimis | Drop | Propose Drop Terminate |  | DROP | PT SINERGI REKTA DENTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Terminate |  | 106.9398 | -6.2124 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [9 empty] | Terminate
98 | Area 2 | JKT435 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0448 | JKT435 | PSRKLENDERNGURAHRAIDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 9. Propose Drop | Justifikasi Report | PROPOSE DROP > 18.12.2025 (Legalitas LL sertifikat tidak ada yang asli) | Optimis | 2026-02-14 | 18.12 GAGAL LL, 12.12 IW OG 4.12 issue permintaan warga penambahan kompensasi 20 jt | PROPOSE DROP |  | PT CIPTA KARSA ANUGERAH SEMESTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 106.905 | -6.2134 |  |  |  |  | Monopole 18 1Leg |  |  | Extend 3m | [8 empty] | Extend 3m OG | Extend 3m
96 | Area 2 | JKT680 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0455 | JKT680 | RSISLAMPDKOPIDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Justifikasi Report | HARD CANDIDAT Propose DROP | Not Optimis | 2026-02-13 | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial |  |  | PT CIPTA KARSA ANUGERAH SEMESTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Lock Trial |  | 106.9417 | -6.2214 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [9 empty] | Lock Trial
313 | Area 2 | JTX497 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0066 | JTX497 | JLGORDACIPAYUNGDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK | 08.04 : IW OG 3 Orang (13/04), Kalo IW Fail Proposed Extend 6 m 16.03 : BAN/BAK 30 Jt/Tahun, IW OG (Plan Extend 6 m) 19.01 : High Price, Permintaan LL Over 100 Juta/Tahun (OG Negosiasi Nilai Maksimal) 13.01 : Validasi OK, BAN/BAK OG 12.01 : Need Validasi Cand P (-6.29383 ; 106.8962) 25.02 : OG IW | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 15/05/05/2026 | Mei | PT DESATRIA ALARD MANDIRI | PT MULTI BMITRA SEJAHTERA | BTR | 100 degree arah 70m | 106.8963 | -6.2943 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Didin | 085286733390 | Lahan Cukup Untuk Extend | Tubular | Flange Luar | 1.5 | 1.5 | 3 |  | BTR
69 | Area 2 | JKU199 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0451 | JKU199 | HOTELDANAUSUNTERDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 9. Propose Drop | IW OG | 25/02/26: 5/1/2026 Proses IW IW PROSES (POLE ROOFTOP 6 METER + 24 METER) | Optimis | 2026-02-28 | 4.12 proses negosiasi harga sewa pertahun 100 jt/thn untuk sewa per 5 tahun, Waiting Approval nilai | W8 2026 | Apr | PT DENTRA MITRA ABADI | PT ATRYA REKAYASA | BTR |  | 106.8789 | -6.1466 |  |  |  |  | Monopole 15 1Leg |  |  | BTR | [9 empty] | BTR
172 | Area 2 | JKU249 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0114 | JKU249 | PLUITKARANGAYU1DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | Rehunting | 22/04/26 : Rehunting, submit datek 24/4/26 08/04/26 : Waiting approval BAN(50jt/th), IW OG (pemilik tidak di tempat, ruko kosong), paralel Rehunting 1/4/26: Waiting approval BAN(50jt/th) 16/3/26: Waiting approval BAN, IW OG 04/03/26 : Waiting approval BAN (50jt/thn) 25/02/26 : waiting approval BAN/BAK 50jt/thn site eksisting extend 6m 6. 26/01/26 : Need Validasi, BAN 35jt/th, IW OG 5. BAN/BAK OG (60jt/tahun), segera di submit ke mitratel 4. 31/12/12025 Validasi NBAE OK (Cand P : -6.1123,106.78415) 3. 23.12 Need Validasi CAN P ( 106.78415 -6.11230) RT 13m + 12m 2. 26/11 : CAND C IW kurang 2 (corporate) meminta surat pemebritahuan secara tertulis, target 1. 29/11/2025, cand D (hotel Prima) blm ada jawaban dari pihak MB hotel | Optimis | 2026-03-20 | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Rehunting : 13/4/26 | Apr | PT SUMBERSOLUSINDO HITECH | PT TRITECH CONSULT | BTR |  | 106.7832 | -6.1123 |  | 106.7841 | -6.1123 |  | Monopole 20 1Leg | Fasum | extend 6m | extend 6m |  |  | Trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 |  | BTR
101 | Area 2 | JKU760 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0442 | JKU760 | PLUITUTARARAYADMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | LOCK TRIAL | 06.01 Proposed Drop 5/1/2026 Extend 3M, HOLD 1. HOLD : STATUS LOCK TRIAL | Not Optimis | 2025-12-28 | Arahan NBAE SAR 150m |  |  | PT AJIAN TRI SUKSES | PT ATRYA REKAYASA | Lock Trial |  | 106.7921 | -6.1122 |  |  |  |  | Monopole 18 1Leg |  |  | BTR | [9 empty] | Lock Trial
187 | Area 2 | JKU792 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0033 | JKU792 | ASRAMAHDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | Rekom Done | 27/04/26 : Pengurusan rekom zona, plan skom 29/4/26, submit NOD 27/4/26 22/04/26 : Plan Skom 29/04/26 08/04/26 : Soil test 9/4/26, Mitra akan mengajukan NOD 8/4/26 1/4/26: Rekom done, Soil test plan 4/4/26 16/3/26: Legalisir SKT sampe level Lurah, Paralel REkom Lurah dan Camat. PlanFU setelah masa lebaran (30/3/26) 04/03/26 : SKT finish 6/2/26 25/02/26: Proses SKT OG sudah di tahap Camat dan lurah plan terbit 27/02 7. 20/02/26 : pembuatan SKT dari kelurahan untuk pendampingan akta tanah LL, IW Done 7. 30/01/26 : Validasi OK Cand P 6. 27/1/26 : Need Validasi cand P (-6.13748 106.90347) 5. 26/01/26 : Hunting 4. 13/01/26: hunting OG 3. Site eksisting berupa tanah garapan, surat tanah tidak ada, paralel hunting cand P, plan submit datek 07.01.2026 2. Plan submit datek 31.12.2025 19/11 : Soswar OG, BAN 30jt, alternatif kandidat dihotel D'Prima, kandidat 2 | Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | RFI : 25 Mei 2026 RFI : W1 Mei 2026 4/30/2026 | Apr | PT SUMBERSOLUSINDO HITECH | PT TRITECH CONSULT | BTR |  | 106.9031 | -6.14 |  | 106.9035 | -6.1375 | Jl Durian RT 004/08 Kel Rawa Badak Selatan Kec Koja Jakarta Utara | Monopole 20 1Leg | Fasum | MP30m | BTR | 3x4 | 388888888.8889 | Trotoar(ada perkuatan eksisting) | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | MP 30 | BTR
102 | Area 2 | JKU832 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0443 | JKU832 | PLUITTIMURBARUDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | 06/03/2026, RFI 5/1/2026 Extend 3M, erection On going HARD CANDIDAT Propose DROP | Optimis | 2026-01-12 | 12.12 plan material done 14 Dec target RFI 28 Dec 04.12 proses pabrikasi, target RFI 28 Dec, Lanjut MCP, Proses Design dan Perijinan Pole Extend, drop by tsel, proses nego ke Tsel untuk proposed Extend 3m |  | Done RFI | PT DENTRA MITRA ABADI | PT ATRYA REKAYASA | Lock Trial |  | 106.7942 | -6.1207 |  |  |  |  | Monopole 18 1Leg |  |  | Extend 3m | [9 empty] | Extend 3m
103 | Area 2 | JKU858 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0444 | JKU858 | PLUITKARANGBARATDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | Justifikasi Report | 5/1/2026 HOLD Cancel extend 3m (need 6m) | Optimis | 2025-12-28 | 12.12 plan material done 14 Dec target RFI 28 Dec 04.12 proses pabrikasi, target RFI 28 Dec, Lanjut MCP, Proses Design dan Perijinan Pole Extend | PROPOSE DROP |  | PT DENTRA MITRA ABADI | PT ATRYA REKAYASA | Contine with Macro |  | 106.7768 | -6.1139 |  |  |  |  | Monopole 18 1Leg |  |  | Extend 3m | [8 empty] | Extend 3m OG | Extend 3m
144 | Area 2 | JKU900 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0410 | JKU900 | SUNTERJAYATIMURDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Justifikasi Report | HARD CANDIDAT Propose DROP | Not Optimis | 2026-02-22 | 4.12 IW OG, hard sitac dan kandidat |  |  | PT DYEVA DIGITAL SELULAR | PT ATRYA REKAYASA | Lock Trial |  | 106.8778 | -6.1572 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
114 | Area 2 | JKU944 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0431 | JKU944 | MENARAMITRABAHARIDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | Justifikasi Report | HARD CANDIDAT Propose DROP | Not Optimis | 2026-02-13 | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial |  |  | PT NAER TUNAS INDONESIA | PT ATRYA REKAYASA | Lock Trial |  | 106.8068 | -6.1281 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
169 | Area 2 | JKU954 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0088 | JKU954 | TELUKGONGSELATANFAJARDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN BAK OG | 22/04/26 : Wait approved BAN BAK (55jt) 08/04/26 : BAN BAK 55jt/tahun 01/04/26 : Issue High price 550/10th 16/3/26: Hihgprice 550/10th LL mendasarkan penawaran TP sebelumnya(Protel) mitra mengajukan skema /5th 10/03/26 : BAN 550jt/10tn masih proses Renego 04/03/26 : Validasi OK Cand R 25/02/26: Rehunting OG plan submit datek 27/02/26 03/02/26: Validasi NBAE NOK (Can R 106.78174 -6.14040) rehunting sesuai note 7. 26/01/26 : hunting, 20/01/26 Kunjungn GM Tsel, Datek OG 6. 19/1/26 : Need Validasi cand R (106.78174 -6.14040) RT 13 + Pole 12 5. 13/01/26: Submit datek menunggu konfirmasi LL calon kandidat 4. Plan submit datek cand P 06.01.2026 3. Plan submit datek 31.12.2025 2. 23.12 : Hunting OG, proposed lahan kosong seberang eksisting 1. 01/12 : IW OG, RT menyarankan 4 warga di masukkan dalam IW (sebelumnya sudah termasuk LL), 2 Corp. masih review management | Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT SUMBERSOLUSINDO HITECH | PT TRITECH CONSULT | BTR |  | 106.7831 | -6.1414 |  | 106.7817 | -6.1404 | Taman permata indah blok. PB 9 RW. 7 kel. Pejagalan kec. Penjaringan, Jakarta utara. | Monopole 20 1Leg | Fasum | MP30m | BTR | 3x4 | 611111111.1111 | Trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | MP 30m Lanjut BTR (106.781740° -6.140400°) CAN R Ok | BTR
110 | Area 2 | JKU959 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0435 | JKU959 | PASARIKANMUARAANGKEDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI Done | Optimis | RFI : 14/05/2025 | 0 | RFI | Done RFI | PT NAER TUNAS INDONESIA | PT ATRYA REKAYASA | BTR |  | 106.7746 | -6.106 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
111 | Area 2 | JKU962 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0432 | JKU962 | PERUMMUARAANGKEDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Justifikasi Report | 5/1/2026 HARD CANDIDAT Proposed DROP 1. 23.12 : Rehunting karena site eksisting ada issue warga, plan 30.12.2025 | Not Optimis | 2026-02-14 | 4.12 lahan pemda, ijin dari pemda tdk released, existing monopole 18m extend jadi 32m, proposed drop, hard sitac dan kandidat | W5 2026 | Apr | PT NAER TUNAS INDONESIA | PT ATRYA REKAYASA | BTR |  | 106.768 | -6.107 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate |  |  | Trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | TBD 2 week | HOLD By Tsel (Propose DROP)
107 | Area 2 | JKU977 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0438 | JKU977 | TELUKNIBUNGDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Drop | 1. HOLD : STATUS TERMINATE | Not Optimis | Drop | Propose Drop Terminate |  | DROP | PT AJIAN TRI SUKSES | PT ATRYA REKAYASA | Terminate |  | 106.7747 | -6.1274 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Terminate
116 | Area 2 | JPX005 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0428 | JPX005 | KEBONKACANG4DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Justifikasi Report | 5/1/2025 Hold Cancel extend 3m | Not Optimis | 2025-12-28 | 12.12 Permintaan Tsel extend 6m, need konfirmasi ke Soleng, pabrikasi done untuk extend dan STR 3m, hard kandidat untuk BTR 4.12 erection OG, Target RFI 14 dec | DROP |  | PT ANUGERAH SELARAS RAYA | PT ATRYA REKAYASA | Extend Pole |  | 106.8174 | -6.1891 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [9 empty] | Extend 3m
136 | Area 2 | JPX012 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0417 | JPX012 | SALEMBARESIDENCEDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | Justifikasi Report | HARD CANDIDAT Propose DROP | Not Optimis | Drop | 5.12 proses pabrikasi material extend, target RFI 20 Dec, lock trial, Tsel RFI di TP sebelah |  |  | PT ANUGERAH SELARAS RAYA | PT ATRYA REKAYASA | Lock Trial |  | 106.8544 | -6.196 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
117 | Area 2 | JPX017 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0453 | JPX017 | JALANCISADANECIKINIDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 4. CME | Erection OG | 21/04/26 : Pabrikasi done 23/4/26, Platform recti sudah di instal 5/1/2026 Extend 6M,Plan erection tgl 9/1/2025 menunggu selesai tim dr tanahtinggi PROPOSE DROP > 18.12.2025 (tidak bisa extend 6m) hanya bisa 3m | Optimis | 2026-01-19 | 12.12 plan pabrikasi done week 3 Dec, Target RFI 28 Dec 4.12 pabrikasi OG | 2026-05-03 | Mar | PT ANUGERAH SELARAS RAYA | PT ATRYA REKAYASA | Extend Pole |  | 106.8427 | -6.1945 |  |  |  |  | Monopole 18 1Leg |  |  | Extend 6m | [8 empty] | Extend 6m | Extend 6m
120 | Area 2 | JPX028 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0429 | JPX028 | TANAHTINGGIDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | 30/01/2026 RFI notice OG 5/1/2026 Extend 3M ,PBG sdh done, erection on going Erection OG | Optimis | 2026-01-12 | 10.12 plan erection 16 Dec, Target RFI 20 dec | W4 DESEMBER 2025 | Done RFI | PT ANUGERAH SELARAS RAYA | PT ATRYA REKAYASA | Extend Pole |  | 106.8462 | -6.179 |  |  |  |  | Monopole 18 1Leg |  |  | Extend 3m | [8 empty] | Extend 3m OG | Extend 3m
126 | Area 2 | JPX029 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0423 | JPX029 | JALANBAKTIDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | Lock Trial | HARD CANDIDAT Propose DROP | Not Optimis | 2026-02-13 | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial |  |  | PT ANUGERAH SELARAS RAYA | PT ATRYA REKAYASA | Lock Trial |  | 106.8063 | -6.2013 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
145 | Area 2 | JPX041 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0409 | JPX041 | BENHIL15 | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | Lock Trial | HARD CANDIDAT Propose DROP | Not Optimis | 2026-02-13 | 4.12 IW OG |  |  | PT ANUGERAH SELARAS RAYA | PT ATRYA REKAYASA | Lock Trial |  | 106.8117 | -6.2144 |  |  |  |  | Monopole 18 1Leg |  |  | BTR | [9 empty] | Lock Trial
137 | Area 2 | JPX048 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0415 | JPX048 | KEBONSAYURMELATIDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | Lock Trial | HARD CANDIDAT Propose DROP | Not Optimis | 2026-02-13 | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial |  |  | PT ANUGERAH SELARAS RAYA | PT ATRYA REKAYASA | Lock Trial |  | 106.8187 | -6.2006 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
499 | Area 2 | JPX050 | Jabat |  | Non MKT | Non MKT | #N/A | BTSH | NY | JPX050 | PROKLAMASICIKINIDMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | Drop | DROP | Not Optimis | Drop | #N/A | DROP |  | NY | NY | Terminate | Terminate (Dismantel Done) | 106.846 | -6.2003 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Terminate
138 | Area 2 | JPX062 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0416 | JPX062 | KEBONKACANG9DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 2. SITAC | IW OG | 21/04/26 : Pertemuan dengan RT/RW untuk audensi dengan lingkungan 07/01 Plan pembuatan JR untuk pengajuan extend SAR ke TSEL 1/5/2026 HARD CANDIDAT Proposed DROP PENDING 1 IW RADIUS TOWER, TARGET IW CLEAR 27 DESEMBER 2025 | Optimis | 2026-02-14 | 12.12 masih proses negosiasi 10.12 kandidat baru, proses BAN BAK, BTR | W3 May 2026 | Apr | PT ANUGERAH SELARAS RAYA | PT ATRYA REKAYASA | BTR |  | 106.8187 | -6.1921 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
189 | Area 2 | JPX071 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0121 | JPX071 | RELOCKEDUBESAUSTRIADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 0. ATP | ATP done | 22/04/26 : Plan ATP 10/04/26 : RFI Submitted 4/4/26 : ATP done 1/4/26: Erection OG 16/03/26 : Curing time done, erection malam 16/03/26 13/03/26 : Curing time hari ke-2 12/03/26 : Curing time hari ke-1 11/03/26 : Pengecoran site 10/03/26 : undangan pengecoran site 11 Mar 2026 04/03/26 : Galvanis OG 25/02/26: Proses pabrikasi material extend 3m (start pabrikasi 19/02/26) target finish 3/03/26 6. 04/02/26 : Proses kordinasi design extend tower ke bagian SOLENG 5. 22/01/26 : Proses Design Extend tower 3 meter - Done 4. 22/01/26 : Paralel proses kordinasi dengan dinas terakit penambahan ketinggian menara - Done 3. 22/01/26 : Menunggu review konsultan - Done 2. 22/01/26 : Proses survey Kand untuk Extend - Done 1. JOVIS Konsultan OG 05/01/2026 | Optimis | 2026-01-29 | Add 3 RF Add 9 RRU Final Sow Rescope: 3. reheight tower | W4 April 26 | Mar | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | Extend Pole |  | 106.8384 | -6.2011 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 3m |  |  | Taman | Tubular | Flenge Dalam | 1.5 | 1.5 | 3 | Extend 3m OG | Extend 3m
73 | Area 2 | JPX110 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0105 | JPX110 | MENTENGJAKPUSDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Proposed DROP | 22/04/26 : Submit JR 08/04/26 : Submit JR 01/04/26 : Hard cand, extend fail (lahan terbatas), Plan submit JR 16/03/26 : LL masih rembuk keluarga 04/03/26 : Hunting new cand(hardcandidat), plan extend MP eksisting, survey eksisting MP, plan Jovis 25/02/26: 09/10/26 : Ketua RT 06 setuju penambahan ketinggian pole 3 m dan memita soswar ke warga sekitar rebahan 05/01/26: plan submit datek 07/01/2026 Hunting, submit 31.12.2025 | Not Optimis | 2026-01-29 | Add 3 RF Add 6 RRU Final Sow Rescope: 3. reheight tower |  | Apr | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | Extend Pole | Extend 3m | 106.839 | -6.2033 |  |  |  |  | Monopole 20 1Leg | Fasum | MP20 extend 6m | Extend 3m |  |  | space lahan terbangun warung | Tubular | Flenge luar | 1.5 | 1.5 | 3 | Extend 3m OG | Extend 3m
199 | Area 2 | JPX133 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 25TS08N1993 | JPX133 | SEGITIGAPASARSENENDMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Lock Trial |  |  |  | NY | NY | Lock Trial |  | 106.841 | -6.1746 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
177 | Area 2 | JPX137 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0092 | JPX137 | DANAUTONDANODMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 22/04/26 : Reminder ke dispora 22/04/26 08/04/26 : Reminder jawaban dispora 8/4/26 01/04/26 : Reminder jawaban dinas Pemuda dan Olahraga mengenai sewa lahan 2/4/26 16/03/26 : BAN BAK OG 04/03/26 : submit datek cand R (-6.20720 106.80812), Need Validasi, Validasi OK Lanjut BAN 25/02/26: Rehunting , plan proposed extend 6m di eksisting 10/01/26 : Validari NOK, rehunting cand R Need Validation Cand Q ( -6.20732, 106.80718) Plan submit DATEK rehunting 07/01/2026 Validasi NBAE Not OK:31/12/2025 (rehunting as note) 24/12 Need Valisasi Cand P ( 106.80788 -6.20709) GF 25m | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Reminder : 8/4/26 Remider : 2/4/26 | Apr | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | BTR |  | 106.8085 | -6.2066 |  | 106.8081 | -6.2072 | JL. DANAU TONDANO GG. SEKOLAH RT. 020/RW.004 KEL. BENDUNGAN HILIR, KEC. TANAH ABANG, KOTA JAKARTA PUSAT, DKI JAKARTA | Monopole 20 1Leg | Fasum |  | BTR |  |  | trotoar | Tubular | Flenge luar | 1.5 | 1.5 | 3 | Lanjut BTR (106.80812 -6.20720) | BTR
91 | Area 2 | JPX144 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0116 | JPX144 | PASARBARUTIMURSAHARIDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 0. ATP | ATP Done | 05/05/26 : ATP Done 04/05/26 : Undangan ATP 04 Mei 2026 Pukul 14:00 25/04/26 : Pondasi maksimal di 120x100 cm, menunggu hasil analisa dari konsultan 22/04/26 : LL sudah OK mengenai lay out, menunggu ijin mulai kerja, koordinasi dgn pak Arizal 08/04/26 : LL pindah alamat (Season city), mitra akan mengirim ulang hasil analisa 07/04/26 : Hasil analisa sudah dikirim ke LL namun menurut info, LL belum menerima, sehingga akan dilakukan pengiriman ulang 01/04/26 : Reminder jawaban LL mengenai analisa gedung dan perijinan 16/03/26 : Menunggu jawaban LL perihal hasil analisa gedung dan perijinan 04/03/26 : Menunggu jawaban LL perihal analisa gedung dan perijinan (surat dari DMT ke LL) 25/02/26: Menunggu data analisa gedung sesuai permintaan LL (LLRuko), Relok MT Rooftop 4lt 10/01/26: PKS OG, IW paralel 09/01/26 : Negoisasi Sewa Lahan by DMT Done, proses PKS OG, pararel Joint survey by DMT 05/01/26 : Negosiasi perpanjangan site Menunggu pertemuan LL plan 07/01/2026 Negosiasi perpanjangan site eksisting | Optimis | 2025-12-28 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | info dari pak Arizal : 22/4/26 Info LL : 10/4/26 Reminder : 2/4/26 | Mar | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | Reloc to existing MTEL |  | 106.838 | -6.1622 |  |  |  |  | Monopole 20 1Leg | Privat | RT 16m + Pole 15m = 31m | Reloc Tower DMT |  |  | trotoar | Tubular | Flenge luar | 1.5 | 1.5 | 3 |  | Reloc to existing MTEL
185 | Area 2 | JPX146 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 25TS08N2016 | JPX146 | PASARSENENIMPRESSDMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Lock Trial |  |  |  | NY | NY | Lock Trial |  | 106.8384 | -6.174 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
371 | Area 2 | JPX149 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0103 | JPX149 | KALIBARUBARATDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | Site Opening | 05/05/26 : Revisi dokumen BAN BAK, 22/04/26 : Menunggu DP lahan 08/04/26 : Menunggu dp lahan, pabrikasi OG 1/4/26: SKOM done, Implementasi menunggu DP | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | W1 Juni 2026 | Apr | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | BTR |  | 106.8428 | -6.1704 |  | 106.8438 | -6.1704 | Jln. Bungur Besar Raya No. 131 RT01/01, Kel. Kemayoran , Kec. Bungur Jakarta Pusat | Monopole 20 1Leg | Fasum | Pole 12 M | BTR |  | 130000000 | trotoar | Tubular | Flenge luar | 1.5 | 1.5 | 3 |  | BTR
367 | Area 2 | JPX152 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JPX152 | CIMAHIMENTENGDMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial |  | 106.8301 | -6.2032 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
175 | Area 2 | JPX153 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0093 | JPX153 | SDKENARIDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 9. Propose Drop | Proposed DROP | 22/04/26 : Drop 08/04/26 : Drop 01/04/26 : Proposed drop 16/03/26 : Submitted JR 01/03/26 : Mitra Submit JR 25/02/26:Rehunting issue hard candidat paralel pembuatan JR, paralel proposed extend 6M site eksisting 8. 09/02/26 : Validasi OK Cand R 7. 22/01/26 : Kand R LL berminat, namun akan musyawarah dengan keluarga., LL adalah Pak RW setempat 6. 22/01/26 : Kand Q LL tidak jadi menyewakan, Reunting Kand R done, Proses validasi 5. 14/01/26: Validasi NBAE OK (Can B) Lanjut BAN/BAK 4. 05.01 Need Validasi CAN B ( 106.84358 -6.18525) GF 32m CAN A drop by LL 3. Validasi NBAE OK : 29/12/2025 (Cand A : -6.18536,106.84326) 1. 18.12 Need Validasi CAN A ( 106.84326 -6.18536) GF 32m 2. 18.12 Need Validasi CAN B ( 106.84358 -6.18525) GF 32m | Not Optimis | 2026-03-20 | Add 3 RF Add 7 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | BTR |  | 106.8434 | -6.1853 |  | 106.84326 | -6.18536 |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | trotoar | Tubular | Flenge luar | 1.5 | 1.5 | 3 |  | BTR
207 | Area 2 | JPX155 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0094 | JPX155 | JLPERNEGCEMPAKAPUTIHDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | JR | 22/04/26 : Proposed JR 08/04/26 : MK Review hasil Jovis 1/4/26: Ekstend NA, terkendala Perkuatan eksisting 16/03/26 : Submited JR, MK akan menanyakan ke DMT perihal ABD site eksisting 10/03/26 : Cek lokasi oleh mitra dan konsultan 04/03/26 : Plan extend 6m 01/03/26 : Mitra Submit JR 25/02/26:Rehunting issue hard candidat paralel pembuatan JR, paralel proposed extend 6M site eksisting 9. 13/02/26 : Validasi Cand B NOK (CAND dan NOM terlalu jauh) 8. 22/01/26 : Can B(106.86181,-6.18275) 32m LL bersedia disewakan dan akan bermusyawarah dengan keluarga. 7. 22/01/26 : Need validasi cand Q (106.86181 -6.18275) GF 32m, cand P batal by LL 6. 14/01/26: Need Validasi Can Q (106.86181 -6.18275) GF 32m, Can P drop by LL 5. 13/01/26 BAN/BAK OG waiting pertemuan LL 4.07/01;26: Validasi NBAE OK (Can A) lanjut BAN/BAK 3. 07/01/26: Need Validasi CAN A (106.86156 -6.19085) GF MP 32m: Can B(106.86181 -6.18275) GF 32m 2. Waiting JR untuk perubahan SAR terkait issue kandidat 1. 18.12 HARD CANDIDAT RADIUS SAR 200m masih punya PT GARAM | Optimis | 2026-03-20 | Add 3 RF Add 11 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | BTR |  | 106.8621 | -6.19 |  |  |  |  | Monopole 20 1Leg | Fasum | extend 6m | Extend 6m |  |  | trotoar (ada eksisting perkuatan & ring mounting) | Tubular | flenge Dalam | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
178 | Area 2 | JPX156 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JPX156 | KARETPSRBARUBARATDMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial |  | 106.8144 | -6.2094 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
135 | Area 2 | JPX157 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JPX157 | HONDAPECENONGANDALAMDMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.8249 | -6.1611 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
181 | Area 2 | JPX158 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | WO Proses | JPX158 | CEMPAKAPUTIHBRT2EDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Rehunting | Hunting | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | WO PROSES | WO PROSES | Extend 6m |  | 106.862 | -6.1762 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 6m | [8 empty] | Extend 6m | Extend 6m
192 | Area 2 | JPX163 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0097 | JPX163 | CEPMAKAPUTIHBARATDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 9. Propose Drop | Proposed DROP | 22/04/26 : Drop 08/04/26 : Drop 01/04/26 : Proposed drop 16/03/26 : Mitra submitted JR 01/03/26 : Mitra Submit JR 25/02/26:Rehunting issue hard candidat paralel pembuatan JR, paralel proposed extend 6M site eksisting 7. 23/02/26 : Validasi Cand Q NOK 6. 22/01/26 : Surat balasan terkait persetujuan sewa lahan 20/01, Haga sewa lahan 80jt/th , tinggi tower 42M, Waiting approval sewa lahan 5.13/01/26: Plan pertemuan management gedung 15/01/26 4. Perlu surat Pengajuan dari DMT ke ARCICI group 3. Validasi NBAE OK : 29/12/2025 (Cand A : -6.18212,106.86812) 1. 18.12 Need Validasi CAN A ( 106.86812 -6.18212) GF 32m 2. 18.12 Need Validasi CAN B ( 106.86827 -6.18340) GF 32m | Not Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | BTR |  | 106.8678 | -6.1827 |  | 106.86812 | -6.18212 |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | trotoar | Tubular | flenge Dalam | 1.5 | 1.5 | 3 |  | BTR
74 | Area 2 | JPX166 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 25TS03Z0004 | JPX166 | DUKUHPINGGIR5DMT | Plan ≥ 2026 | RESCOPING |  | 5. RFI | RFI | RFI (Solution Issue lahan eksisting sengketa Dengan Perusahaan GT) | Optimis | RFI : 15/05/2025 | site solution, sudah RFI, mitra solution, existing lahan sengketa (lahan fasum diakui lahan PT) need solution, on air | RFI | Done RFI | PT SINERGI REKTA DENTA | PT TUNAS GEOTEKNIK INDONESIA | Reloc to existing MTEL |  | 106.8146 | -6.198 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
196 | Area 2 | JPX167 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0101 | JPX167 | JLKARTINIPSBARUDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 9. Propose Drop | Proposed DROP | 08/04/26 : Drop 01/04/26 : Proposed drop 16/03/26 : Submit JR 04/03/26 : Mitra Submit JR, plan extend 6m tapi lahan tidak mencukupi 01/03/26 : Mitra Submit JR, 25/02/26:Rehunting issue hard candidat paralel pembuatan JR, paralel proposed extend 6M site eksisting 5. 12/02/26 : Validasi NOK Cand Q 4. 22/01/26 : Kand P LL tidak jadi menyewakan, Hunting Kand Q done, Proses validasi 3. BAN/BAK OG menunggu pertemuan LL 06/01/2026 2. Validasi NBAE OK:31/12/2025 (Cand P : -6.15205,106.83855) 1. 18.12 Need Validasi CAN A ( 106.83855 -6.152053) GF 32m | Not Optimis | 2026-03-20 | Add 3 RF Add 10 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | Extend 6m |  | 106.8385 | -6.1511 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 6m |  |  | trotoar | Tubular | Flenge luar | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
179 | Area 2 | JPX168 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0119 | JPX168 | KEPUDALAMDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | Pabrikasi OK | 22/04/26 : Koordinasi dgn PEMDA OG 08/04/26 : Koordinasi dgn PEMDA OG 1/4/26: koordinasi dgn PEMDA perihal ijin kerja 16/03/26 : Pabrikasi done, koordinasi dgn PEMDA perihal ijin kerja, pekerjaan akan di lanjutkan setelah hari Raya 04/03/26 : Galvanis OG 25/02/26: Proses pabrikasi material extend 3m (start pabrikasi 19/02/26) target finish 3/03/26 04/02/26 : Proses kordinasi design extend tower ke bagian SOLENG 22/01/26 : Proses Design Extend tower 3 meter Done 22/01/26 : Paralel proses kordinasi dengan dinas terakit penambahan ketinggian menara - Done 22/01/26 : Menunggu review konsultan - Done 22/01/26 : Proses survey Kand untuk Extend - Done JOVIS Konsultan OG 05/01/2026 | Optimis | 2026-01-29 | Add 3 RF Add 6 RRU Final Sow Rescope: 3. reheight tower | Koordinasi PEMDA : 11/0/4/26 | Mar | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | Extend Pole |  | 106.8441 | -6.162 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 3m |  |  | trotoar | Tubular | Flenge luar | 1.5 | 1.5 | 3 | Extend 3m OG | Extend 3m
77 | Area 2 | JPX169 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 25TS08N1781 | JPX169 | SIMPANGSENENRAYADMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Lock Trial |  |  |  | NY | NY | Lock Trial |  | 106.8368 | -6.171 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
557 | Area 2 | JPX172 | Jabat |  | Non MKT | Non MKT | #N/A | BTSH | NY | JPX172 | JLHAJIFACHRUDINDMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | Drop | DROP | Not Optimis | Drop | #N/A | DROP |  | NY | NY | Terminate |  | 106.8181 | -6.1836 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Terminate
213 | Area 2 | JPX173 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JPX173 | CPPUTIHTENGAH27A | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial |  | 106.8722 | -6.1742 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
287 | Area 2 | JPX178 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0111 | JPX178 | JLPERCETAKANNEGARADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | upgrade PLN NY | 29/04/26 : Mitra submit RFI Checklist 22/04/26 : Pending upgrade PLN, upgrade plan 23/04/26 1/4/26: CME OG, 16/3/26: CME OG, Target STR Done 18/3/26 10/03/26 : Plan MOS 13/3/26 25/02/26 : Plan MOS 26/02/26 23/02/26 : Start Pabrikasi Done 02/02/26 ¦ finish pabrikasi Done 11/02/26 ¦ finish galvanish done 23/02/26 ¦ plan pickup material 24/02/26 28/01/26 : APD OK, IW OK, plan pabrikasi 1/2/26 05/01/26 : Waiting APD plan 05/01/26 SIK survey perkuatan belum keluar 24/12/25 : IW Done 22/12/25 : Survey OG PLan submit Datek | Optimis | 2026-01-29 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-04-07 | Mar | PT ANUGERAH SELARAS RAYA | PT TRITECH CONSULT | Extend Pole | Extend 3m | 106.8566 | -6.1884 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 3m |  |  | trotoar(perkuatan eksisting) | Tubular | Flenge luar | 1.5 | 1.5 | 3 | Extend 3m OG | Extend 3m
318 | Area 2 | JPX184 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0078 | JPX184 | KOMPLEKDITJENDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | Rehunting | 22/04/26 : Submit JR 08/04/26 : Rehunting OG (lahan tidak bersertifikat) 06/04/26 : Rehunting OG 01/04/26 : IW fail (3 kk menolak), rehunting 16/03/26 : BAN/BAK 37jt/thn, submit BAN 16/03/26 13/03/26 : Cand Q OK, BAN BAK OG 04/03/26 : Need Validasi Cand Q dan R 07/01/26: Need Validation cand Q (-6.17051, 106.86203) dan R (-6.17064, 106.86199) submit datek 7/1/26 05/01/2025 BAN BAK masih terkendala LL diluar negeri 31/12/2025 BAN BAK masih terkendala LL diluar kota Validasi NBAE OK : 23/12/2025 (Cand P : -6.1711,106.86226) 18.12 Need Validasi CAN P (106.86226 -6.17110) RT 7m + Stacking 6m + Pole 12m | Not Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Rehuntuing : 13/4/26 Rehunting : 2/4/26 | Apr | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | BTR | BTR Arah 100m 110 degree | 106.8621 | -6.1702 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | lahan warga | Tubular | Flenge luar | 2 | 2 | 4 |  | BTR
249 | Area 2 | JPX186 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0019 | JPX186 | JLPSGEMBRONGDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 9. Propose Drop | Proposed DROP | 22/04/26 : Submit JR 08/04/26 : Proposed drop 01/04/26 : Proposed drop 16/03/26 : Mitra submit JR 04/03/26 : Hard candidate, plan JR 25/02/26: Rehunting (Can P Reject IW ) 6. 11/01/26 : IW OG, plan 15/1/26 done 5. 05/01/26: Submit BAN done, IW OG 4. 31/12/2025 : Menunggu sosialisasi RT radius terdampak 3. BAN BAK 2. Validasi NBAE OK : 23/12/2025 (Cand P : -6.18023,106.85412) 1. 18.12 Need Validasi CAN P ( 106.85412 -6.18023) RT 12m + pole 20m | Not Optimis | 2026-03-20 | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | JR : 13/4/26 | Apr | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | BTR | 100m arah barat ruko depan alfamart | 106.8546 | -6.1805 |  | 106.8541 | -6.1802 |  | RT 11m + Pole 9m = 20m | Fasum |  | BTR |  |  | Rooftop | Pole | Stacking Pole | 3 | 5 | 8 |  | BTR
257 | Area 2 | JPX187 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0016 | JPX187 | JLLUMBALUMBADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Proposed DROP | 22/04/26 : Submit JR 08/04/26 : Proposed drop 01/04/26 : Plan submit JR 16/03/26 : Lahan terbatas 10/03/26 Mitra koordinasi dgn LL, pengecekan surat2 tanah 07/03/26 : Validasi NOK Cand R 04/03/26 : Need validasi cand R 25/02/26: Need Validasi CAN R (106.86383 -6.16678) RT 7m + Monopole 20m 3. 13/01/26: Validasi NBAE NOK (CAN Q) rehunting 2. 21/12 Need Validasi Cand Q (106.86563 -6.16690) GF 32M 1. Validasi NBAE OK : 18/12/2025 (Cand P : -6.16732,106.86473) | Not Optimis | 2026-03-20 | 1. 18.12 BAN/BAK OG | JR : 13/4/26 Submit JR : 6/4/26 | Apr | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | Extend 6m | BTR lapangan | 106.8648 | -6.1673 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 6m |  |  | lahan warga | Tubular | Flenge luar | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
247 | Area 2 | JPX188 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0060 | JPX188 | JALANWAHIDHASYIMDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 0. ATP | ATP OK | 10/03/26 : ATP 10/3/26 04/03/26 : STR done 4/3/26 02/03/26 : STR OG 07/02/26 : MOS 25/02/26: Survey pra Implementasi untuk penentuan jadwal SKOM, Pabrikasi done 17/02/26 26/1/26 : Pabrikasi OG 05/01/2026: negosiasi Perpanjangan PKS OG, APD Done plan submit 05/01/2026 APD menunggu approved Soleng Negosiasi Perpanjangan PKS | Optimis | 2025-12-28 | [30/10/25] Plan Eksekusi W4 Nov [9/09/25] Proses Fabrikan Ring mounting + Rack Gendong + Bracket Panel KWH + ACPDB [20/07/2025] Submit Dok.RFIN done | ATP OK | Done RFI | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | Reloc to existing MTEL | Reloc Ke Tower terdekat Need Panoramic site terdekat 16HC09W0004 Wahid Hasyim('106.81996 '-6.18664) | 106.8195 | -6.1871 |  |  |  |  | Monopole 20 1Leg | Privat | RT 15m + Pole 15m = 30m | Reloc Tower DMT |  |  | trotoar | Tubular | Flenge luar | 1.5 | 1.5 | 3 |  | Reloc to existing MTEL
100 | Area 2 | JPX190 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JPX190 | JLNASIONALDMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.7959 | -6.2107 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
288 | Area 2 | JPX193 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JPX193 | KRAMATLIMADMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Done DRM | 106.8438 | -6.1881 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
270 | Area 2 | JPX199 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JPX199 | UTANPANJANGDMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.8514 | -6.1596 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
272 | Area 2 | JPX211 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0104 | JPX211 | JLKEBONSIRIHMENTENGDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Validasi OG | 22/04/26 : Need validasi, BAN sudah submit 01/04/26 : Need Validasi ( Paralel proses BAN) 16/03/26 : Need Validasi CAN Q (-6.18476 106.82787) RT 12+ Pole 15m 10/03/26 : Extend 6m cancel, LL tidak mau perpanjangan sewa, Need Validasi Cand Q (-6.18476,106.82787) 25/02/26 : Menunggu jadwal Jovis dari TSEL 28/01/26 : Plan JOVIS 6/2/26 13/01/26 : Validasi NBAE NOK (Can P), proposed extend eksisting 6m 09/01/26 : Submit datek cand Q (-6.18476 106.82787) need validation 01/01/26 : Need Validasi CAN P (106.82762 -6.18379) RT 10m + 25m Plan submit datek cand. P, 31.12.2025 22/12/26 : Extend NA, Rehunting OG | Optimis | 2026-01-29 | Add 3 RF Add 5 RRU Final Sow Rescope: 3. reheight tower |  | Apr | PT ANUGERAH SELARAS RAYA | PT TRITECH CONSULT | Extend Pole | Extend Pole 10m (Need Survey dan cek pondasi pole) | 106.8276 | -6.1848 |  |  |  |  | RT 14m + Pole 6m = 20m | Privat | RT 12m + pole 18 | Extend 6m | 4x5 | 733333333.3333 | Rooftop | Pole | Stacking Pole | 3 | 5 | 8 | RT 12m + pole 18m | Extend 6m
308 | Area 2 | JPX235 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0059 | JPX235 | JLPENJERNIHAN2DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 9. Propose Drop | Proposed DROP | 22/04/26 : Submit JR 08/04/26 : Proposed drop 01/04/26 : Proposed drop, plan submit JR 6/4/26 16/03/26 : Hunting 10/03/26 : Re-hunting new cand, extend 6m not possible(space issue) 04/03/26 : Hunting new cand OG, optional extend MP eksisting 25/02/26: Rehunting OG, paralel plan extend 6m (survey lahan eksisting) 4. 30/01/26 : Validasi NOK Cand A 3. 20/01/26 : Need Validasi cand A (-6.20509,106.80933) 2. 05/01/26: Plan submit datek 07/01/2026, issue kawasan padat 1. Hunting, submit 31.12.2025 | NOT Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | JR : 13/4/26 Submit JR : 6/4/26 | Apr | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | Extend 6m | BTR Arah 50m 230 degree | 106.8082 | -6.2035 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 6m |  |  | trotoar | Tubular | Flenge luar | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
325 | Area 2 | JSA010 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0058 | JSA010 | TEGALPARANGUTRDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW OG | 22/04/26 : Putusan DKM 24/04/26, bila tidak sepakat akan di pindah lokasinya 08/04/26 : Keputusan DKM 16/4/26, paralel submit datek 01/04/26 : Plan pertemuan DKM 3/4/26, 16/03/26 : Menunggu keputusan DKM mesjid As Sa'adah, mitra submit datek cand S 04/03/26 : FU DKM As Saadah 6/3/26, paralel rehunting 25/02/26 : Menunggu konfirmasi DKM 6. 18/02/26 : Validasi OK Cand R (-6.24500,106.83470) 5. 02/02/26 : Need Validasi Cand R ( -6.24500,106.83470) Mesjid ASSaadah 4. 20/01/26 : Gagal IW ( ada beberapa warga menolak ) plan hari ini rehunting 3. BAN / BAK OG (issue kesepakatan keluarga LL) 2. Validasi NBAE OK 23-12-2025 (Cand P : -6.24449,106.83365) 1. 22.12 Need Validasi CAN P ( 106.83365 -6.24449 ) GF 30m Proposed MT | Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | DKM : 16/4/26 | Apr | PT CELEBES KONTRUKSINDO | PT TRITECH CONSULT | BTR | BTR Arah 80m 200 degree | 106.8336 | -6.2444 |  | 106.8337 | -6.24449 | Jl. Tegal Parang Utara III RT.007 RW 004, Kel. Mampang Perapatan. Kec. Mampang | Monopole 20 1Leg | Fasum | MP30 | BTR |  |  | Lahan berpagar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 |  | BTR
314 | Area 2 | JTX498 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0071 | JTX498 | PULOMERSKTAMANSARIDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Rehunting | 08.04 : Need Join Survey Dengan TSEL, Hard Cand 16.03 : Hard Cand Hard Sitac, Need Remap (Not Optimis) 11.01 : Lahan Eksisting & Lahan Sekitar Eksisting Warga Issue (Penolakan Pembangunan Tower), BA Lapangan Penolakan Dari Sekertaris RT OG Create | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Hard Cand | Apr | PT DESATRIA ALARD MANDIRI | PT MULTI BMITRA SEJAHTERA | BTR | BTR Arah 170m 50 degree | 106.8827 | -6.3559 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 6m | Didin | 085286733390 | Lahan Cukup Untuk Extend | Tubular | Flange Luar | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
316 | Area 2 | JSA015 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0055 | JSA015 | JLDAMAIRAYA8DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 3. RFC | APD OK | 30/04/26 : APD Done.. Menunggu dari DMT NOD pole 30 Std Baru (Resquest sudah diajukan) 29/04/26 : Waitung info NOD 22/04/26 : APD OK, pra SKOM 23/04/26, mitra submit nod 23/4/26 08/04/26 : APD review by MK, menunggu informasi hasil pertemuan dgn DKM di sampaikan 08/04/26 01/04/26 : Plan pertemuan dgn DKM 4/4/26 (negosisasi) 30/03/26 : APD OG (submitted to sol eng 18/3/26), DKM minta approval harga sebelum IW 16/03/26 : APD OG (target 18/03/26) 08/03/26 : IW Done, Rekom OG, Soiltest 11 Mar 2026 25/2/26 : Need approved BAN BAK (35jt/thn), IW menunggu BAN 13/01/26 : Validasi Cand P OK, BAN OG 35jt/thn & IW OG ( dari pihak DKM minta approval harga sebelum di lakukan IW) 13/01/26 : Validasi OK 22/12/25 : Need Validasi CAN A ( 106.75312 -6.24881) GF 25m | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | RFI : 25/5/26 APD : 02/04/26 | Apr | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | BTR | BTR Arah 100m 260 Degree | 106.7533 | -6.2489 |  | 106.7531 | -6.2488 | Jl. Damai Raya RT 004/008,Kel. Petukangan, Kec. Pesanggrahan ,Jakarta selatan | Monopole 20 1Leg | Fasum | MP 30 | BTR | 4x4 | 500000000 | Lahan berpagar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 |  | BTR
307 | Area 2 | JSA024 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0057 | JSA024 | ULUJAMIPERDATAMDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN BAK OG | 27/04/26 : Need Approval permintaan warga (5jt) dan LSM(25jt) 22/04/26 : Wait approved BAN BAK (45jt/thn) 08/04/26 : Need Approved BAN BAK (45jt/thn) 01/04/26 : Need Approval BAN(45jt) IW done, Proses nego kompensasi, Dok Sitac sudah disubmit 16/03/26 : Surat Jaminan rilis 16/3/26, plan 17/3/26 janjian dgn warga yg bersangkutan (1kk) 13/03/26 : Mitra submit surat pernyataan jaminan 12/03/26 : Request surat jaminan ada permintaan khusus batas lahan, alamat rumah dicantumkan 04/03/26 : IW Plan 6/3/26 finish, kurang 3kk dari 15 kk, need BAN (45jt/th) 25/02/26: IW OG (sisa 4 dari 15) target done 28/2/26 23/02/26 : IW OG 7/15 (beberapa warga meminta surat jaminan asuransi) 20/02/26 : IW OG 09/02/26 : BAN/BAK 45jt/thn 03/02/26: Validasi NBAE OK ( Can Q 106.76500 -6.24169) Lanjut BAN/BAK 20/01/26 : Validasi OG can Q(106.76500 -6.24169) GF 32m 19/01/26: Need Validasi CAN Q(106.76500 -6.24169) GF 32m 06/01/26 : Validasi NOK, rehunting cand Q 05/01/26: Need Validasi CAN P (106.76440 -6.24025) GF 32m 05/01/26: Rehunting OG plan submit Date 06/01/26 Proses rehunting issue space lahan minim di sekitar SAR | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT VALUE TELECOMMUNICATION | PT TRITECH CONSULT | BTR | BTR Arah 100m 270 Degree | 106.7649 | -6.2416 |  | 106.765 | -6.2417 | GS Preatige Ulujami Jl. Perdatam VIII No.11 RT.006 RW.005 Kelurahan Ulujami Kecamatan Pesanggrahan Kota Jakarta Selatan Provinsi DKI Jakarta | Monopole 20 1Leg | Fasum | MP 30M | BTR | 3x3 | 500000000 | Lahan berpagar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | MP 30m | BTR
322 | Area 2 | JSA033 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0054 | JSA033 | JLKENCANAINDAHDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG IW Done | 22/04/26 : Wait approved BAN BAK (45jt/thn) 08/04/26 : Verifikasi ke site 11/4/26, high capex 01/04/26 : Plan 4/4/26 re-negosiasi ulang bersama DMT (45jt/thn), IW radius tower done 30/03/26 : Wait approved BAN BAK (45jt/thn), mitra submit softcopy lsg ke pak Ihsan 16/03/26 : Wait approved BAN BAK (45jt/thn), mitra submit softcopy lsg ke pak Ihsan 08/03/26 : Pihak RT minta menambahkan warga agar tidak terkendala target 10 Mar 2026 25/02/26 : Need approved BAN (45/thn), IW OG koordinasi dgn RT/RW 18/02/26 : Vaidasi OK Cand R (-6.27492,106.79185) 09/02/26 : Need Validasi Cand Q ( 06.27492,106.79185) 09/02/26 : IW done dan Paralel Rehunting 02/02/26 : BAN waiting Approval 13/01/26 : Validasi cand Q OK, lanjut BAN/BAK 29/12/25 : Need Validasi CAN Q ( 106.79296 -6.27605) GF 25m 23/12/25 : Validasi NBAE NOK /Reject : 23/12/2025 (Rehunting as note) 22/12/25 : Need Validasi CAN A ( 106.79362 -6.276617) GF 25m | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Re-negosiasi :4/4/26 | Apr | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | BTR | Parkiran mobil, 120' 80m | 106.7925 | -6.2754 |  | 106.7925 | -6.2754 | Jl Poncol No II Gandria Selatan.Kel Gandaria Selatan Kecamatan Cilandak Jakarta Selatan | Monopole 20 1Leg | Fasum | RT 12 + Pole 18 | BTR | 3x3 | 50000000 | Lahan berpagar | Tubular | Flenge Dalam | 1.5 | 1.5 | 3 | RT 12 + Pole 18 | BTR
297 | Area 2 | JSA035 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0056 | JSA035 | GRENINTANRESIDENCEDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG IW Done | 22/04/26 : Wait BAN BAK (40jt/thn) 08/04/26 : Verifikasi ke site 11/4/26, high capex 01/04/26 : Plan 4/4/26 re-negosiasi ulang bersama DMT (40jt/thn), IW done 30/03/26 : Wait approved BAN BAK (40jt/thn), mitra submit softcopy lsg ke pak Ihsan, LL minta gambar STR pondasi 16/03/26 : Wait approved BAN BAK (40jt/thn), mitra submit softcopy lsg ke pak Ihsan, LL minta gambar STR pondasi 08/03/26 : Keluarga Owner meminta kepastian bentuk tower dan type perkuatannya bangunan gedungnya, site visit konsultan 15 Mar 2026 25/02/26 : Need approved BAN BAK (40/thn), IW OK 02/02/26 : BAN Waiting Approval 30/01/26 : Validasi OK 17/01/26: Need Validasi CAN Q(106.80436 -06.26698) RT 12m + Pole 15m 13/01/26: Validasi NBAE NOK (CAN P) Rehunting 22/12/25 : Need Validasi CAN P ( 106.79340 -6.27615) RT 8 + 20m | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Re-negosiasi :4/4/26 | Mar | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | BTR | 70' 150m | 106.8044 | -6.2666 |  | 106.8044 | -6.267 |  | Monopole 20 1Leg | Fasum | RT10m + pole 20m | BTR | 3x4 | 44444444.4444 | Lahan warga | Tubular | Flenge Luar | 1.5 | 1.5 | 3 |  | BTR
323 | Area 2 | JSA037 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0062 | JSA037 | JLDIENGMAMPANGDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Rehunting | 22/04/26 : Proposed drop, submit JR 08/04/26 : Plan Jovis w/ Tsel 1/4/26: Plan extend NA, menunggu jadwal Jovis, paralel plan 16/03/26 : survey luas lahan untuk extend 6 m, plan submit JR 10/3/26: Extend 6m di eksisting minim space, rehunting OG (hardcandidat , Highprice) 04/03/26 : Rehunting 25/02/26: Menunggu jadwal Jovis tsel 5. 4/2/26 : Plan Jovis 4. 20/01/26 : Gagal IW ( ada beberapa warga menolak ) plan hari ini rehunting 3. BAN/BAK OG (waiting pertemuan LL dari luar negeri), plan bertemu LL hari selasa 13/1/26 2. Validasi NBAE OK 31-12-2025 (Cand P : -6.25501,106.83091), 1. 24.12 Need Validasi CAN P ( 106.83091 -6.25501 ) GF 30m | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT CELEBES KONTRUKSINDO | PT TRITECH CONSULT | Extend 6m | 170 degree arah 180m | 106.8301 | -6.2543 |  | 106.8309 | -6.255 | Jl. Mampang Prapatan RT.005 RW.005, Kel. Duren Tiga, Kec. Pancoran, Kota Jakarta Selatan | Monopole 20 1Leg | Fasum | MP30 | BTR |  |  | Trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
204 | Area 2 | JSA041 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0053 | JSA041 | JLMANGGISMANGGARAIDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | Rehunting | 22/04/26 : IW fail, rehunting 08/04/26 : Verifikasi ke site 13/4/26, community issue 01/04/26 : Target IW 5/4/26 30/03/26 : Target IW Done 30 Mar 26 16/03/26 : IW OG (masih ada penolakan warga) 08/03/26 : IW OG(40 warga), pendekatan warga yang tolak 8(3 tokohwarga) target 15 Mar 2026 06/03/26 : BAN 45jt/th 25/2/26 : BAN OG, LL kondisi sakit belum bisa di temui 18/02/26: Validasi NBAE OK (Cand S -6.21899,106.84823) Lanjut BAN/BAK 02/02/26 : Need Validasi Cand S ( -6.21899,106.84823) 30/01/26 : Validasi NOK Cand Q, Validasi NOK Cand R 26/01/26 : Need Validasi Cand Q (-6.22024,106.84931) & Need Validasi Cand R (-6.22015,106.84950) issue Cand P reject warga sempadan BAN / BAK OG , IW 70% radius (8KK) BAN BAK OG (50jt/tahun) paralel proses hunting cand. Q 18/12/25 : Validasi NBAE OK (Cand P : -6.21952,106.84859) | Optimis | 2026-03-20 | 1. 18.12 BAN/BAK OG | IW : 5/4/26 IW : 30/03/26 | Apr | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | BTR | 290' 80m | 106.8484 | -6.2196 |  | 106.8486 | -6.2195 |  | Monopole 20 1Leg | Fasum | MP 30 | BTR |  |  | Lahan berpagar | Tubular | Flenge Luar | 3 (1.5) | 3 (1.5) | 9 (2.25) |  | BTR
312 | Area 2 | JSA043 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JSA043 | RELOCCILANDAKDMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.8029 | -6.3044 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
450 | Area 2 | JSX016 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0439 | JSX016 | ALAMSEGAR5DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Drop | 31/10 : Validasi OK | Not Optimis | Drop | Propose Drop Terminate |  | DROP | PT SUMBERSOLUSINDO HITECH | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Terminate |  | 106.782 | -6.268 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [9 empty] | Terminate
156 | Area 2 | JSX028 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 23TS03Z0024 | JSX028 | GARUTMENTENGDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 15/08/2023 | 0 | RFI | Done RFI | PT SUMBERSOLUSINDO HITECH | Waspang | Contine with Macro |  | 106.8413 | -6.2049 |  |  |  |  | Monopole 18 1Leg |  |  | Contine with Macro | [9 empty] | Contine with Macro
105 | Area 2 | JSX032 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0440 | JSX032 | CAMATKEBAYORANLAMADMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Drop | 18/12/2025 TERMINATE | Not Optimis | 2026-02-14 | Propose Drop Terminate |  | DROP | PT MITRA SARANA KARYA BANGSA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Terminate |  | 106.7783 | -6.2488 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [9 empty] | Terminate
104 | Area 2 | JSX130 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0445 | JSX130 | PERCETAKAN2DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Drop | 18/12/2025 TERMINATE | Not Optimis | 2026-02-14 | Propose Drop Terminate |  | DROP | PT MITRA SARANA KARYA BANGSA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Terminate |  | 106.7942 | -6.2483 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [9 empty] | Terminate
473 | Area 2 | JSX257 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 25TS11B0012 | JSX257 | JERUKPURUTDALAMDMT | Plan ≤ 2025 | Rescoping tambahan WO | Tracker Project DMT_TSEL | 4. CME | NOD OG | 05/05/26 : Pouring OG, plan RFI 22/5/26 04/05/26 : Undangan Pouring 05 Mei 2026 28/04/26 : Borepile lubang ke 6, kondisi tanah berair dan juga longsoran karena site sempit 22/04/26 : Galian pondasi OG 20/04/26 : Pembersihan lahan 08/04/26 : Menunggu NOD 1/4/26: Menunggu NOD, 16/03/26 : Menunggu NOD, DP OK 04/03/26 : Menunggu NOD, DP done 25/02/26: Menungu NOD & DP sewa lahan 22/01/26 : Menunggu NOD, Menunggu DP sewa lahan 21/1/26 : SKOM done 20/01/26 : Submit APD, plan SKOM 21/1/26 15/01/26: Proses Soil test OG 13/01/26: Rekom lurah OG, BAN/BAK done , IW done BAN / BAK OG plan pertemuan LL 06/01/2026 Validasi NBAE OK : 18/12/2025 | Optimis | 2026-02-28 | BAN/BAK OG | 2026-05-22 | Mar | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | BTR |  | 106.8143 | -6.2845 |  |  |  |  | Monopole 20 1Leg |  | MP32m | BTR |  | 277777780 | Trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | MP32m | BTR
451 | Area 2 | JSX345 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 24TS10B0025 | JSX345 | JALANKUMBANGDMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Drop | 18/12/2025 TERMINATE | Not Optimis | Drop |  | DROP | DROP | PT SINERGI REKTA DENTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Terminate |  | 106.7763 | -6.2976 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Terminate
210 | Area 2 | JSX351 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0107 | JSX351 | RELOCSWADARMDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Validasi OG | 1/4/26: Need Validasi Cand D ( -6.23275,106.75758) 27/03/26 : Need Validasi Cand D ( -6.23275,106.75758) 16/03/26 : IW gagal, paralel re-hunting 04/03/26 : BAN OK, warga minta ketinggian MP 25m, menunggu validasi Tsel 8. 21/02/26 : BAN 25jt/th , masih ada case ahli waris yg keberatan sedang di follwup 7. 3/02/26: Validasi NBAE OK (CAN C 106.75666 -6.23170) lanjut BAN/BAK 6. 21/01/26 : Menunggu validasi can C(106.75666 -6.23170) GF 32m (BAN 25jt/th) 5. 14/01/26: Need Validasi CAN C(106.75666 -6.23170) GF 32m (BAN 25jt/th) 4. 14/01/26: Validasi NBAE NOK (Can B) 3. 05/01/26 : Need Validasi cand B 2. 25/12/25 : Need Validasi CAN B (106.75836 -6.23126) GF 32m 1. 22/12.25 : Need Validasi CAN A (106.75624 -6.23129) GF 32m cancel by LL | Optimis | 2026-03-20 | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | PT TRITECH CONSULT | BTR |  | 106.7572 | -6.2313 |  | 106.7576 | -6.2328 | jl Kostrad Pusri RT 10 /05 Petukangan Utara. Kec. Pesanggrahan provinsi DKI Jakarta | Monopole 20 1Leg | Fasum | MP 32m | BTR |  |  | Trotoar | Tubular | Flenge Dalam | 1.5 | 1.5 | 3 |  | BTR
261 | Area 2 | JSX395 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0017 | JSX395 | LURAHKEBONBARUDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | Ban/Bak | 28/04/26 : Soil test OG 22/04/26 : Plan soil test 24/4/26 16/04/26 : IW OG (warga minta pembayaran cash n carry ) 08/04/26 : IW OG (warga minta pembayaran cash n carry ) 01/04/26 : Plan ketemu lurah 4/4/26 16/3/26: Proses koordinasi dengan kantor kelurahan terkait plan extend, tower eksisting berbatasan dgn kantor lurah 10/03/26 : RT meminta surat dari DMT (9/3/26) 09/03/26 : lanjut Extend 6m 04/03/26 : Extend 6m 25/02/26: Plan proposed extend 6m eksisting 8. 04/02/26 : Rehunting 7. Submit JR 1. kandidat P. High Price harga sewa 75 jt/thn 2. Kandidat Q. Adanya Penolakan dari salah satu ahli waris/tidak menyetujui adanya Pembangunan Tower. 3. Kandidat R.legalitas kepemilikan tanah bermasalah Atau Tanah Sengketa.) 6. 30/01/26 : Validasi OK Cand Q, Validasi OK Cand R 5. 17/01/26: Need Validasi CAN R (106.86028 -06.23201) RT 16m + Pole (BAN 25jt/th) 4. 09/01/26 : Need Validasi CAN Q (106.86076 -6.23273) RT 15m + Pole 12m, Cand P Issue Highprice(75jt/th) 3. BAN / BAK plan 05/01/2026 2. Validasi NBAE OK : 31/12/2025 (Cand P : -6.23238,106.86063) 1. 24.12 Need Validasi CAN P ( 106.86063 -6.23238) RT 4m + 32m | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | RFI : W2 Mei 26 Lurah : 4/4/26 | Apr | PT JAGANATA SAKTI UNGGUL | PT TRITECH CONSULT | Extend 6m | 150m arah 90 degree | 106.8596 | -6.2323 |  | 106.8603 | -6.232 | JL asem baris raya No.1C RT04/RW04 Kebon baru ke. Tebet Jakarta Selatan | Monopole 20 1Leg | Fasum | eXTEND 6M | BTR |  |  | Trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
290 | Area 2 | JSX408 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0079 | JSX408 | JLDUKUCILEDUGDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 22/04/26 : Wait approved BAN BAK (37/thn), paralel re-hunting 08/04/26 : Waiting Approval BAN (37jt/thn) stacking RT+ pole 1/4/26: waiting approval BAN (37jt/th), paralel proposed surat pengantar dari DMT untuk kandidat di kampus moestopo 16/03/26 : LL tetap dgn harga 37jt/thn (stacking 12m + pole 13m) 04/03/26 : nego BAN 37jt/thn justifikasi potensi nilai CME tinggi 25/02/26: waiting Approval BAN, IW OG plan soswar 27/02 5. 04/02/26 : Plan BAN (05/02/26) minta ttd orang tua LL harga 37jt/thn 4. 20/01/26 : LL msh bertahan di 55jt per tahun 3. BAN/BAK OG (issue high price) (55jt/tahun) potensi IW 80% (anak LL ketua RW), plan bertemu LL hari selasa 13/1/26, Paralel rehunting CAN Q 2. Validasi NBAE OK 23-12-2025 (Cand P : -6.2285,106.76136) 1. 22.12 Need Validasi CAN P ( 106.76136 -6.22850 ) RT 4m + Pole 20m | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT CELEBES KONTRUKSINDO | PT TRITECH CONSULT | BTR | arah 100m 230 degree | 106.7614 | -6.2284 |  | 106.7614 | -6.2285 | Jl. Kp Baru 1 Rt 001 Rw 002 kel. Ulujami Kec. Pesanggrahan kota jakarta seLatan | Monopole 20 1Leg | Fasum | MP30 | BTR |  |  | Streetview NA |  |  | 2 | 2 | 4 |  | BTR
253 | Area 2 | JSX409 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0103 | JSX409 | JLRAYAMAJADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW OG | 1/4/26: IW done(minus RT/RW) ,plan soil test 7/4/26 16/03/26 : BAN OK, IW OG, sebagian warga sudah mudik, di lanjut setelah hari Raya 04/03/26 : IW OG, extend 6m, LL minta 350jt/15th 5. 21/02/26 : LL mau harga 350jt/15thn 4. 21/01/26 : IW OG dan menunggu approval harga sewa 3.13/01/26: Validasi NBAE OK (Can P) lanjut BAN/BAK 2. 05/01/26 : Need Validasi CAN P (106.80092 -6.26560) GF 32 m 1. 29/12/25 : Need Validasi CAN P (106.80092 -6.26560) GF 32 m | Optimis | 2026-01-29 | Add 3 RF Add 6 RRU Final Sow Rescope: 3. reheight tower |  | Apr | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | PT TRITECH CONSULT | Extend Pole | Extend 3m | 106.8013 | -6.2657 |  | 106.80092 | -6.26560° | jl Abdul Majid GG bungur no 50 RT 11/02 Kel . Kebayoran Baru kec.cipete Utara | RT 16m + Pole 9m = 25m | Fasum Masjid | Extend 6m | Extend 6m |  |  | Rooftop mesjid | Pole | Pole | 3 | 5 | 8 | Extend 3m OG | extend 6m
299 | Area 2 | JSX413 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0076 | JSX413 | JALANKHROYANIDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 8. Lock Trial | Validasi OG | 22/04/26 : Need validasi cand R 09/04/26 : Need Validasi Cand R ( -6.21830,106.82217) 08/04/26 : Submit datek 8/4/26 cand C 1/4/26: Rehunting OG plan submit 6/4/26 31/03/26 : lahan 2x3 terlalu mepet untuk pondasinya, minimal 3x3 untuk MP30m, pararel rehunting 16/03/26 : Cand P validasi OK, luas lahan 2x3m. menunggu arahan DMT (pak Ihsan) 12/03/26 : Mitra submit JR (LL menolak extend) menunggu arahan kembali 04/03/26 : Hard candidate, LL tidak mau perpanjang, rehunting 25/02/26: Rehunting, paralel proposed extend 6m 27/01/26 : Rehunting, LL Can A tetap minta dilahan 2x3 20/01/26 : Bertemu dengan pemilik lahan Can A 13/01/26: Validasi NBAE NOK (can B) rehunting or cek ulang lahan CAN A 25.12 Need Validasi CAN Q (106.82148 -6.21903) CAN A Lahan terbatas 2x3 Validasi NBAE OK : 18/12/2025 (Cand P : -6.21817,106.82284) | Not Optimis | 2026-03-20 | 1. 18.12 BAN/BAK OG | Datek : 8/4/26 | Apr | PT VALUE TELECOMMUNICATION | PT TRITECH CONSULT | BTR | Arah 70m 290 degree | 106.8225 | -6.2184 |  |  |  |  | Monopole 20 1Leg | Fasum | RT 10 m + Pole 15 m | BTR | 2.15x2.8 |  | Lahan berpagar | Tubular | Flenge Luar | 2 | 2 | 4 | RT 10m +pole 15m | BTR
78 | Area 2 | JSX444 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 25TS08N2005 | JSX444 | KELKARETPEDURENANDMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Lock Trial |  |  |  | NY | NY | Lock Trial |  | 106.833 | -6.2126 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
182 | Area 2 | JSX454 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 25TS08N1765 | JSX454 | JATIINDAHKEBLAMADMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Lock Trial |  |  |  | NY | NY | Lock Trial |  | 106.7746 | -6.2609 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
183 | Area 2 | JSX467 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 25TS08N1764 | JSX467 | SAWOMANGGARAIDMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Lock Trial |  |  |  | NY | NY | Lock Trial |  | 106.8458 | -6.2165 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
621 | Area 2 | JSX469 | Jabat |  | Non MKT | Non MKT | #N/A | BTSH | NY | JSX469 | TEBETBARATBUKITDURIDMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | Drop | DROP | Not Optimis | Drop | #N/A | DROP |  | NY | NY | Terminate | Terminate (Dismantel Done) | 106.8654 | -6.2212 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Terminate
245 | Area 2 | JSX470 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0052 | JSX470 | LEBAKSARITJBARATDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK | 22/04/26 : Menunggu pertemuan dgn DKM 24/4/26 08/04/26 : Informasi hasil pertemuan dgn DKM 8/4/26 01/04/26 : Musyawarah dgn DKM 5/4/26 16/03/26 : Keputusan DKM penentuan yg di setujui di bangun 18/03/26 (Pole) 10/03/26 : Extend lahan eksisting NA, lahan BTR (cand R) plan soswar 14-Mar-26 (minaret) 08/03/26 : Mesjid Rooftop mesjid tinggi 10m + pole 20m, bertemu ketua DKM BAN OG dan persiapan IW 14 Mar 26 07/03/26 : Validasi OK Cand R 25/02/26 : Need Validasi Cand R ( -6.30093,106.85461), Need Validasi Cand S ( -6.3010,106.85350) 21/02/26 : Need Validasi Cand R ( -6.30093,106.85461), Need Validasi Cand S ( -6.3010,106.85350) Cand Q gagal IW, rehunting new cand 09/01/25 : Cand Q validasi NBAE OK (9/1/26), next BAN/BAK 09/01/26 : Submit Datek cand Q ( -6.30057 106.85334) BAN /BAK OG , IW paralel 31/12/25 : Validasi NBAE OK : 31/12/2025 (Cand P : -6.30207,106.8535) 24/12/25 : Need Validasi CAN A ( 106.85339 -6.30207) GF 32m | Optimis | 2026-03-20 | [30/10/25] Plan Eksekusi W4 Nov [9/09/25] Proses Fabrikan Ring mounting + Rack Gendong + Bracket Panel KWH + ACPDB [20/07/2025] Submit Dok.RFIN done | Musyawarah DKM : 5/4/26 | Apr | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | Extend 6m | 280m arah 0 (106.852667 -6.298361 ) | 106.8534 | -6.30242 |  | 106.8535 | -6.30207 | Jalan Lebaksari RT 012/05 Kel Tanjung Barat Kec Jagakarsa Jakarta Selatan | Monopole 20 1Leg | Fasum | MP 30 | BTR | 3x4 |  | Trotoar | Tubular | Flenge Luar | 2 | 2 | 4 | Extend 6m | Extend 6m
186 | Area 2 | JSX473 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 24TS10B0026 | JSX473 | PERTANIANLEBAKBULUSDMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 04/08/2025 | Program Jakarta Quality Improvedment | RFI | Done RFI | PT SINERGI REKTA DENTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 106.7776 | -6.3022 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
217 | Area 2 | JSX486 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0014 | JSX486 | TANGKASPESANGGRAHANDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Validasi OG | 22/04/26 : Wait validasi cand S 16/04/26 : Need validasi cand S 08/04/26 : Need validasi 05/04/26 : Need Validasi Cand S ( -6.24864,106.75951) 01/04/26 : Issue tanah yang akan disewa proses pembebasan lahan TOL dan Pemakaman Umum Pemda, rehunting 16/3/26: IW OG(14KK) proses IW dilanjutkan setelah lebaran 10/03/26 : plan Soswar 11 Maret 2026 05/03/26: BAN Approve (28jt/th) lanjut IW 04/03/26: BAN/BAK OG, 8. 26/02/26 : Validasi OK Cand B 7. 25/02/26: Waiting approval BAN Can A(50jt) , can B (30jt) need validasi 6. 30/01/26 : Need Validasi Cand B ( -6.24730,106.75922) issue banjir 1m 5. 23/01/26 : BAN OG (issue high price 50jt/th) 4. 17/01/26: BAN OG (issue high price 60jt/th) 3. 15/01/26: LL sedang cek PKS lama terkait plan newsite disamping lahan eksisting 2. 14/01/26: Validasi NBAE OK (Can A) Lanjut BAN/BAK 1. 18.12 Need Validasi CAN A ( 106.75954 -6.24860) GF 30m | Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | W4 Mei 2026 | Apr | PT JAGANATA SAKTI UNGGUL | PT TRITECH CONSULT | BTR |  | 106.7595 | -6.2486 |  | 106.7595 | -6.2486 | Jl. Mertilang ujung, RT.007 RW 001 Kel. Petukangan Selatan Kec. Pesanggrahan kota Jakarta Selatan | Monopole 20 1Leg | Fasum | MP 32M | BTR |  |  | Lahan berpagar | Tubular | Flenge Dalam | 1.5 | 1.5 | 3 |  | BTR
214 | Area 2 | JSX498 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0112 | JSX498 | KEMANGDALAMDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Rehunting | 1/4/26: Extend NA, penolakan 16/03/2604/03/26 : Plan Extend 6 m, FU IW (4 KK), warga belum bisa di ajak koordinasi krn tidak ada di tempat 6. 21/02/26 : IW OG dengan extend 6m sedang dicoba tim 5. 21/01/26 : Submit JR 4. 12/01/26: issue hard candidat proses JR OG 3. 05/01/26 : Rehunting OG (plan candidat lahan parkir) plan submit Datek 09/01 2. 31/12/25 : Validasi NBAE Not OK (rehunting as noted) 1. 22/12/25 : Need Validasi CAN A (106.81751 -6.27107) GF 32m | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | DROP | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | PT TRITECH CONSULT | BTR |  | 106.819 | -6.2712 |  |  |  |  | Monopole 20 1Leg | Fasum | Extend 6m | extend 6m |  |  | Trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 |  | BTR
109 | Area 2 | JSX500 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 25TS08N2036 | JSX500 | JLNPANGERANANTASARIDMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Lock Trial |  |  |  | NY | NY | Lock Trial |  | 106.8073 | -6.283 |  |  |  |  | Monopole 18 1Leg |  |  | Terminate | [9 empty] | Lock Trial
193 | Area 2 | JSX507 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 25TS08N1779 | JSX507 | SOUTHQUATERWESTDMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Lock Trial |  |  |  | NY | NY | Lock Trial |  | 106.7826 | -6.2954 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
296 | Area 2 | JSX510 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0080 | JSX510 | KESEHATANRYBINTARODMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Validasi OG | 05/05/26 : Waiting Need Validasi Cand S ( -6.27126,106.76039) 30/04/26 : Need validasi cand S ( -6.27126,106.76039) 22/04/26 : Need validasi cand S ( -6.27126,106.76039) 08/04/26 : Need Validasi 06/04/16 : Need Validasi Cand S ( -6.27126,106.76039) 01/04/26 : Rehunting 16/03/26 : Gagal IW, submit JR 03/03/26: Validasi NBAE OK (Cand C : -6.27091,106.76118) Lanjut BAN/BAK 26/02/26: Need Validasi CaN C (106.76118 -6.27091) GF MP 32m 25/02/26: Rehunting harus geser radius RT eksisting 01/02/26 : Soswar OG, Mitra Submit BA Penolakan pembangunan tower, Rehunting 19/01/26: BAN OG(50jt/th) waiting approval 5.13/01/26: Validasi NBAE OK (Can B) lanjut BAN/BAK 4. 05/01/26 : Need validation 3. 30.12 Need Validasi CAN B (106.76125 -6.27010) GF 32m 2. 25.12 Cancel Candidat A (LL membatalkan persetujuan) , Rehunting OG 1. Validasi NBAE OK : 17/12/2025 (Cand A : -6.27041,106.76162) | Not Optimis | 2026-03-20 | 1. 18.12 BAN/BAK OG | Datek : 7/4/26 | Apr | PT TRIPUTRA SURYA SEJAHTERA | PT TRITECH CONSULT | BTR | SAR 100 quadran 3 | 106.7611 | -6.2705 |  | 106.7612 | -6.2709 | Gg H. Isa, Rt. 10, Rw. 11, Kelurahan Bintaro, kecamatan Pesanggrahan, Jakarta Selatan. | Monopole 20 1Leg | Fasum | MP 32m | BTR |  |  | Trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Lanjut BTR (106.76118 -6.27091) GF MP 32m | BTR
593 | Area 2 | JSX535 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0051 | JSX535 | PEMUKIMANPASARMINGGUDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 22/04/26 : Wait approved BAN BAK (450jt/10thn) 08/04/26 : Verifikasi ke site 11/4/26, high capex | Optimis | 2026-03-20 | 1. 18.12 BAN/BAK OG | BAN : 4/4/26 | Mar | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | BTR | 150m arah 330 degree | 106.8421 | -6.2924 |  | 106.842 | -6.2912 | Jl Rawa Bambu No 14D RT 013/05 Kel Pasar Minggu Kec Pasar Minggu Jakarta selatan | Monopole 20 1Leg | Fasum | RT 12 + Pole 18 | BTR | 3x4 | 500000000 | Trotoar | Tubular | Flenge Dalam | 4 (1.5) | 4 (1.5) | 16 (2.25) |  | BTR
291 | Area 2 | JSX536 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0077 | JSX536 | PDKLABUCILANDAKDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Need Validasi | 22/04/26 : Need validasi can d R 17/04/26 : Need Validasi Cand R ( -6.30714,106.79310) 08/04/26 : Rehunting OG, Plan submit datek 14/4/26 1/4/26: Rehunting, plan submit 6/4/26 16/3/26: SD menolak, re-hunting new cand (18/03/26) 04/03/26 : Rehunting new cand, arahan ke SD Pondok Labu 25/02/26: Plan extend 6m OG pertemuan LL 20/02/26: Issue High price (100jt/th) Proposed Extend 6m Site Eksisting 03/02/26: Validasi NBAE OK (Can Q 106.79327 -6.30658) Lanjut BAN/BAK 20/01/2026 : Validasi OG can Q (106.79327 -6.30658) GF (menara mesjid) 32m 11/01/2026 : Need validation CAN Q (106.79327 -6.30658) GF (menara mesjid) 32m 05/01: Rehunting CAN Q OG plan submit Datek 06/01/26 , CAN P (drop by LL) 26/11 : Wait approval BAN (325jt/10 tahun) | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT VALUE TELECOMMUNICATION | PT TRITECH CONSULT | BTR | Arah 110m 320 degree | 106.7936 | -6.3069 |  | 106.7933 | -6.3066 |  | Monopole 20 1Leg | Fasum | MP 30M | extend 6m | 3x3 |  | Lahan berpagar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | MP 30m | BTR
269 | Area 2 | JSX574 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JSX574 | TEGALPARANGUTARAMAMPANGDMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.8202 | -6.2606 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
133 | Area 2 | JSX693 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0418 | JSX693 | BANGKA11DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | Justifikasi Report | HARD CANDIDAT Propose DROP | Not Optimis | 2026-02-14 | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial |  |  | PT SUMBERSOLUSINDO HITECH | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Lock Trial |  | 106.8193 | -6.2544 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
127 | Area 2 | JSX741 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0422 | JSX741 | KEMANDORANPLUIS1DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 05/11/2025 | Lanjut B2R | RFI | Done RFI | PT SUMBERSOLUSINDO HITECH | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 106.7926 | -6.2109 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
591 | Area 2 | JSX745 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JSX745 | PERDATAMTERUSANDMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.7681 | -6.2438 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
171 | Area 2 | JSX754 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0089 | JSX754 | PERMATAHIJAUTOWNHOUSEDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW OG | 30/04/26 : RT tidak dapat ditemui (di Luar Negeri) dan RW sulit diajak komunikasi (susah ditelp dan enggan ditemui) serta berikan pernyataan bahwasanya kurang berkenan adanya pekerjaan di area lokasi tersebut perihal ijin dari warga sekitar (komplek). 22/04/26 : Pak RW akan mengadakan sosialisasi dgn warga 25-26/4/26, extend 3m 08/04/26 : Extend 3 m, Plan 10/4/26 koordinasi dgn RT/RW 07/04/26 : Validasi Cand A Nok 01/04/26 : Sounding need Validasi cand B (106.78195 -6.21326) RT 15m + Pole 15m, paralel survey extend 6m 16/03/26 : Need Validasi CAN B (106.78195 -6.21326) RT 15m + Pole 15m, paralel survey extend 6m 10/03/26 : Koordinasi dengan pemda perihal extend 6m 25/02/26 : Rehunting hardcandidat 22/01/26 : Submit JR 22/01/26 : validasi NOK 05/01/26 : Need Validasi CAN B (106.78195 -6.21326) RT 15m + Pole 15m 18/12/26 : HARD CANDIDAT KOMPLEK ELIT | Optimis | 2026-03-20 | Add 3 RF Add 4 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-02-04 | Apr | PT TRIPUTRA SURYA SEJAHTERA | PT TRITECH CONSULT | Extend 6m |  | 106.7799 | -6.2152 |  |  |  |  | Monopole 20 1Leg | Fasum | Extend 3 m | Extend 6m |  |  | Streetview NA |  |  | 1.5 | 1.5 | 3 | Extend 3 m | Extend 3 m
112 | Area 2 | JSX768 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0433 | JSX768 | MESJIDPONDOKINDAHDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | IW OG | HARD CANDIDAT Propose DROP | Optimis | 2026-02-13 | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial |  |  | PT SUMBERSOLUSINDO HITECH | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Lock Trial |  | 106.783 | -6.2622 |  |  |  |  | Monopole 20 1Leg |  |  | Extend 6m | [9 empty] | Extend 6m
118 | Area 2 | JSX771 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0430 | JSX771 | KOMPLEKDEPSOSPDKINDHDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 9. Propose Drop | Lock Trial | HARD SITAC ISSUE,PROPOSE RETURN | Optimis | 2026-01-29 | 12.12 Proposed drop, ada penolakan warga 4.12 pabrikasi OG | REASSESMENT | Apr | PT SUMBERSOLUSINDO HITECH | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Extend Pole | Extend 6m | 106.7879 | -6.2658 |  |  |  |  | Monopole 20 1Leg |  |  | Extend 6m | [8 empty] | Extend 6m | Extend 6m
188 | Area 2 | JSX774 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0095 | JSX774 | SUBURPONDOKPINANGDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW OG | 28/04/26 : Menunggu dana kompensasi Addwork 22/04/26 : IW masih menunggu approval permohonan kompensasi fasilitas umum di area tower SDN 08 PP. 16/04/26 : Mitra submit BA perihal Permohonan kompensasi fasilitas umum di tower area SDN 08 PP 1/4/26: Proses klarifikasi kompensasi warga untuk kelanjutan IW, Plan Soil 7/4/26 16/03/26 : IW belum bisa tt kalau belum di bayar, RT minta kompensasi untuk gapura, cctv dan wifi 22jt 10/3/26: IW proses(Penyusunan RAB permintaan warga,) 04/03/26 : Permohonan warga sesuai list yg di minta, plan extend 6m 6. 21/02/26 : RT minta CCTV seperti yang di PKS DKI 5. 21/01/26 : Menunggu jadwal soswar dari RT 4. 12/01/26 : Need cek PKS existing karena PKS nya dipegang RW lama dan belum ketemu 3. 07/01/26 : Menunggun hasil Pertemuan pihak Yayasan baru diagendakan 08/01, pertemuan sebelumnya terkendala kedukaan warga 2. 05/01/26 : Plan pertemuan pihak Yayasan, Plan submit Datek 06/01/26 1. Lahan eksisting area pagar dalam SD | Optimis | 2026-01-29 | Add 3 RF Add 3 RRU Final Sow Rescope: 3. reheight tower |  | Apr | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | PT TRITECH CONSULT | Extend Pole |  | 106.7711 | -6.2758 |  |  |  |  | Monopole 20 1Leg | Fasum Sekolah | Extend 6m | Extend 6m |  |  | Lahan sekolah | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
167 | Area 2 | JSX779 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JSX779 | PENINGGARANTIMUR1DMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.778 | -6.243 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
176 | Area 2 | JSX782 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0112 | JSX782 | BAKTIMURNILEBAKBULUSDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Rehunting | 29/04/26 : Need Validasi Cand C ( -6.30752,106.78632) 27/04/26 : Validasi Cand Q NOK, Rehunting 22/04/26 : Need validasi 08/04/26 : Waiting Validasi 1/4/26: Waiting validasi 16/03/26 : Wait validasi cand P dan Q 10/03/26 : Extend 6 m hold, waiting approved cand P dan Q 04/03/26 : Validasi cand P OG 8. 05/02/26 : Need Validasi Cand P (-6.30791,106.78777), Need Validasi Cand Q ( -6.31000,106.78590) 7. Rehunting. Plan Kand 06/02 6. - Menunggu konfrimasi bagian aset DMT untuk masalah perpanjangan sewa lahan yang akan habis 2026 5. Paralel proses kordinasi dengan dinas terakit penambahan ketinggian menara - Done 4. New kand permintaan sewa lahan 400jt/th 3. Menunggu review konsultan - Done 2. Proses survey Kand untuk Extend - Done 1. JOVIS konsultan done 05/01/2026 menunggu analisa extend 3 m, opsi CAN P (issue High price 300jt/th) | Optimis | 2026-01-29 | Add 3 RF Add 4 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | Extend Pole | Extend 3m | 106.7866 | -6.309 |  |  |  |  | Monopole 20 1Leg | Privat |  | Extend 6m |  |  | Lahan LL | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
86 | Area 2 | JSX784 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JSX784 | MULIAPERDANA2DMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial |  | 106.7558 | -6.2435 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
220 | Area 2 | JSX791 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0048 | JSX791 | SEKOLAHDUTA2DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW OG | 22/04/26 : Warga minta kompensasi sebelum tanda tangan IW 16/04/26 : Wait approved BAN (30jt/tahun), paralel eskalasi IW (1jt/kk, total 30 kk), cash n carry 08/04/26 : wait approved BAN (30jt/thn), proses penyaluran kompensasi untuk warga 02/04/26 : BAN resubmit 30jt/th need approval 01/04/26 : Waiting approval BAN(30jt/th) submit sc ke pak Ihsan, warga minta kompensasi sebelum tanda tangan IW 16/03/26 : IW OG (30KK) proses IW dilanjutkan setelah lebaran 04/03/26 : Waiting approval BAN(30jt/th), 25/02/26: Waiting approval BAN, Paralel penjajakan IW ( potensi KK 30) 17/01/26: BAN 30jt/th waiting approval, done submit DMT 15/01 : Proses negosiasi dgn LL (40jt/tahun) 14/01/26: Validasi NBAE OK (Can A) Lanjut BAN/BAK 18.12 Need Validasi CAN A ( 106.78915 -6.28688) GF 32m | Optimis | 2026-03-20 | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | RFI : W4 Mei 2026 RFI : W2 Mei 2026 BAN : 2/4/26 | Apr | PT JAGANATA SAKTI UNGGUL | PT TRITECH CONSULT | BTR | BTR Arahan Quadran 2 & 3 (dekat sekolah SAR 150m) | 106.7893 | -6.2862 |  | 106.7892 | -6.28688 | Jl. H. Batong II no. 56 RT. 007 RW 006 Kel. Cilandak Barat kec. Cilandak Jakarta Selatan, DKI Jakarta | Monopole 20 1Leg | Fasum | MP 32M | BTR | 3x4 | 333333333.3333 | Lahan berpagar | Tubular | Flenge Dalam | 1.5 | 1.5 | 3 |  | BTR
146 | Area 2 | JSX793 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0408 | JSX793 | PINANGSUASA3DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 9. Propose Drop | Lock Trial | HARD SITAC ISSUE,PROPOSE RETURN | Optimis | 2026-03-20 | 4.12 hard kandidat, Hard Sitac, plan BTR gagal IW, kandidat ke 5, proposed ke existing untuk extend | REASSESMENT |  | PT SUMBERSOLUSINDO HITECH | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 106.7799 | -6.2627 |  |  |  |  | Monopole 20 1Leg |  |  | Extend 3m | [8 empty] | Extend 3m OG | Extend 3m
143 | Area 2 | JSX802 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0450 | JSX802 | DEPSOS11DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 9. Propose Drop | Justifikasi Report | Propose extend 3 Meter (gagal BTR) | Optimis | 2026-01-29 | 10.12 proses IW, kurang 4 KK | W4 2026 | Apr | PT MITRA SARANA KARYA BANGSA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Extend Pole |  | 106.7653 | -6.2679 |  |  |  |  | Monopole 20 1Leg |  |  | Extend 6m | [8 empty] | Extend 6m | Extend 6m
170 | Area 2 | JSX806 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 24TS10B0024 | JSX806 | CINDRAWASIH2DMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Justifikasi Report | HARD CANDIDAT Propose DROP | Not Optimis | 2026-02-14 | Hard Kandidat, proposed drop | DROP |  | PT SINERGI REKTA DENTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Lock Trial |  | 106.7536 | -6.2687 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
166 | Area 2 | JSX809 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0090 | JSX809 | TAMANBINTAROCEMPAKA4DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW done | 30/04/26 : Terdapat permintaan kompensasi additional dari LL terkait relokasi tempat tinggal selama berlangsungnya pekerjaan (telah diemail hari ini) 22/04/26 : LL akan rembug keluarga mengenai pembongkaran bangunan eksisting 14/04/26 : Informasi dari konsultan diarahkan SOLENG menjadi MT 20M 08/04/26 : Perlu perkuatan pondasi di site eksisting, LL OK untuk perpindahan posisi pole 01/04/26 : IW done, hammer test 2/4/26, RT 4m+Stacking 6m+pole 20m 16/03/26 : BAN BAK OK, lanjut IW 05/03/26: Waiting approval BAN(24 jt/th) 3/03/26: Validasi NBAE OK (Can D -6.27393,106.75963) Lanjut BAN/BAK 26/02/26: Need Validasi CAN D(106.75963 -6.27393) RT 4m + MT 20m 25/02/26: lahan arahan tsel area hardsitac, plan rehunting sebrang tower eksisting, 5. 11/01/26 : Submit JR (terlampir), menunggu arahan DMT 4. 08/01/26 : area arahan rehunting issue penolakan tower, lahan kosong menolak disewa 3. 07/01/26: Validasi NBAE NOK (Cand C: -6.27307 106.76041) rehunting as note 2. 25.12 Need Validasi CAN C : (106.76041 -6.27307) GF 32m 1. Validasi NBAE NOK : 18/12/2025 (Cand B : -6.27377,106.76113) 18/12/26 Need Validasi CAN B :(106.76113 -6.27377) RT 10m + MP15, CAN A Cancel by LL Validasi NBAE OK :17/12/26(Cand A: -6.27308,106.76113) | Optimis | 2026-03-20 | Rehunting | APD : 7/4/26 | DROP | PT TRIPUTRA SURYA SEJAHTERA | PT TRITECH CONSULT | BTR | 150m arah 330 degree | 106.7596 | -6.2742 |  | 106.7596 | -6.2739 | JI. Cempaka IV RT 006 RW 017 Kel. Bintaro Keс. Pesanggrahan Jakarta Selatan | Monopole 20 1Leg | Fasum |  | BTR |  |  | Lahan berpagar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 |  | BTR
168 | Area 2 | JSX833 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JSX833 | STALENTENGAGUNGDMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial |  | 106.8355 | -6.3314 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
130 | Area 2 | JSX853 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0420 | JSX853 | KARETGUSURANDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Drop | 7/11 : BAN/BAK OG, LL masih di luar kota, potensi IW 75% | Not Optimis | Drop | Propose Drop Terminate |  | DROP | PT SUMBERSOLUSINDO HITECH | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Terminate |  | 106.8229 | -6.214 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Terminate
419 | Area 2 | JSX870 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 25TS11B0013 | JSX870 | PESONARASUNAMENTENGPULODMT | Plan ≤ 2025 | Rescoping tambahan WO | Tracker Project DMT_TSEL | 7. DROP | Lock Trial | HARD CANDIDAT Propose DROP | Not Optimis | 2026-01-10 | Propose Drop Terminate |  |  | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | Terminate |  | 106.8358 | -6.2222 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate |  |  | Drop |  |  | 1.5 | 1.5 | 3 | Terminate | Terminate
113 | Area 2 | JSX890 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0434 | JSX890 | KAIBALAIYASAMANGGARAIDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 2. SITAC | Rekom Lurah | 21/04/26 : reminder SKT ke lurcam, final 30/4/26 done REKOM LURCAM (GF MONOPOLE 30 METER) | Optimis | 2026-02-14 | 12.12 / 4.12 IW OG | 2026-05-22 | Mar | PT SUMBERSOLUSINDO HITECH | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 106.8523 | -6.2153 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
125 | Area 2 | JSX933 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0452 | JSX933 | KEMAJUANMULIA2DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | Lock Trial | 07/01: Hold LOCK TRIAL HARD CANDIDAT Propose DROP | Not Optimis | 2026-02-13 | 4.12 hard kandidat, Hard Sitac, type 6, infonya tsel lock trial |  |  | PT MITRA SARANA KARYA BANGSA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Lock Trial |  | 106.754 | -6.2392 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
302 | Area 2 | JSX951 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0113 | JSX951 | GURUMUHYINDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 3. RFC | APD OG | 1/4/26: Menunggu konfirmasi SOL Eng terkait kebutuhan borepile 16/03/26 : APD menunggu approved Sol Eng (Pak Dodi) 04/03/26 : Revisi APD menggunakan versi baru 6. 21/02/26 : IW OG, Waiting approval APD 5. 21/01/26 : RT/RW setuju. Tetap ikuti SOP. Koordinasi PT Adimix & 1 warga. Survey lokasi 22 Januari 2026. 4. 12/01/26 : PBG sedang dipastikan apakah bisa keluar atau tidak untuk extend 3m 3. 07/01/26 : info P Riza (IPPT ada, need perpanjangan PKS ) 2. 05/01/26 : Need konfirmasi PKS lahan Fasum 1. 29/12/25 : Lahan Fasum extend Pole Plan Lanjut IW ( paralel croscek PKS) | Optimis | 2026-01-29 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | PT TRITECH CONSULT | Extend Pole | Extend 3m | 106.8377 | -6.3153 |  |  |  |  | Monopole 20 1Leg | Fasum | Extend 6m | Extend 6m |  |  | Taman(eksisting perkuatan) | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 3m OG | extend 6m
106 | Area 2 | JSX998 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 24TS10B0022 | JSX998 | RELOCDANAMONDMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | Justifikasi Report | TERMINATE (JAQI) | Not Optimis | Drop |  | DROP |  | PT SINERGI REKTA DENTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Lock Trial |  | 106.7977 | -6.2483 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
142 | Area 2 | JTX018 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0411 | JTX018 | RAYAPENGGILINGANDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI Notice OG | IW OG | Optimis | 2026-02-28 | 10.12 proses negosiasi sewa lahan 35 -> 38 JT | W8 2026 | Mar | PT CIPTA KARSA ANUGERAH SEMESTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 106.9354 | -6.2028 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
87 | Area 2 | JTX285 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0104 | JTX285 | MANUNGGALCPMELAYUMAKASSARDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW | 08.04 : IW OG, Extend 6m (Soil Test Paralel 10/04) 19.01 : Lahan Disetujui, Nego Harga Sewa Lahan OG 13.01 : Need Validasi Cand P (-6.25001 ; 106.92018) 29.12 Lahan Pemda DKI, Pak RT akan bantu kordinasi ke Pemda 18.12 Kordinasi Lingkungan Setempat 25.02 : IW OG, Harga sudah submit menunggu App | Optimis | 2026-03-20 | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-11 | Mei | PT DYEVA DIGITAL SELULAR | PT MULTI BMITRA SEJAHTERA | BTR |  | 106.92 | -6.2497 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Alif | 088971363431 | Lahan Cukup Untuk Extend | Tubular | Flange Dalam | 1.5 | 1.5 | 3 |  | BTR
68 | Area 2 | JTX061 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0437 | JTX061 | ISTANAANAKTAMINIDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 26/08/2025 | 0 | RFI | Done RFI | PT CIPTA KARSA ANUGERAH SEMESTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 106.8997 | -6.3008 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
233 | Area 2 | JTX294 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0046 | JTX294 | JLNAMALIACAKUNGDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Hunting | 08.04 : Join Visit Dengan BPAD Untuk Penentuan Lahan 23.02 : OG Bersurat Ke BPAD DKI Menunggu Feedback 13.01 : Need Validasi Cand P (-6.21082 ; 106.93256) 29.12 Lahan Pemda DKI, Pak RT akan bantu kordinasi ke Pemda 18.12 Kordinasi Lingkungan Setempat 25.02 : Menunggu Feedback BPAD, | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-25 | Mei | PT DYEVA DIGITAL SELULAR | PT MULTI BMITRA SEJAHTERA | BTR | 170m arah 140 degree | 106.9327 | -6.2092 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Alif | 088971363431 | Lahan Fasum | Tubular | Flange Luar | 1.5 | 1.5 | 3 |  | BTR
599 | Area 2 | JTX314 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0045 | JTX314 | ELANGMALINDOMKSDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW OG | 08.04 : IW OG, Extend 3m (Soil Test Paralel 10/04) 13.01 : Kordinasi Extend, Lahan Eskisting Diperpanjang sampai 2035 29.12 Menunggu feedback dari pengurus lingkungan 18.12 Kordinasi Lingkungan Setempat 25.02 : Menunggu surat aman radiasi dari TSEL | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-11 | Mei | PT DYEVA DIGITAL SELULAR | PT MULTI BMITRA SEJAHTERA | BTR | BTR | 106.9086 | -6.2524 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Alif | 088971363431 | Lahan Cukup Untuk Extend | Tubular | Flange Luar | 1.5 | 1.5 | 3 |  | BTR
573 | Area 2 | JTX086 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 25TS09B0010 | JTX086 | WIRABAKTICIPINANGDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 3. RFC | APD Done | 05/05/26 : Koordinasi dengan LL mengenai pembayaran kompensasi 22/04/26 : Koordinasi desain dan biaya kompensasi dgn LL, 28/4/26 21/04/26 : Target persetujuan LL 28/4/26 08/04/26 : Menunggu persetujuan LL 1/4/26: Menunggu hasil desain konsultan W1 Apr 26 16/03/26 : Menunggu hasil desain konsultan W1 Apr 26 10/03/26 : Menunggu hasil analisa konsultan 04/03/26 : Menunggu hasil analisa konsultan 25/02/26: Plan survey by konsultan extend 6m 8. 05/02/26 : Need Validasi Cand R ( -6.25234,106.90879) 7. 04/02/26 : Rehunting 6. 30/1/26 : Validasi NOK Cand Q 5. 27/1/26 : Need Validasi cand Q (106.90899 -6.25223), submit datek 4. 22/01/26 : Proses BAN BAK, Proses permintaan legalitas tanah ke pengurus setempat, Paralel Rehunting 3. 15/01/26: Proses legalitas dokumen tanah 2. 05/01/2026 : menunggu hasil pertemuan tim Aset DMT dengan LL terkait perpanjangan sewa lahan site eksisting yang baru diperpanjang 1. IW PROSES (GF MONOPOLE 32 METER) | Optimis | 2026-02-28 | 12.12 lahan TNI, waiting surat balasan penawaran harga 4.12 proses negosiasi sewa lahan, nilai 400 jt/5 thn, issue High capex | 2026-05-25 | Apr | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | BTR |  | 106.911 | -6.2517 |  |  |  |  | Monopole 20 1Leg |  |  | Extend 6m |  |  | Trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
121 | Area 2 | JTX091 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0426 | JTX091 | GRAHAWIDYAPATRADMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 26/08/2025 | 0 | RFI | Done RFI | PT CIPTA KARSA ANUGERAH SEMESTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 106.9059 | -6.3008 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
198 | Area 2 | BKX293 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0092 | BKX293 | ANUGRAHRAYADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 5. RFI | RFI | 21.04 : ATP Done 16.03 : STR Done, Site RFI, Waiting ATP 24.02 : Masih Menunggu Tim Perkuatan On Site, Material RFD 13.02 : Fabrikasi Material STR + Extend OG Galvanized (Perkuatan Dilakukan Setelah Jl Udowo), Need CRQ 28.01 : APD Approve 13.01 APD Done, Need Review & Approval Soleng DMT 05.01 Survey Analisa Extend Done, Waiting APD 29.12 IW Done, Proses Pengajuan Permit Survey Pole 24.12 Survey Extend OG (Proses IW Radius Extend) | Optimis | 2026-01-29 | Add 3 RF Add 9 RRU Final Sow Rescope: 3. reheight tower | Mar | Mar | PT INDOJAR MULIA ABADI | PT MULTI BMITRA SEJAHTERA | Extend Pole | Extend 3m | 106.9149 | -6.2521 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 3m | Adit | 082123012385 | Lahan Cukup Untuk Extend | Tubular | Flange Luar |  |  |  | Extend 3m OG | Extend 3m
452 | Area 2 | JTX107 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 24TS10B0023 | JTX107 | RELOKSUPERINDODMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | Justifikasi Report | TERMINATE (JAQI) | Not Optimis | 2026-02-14 |  | DROP |  | PT SINERGI REKTA DENTA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | Lock Trial |  | 106.8911 | -6.1848 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
300 | Area 2 | JTX204 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JTX204 | RELOCPULOGBPERMAIDMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.9523 | -6.2005 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
205 | Area 2 | JTX283 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0094 | JTX283 | JLUDOWOPONDOKGEDEDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 5. RFI | RFI | 21.04 : ATP Done 16.03 : STR Done, Site RFI, Waiting ATP 24.02 : Masih Menunggu Tim Perkuatan On Site, Material RFD 13.02 : Fabrikasi Material STR + Extend OG Galvanized (MOS Rabu), Need CRQ 28.01 : APD Approve 13.01 APD Done, Need Review & Approval Soleng DMT 30.12 Pihak Halim Minta APD Pembangunan Sebelum Masuk Proses Perizinan | Optimis | 2026-01-29 | Add 3 RF Add 8 RRU Final Sow Rescope: 3. reheight tower | Mar | Mar | PT INDOJAR MULIA ABADI | PT MULTI BMITRA SEJAHTERA | Extend Pole | Extend 3m | 106.8934 | -6.2882 |  |  |  |  | Monopole 20 1Leg | Fasum Lahan TNI |  | Extend 3m | Adit | 082123012385 | [6 empty] | Extend 3m OG | Extend 3m
209 | Area 2 | JTX291 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0122 | JTX291 | TAMANDURENSAWITDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK | 08.04 : LL Masih Rundingan Keluarga, Meminta Kompensasi 15jt (Menunggu Harga Renewal Maks 12/04) 16.03 : Need Join Visit Terkait PKS, Material RFD 24.02 : Masih Menunggu Tim Perkuatan On Site, Material RFD 13.02 : Fabrikasi Material STR + Extend OG Galvanized 13.01 APD Done, Need Review & Approval Soleng DMT 05.12 Survey Analisa Extend Done, Warga Belum Mau TTD Menunggu Konfirmasi Perubahan PKS 29.12 IW Done, LL Bersedia Extend dengan merevisi PKS 24.12 Survey Extend OG (Proses IW Radius Extend) | Optimis | 2026-01-29 | Add 3 RF Add 5 RRU Final Sow Rescope: 3. reheight tower | 2026-05-08 | Mei | PT INDOJAR MULIA ABADI | PT MULTI BMITRA SEJAHTERA | Extend Pole | Extend 3m | 106.9103 | -6.2437 |  |  |  |  | Monopole 20 1Leg | Privat |  | Extend 3m | Ari | 081329816978 | [6 empty] | Extend 3m OG | Extend 3m
262 | Area 2 | JTX208 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | WO Proses | JTX208 | KEBUNBUNGADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Rehunting | Hunting | Optimis | 2026-01-29 | Add 3 RF Add 9 RRU Final Sow Rescope: 3. reheight tower |  | Apr | WO PROSES | WO PROSES | Extend Pole | Extend 3m | 106.9331 | -6.2144 |  |  |  |  | RT 12m + Pole 9m = 21m | Privat |  | Extend 3m | [9 empty] | Extend 3m
309 | Area 2 | JTX500 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0100 | JTX500 | MASJIDAMINJIDIATULAHDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 5. RFI | RFI | 21.04 : ATP Done 16.03 : STR Done, Site RFI Waiting ATP 24.02 : Masih Menunggu Tim Perkuatan On Site, Material RFD 13.02 : Fabrikasi Material STR + Extend OG Galvanized (Perkuatan Dilakukan Setelah Anugrahraya) 13.01 APD Done, Need Review & Approval Soleng DMT 05.01 Survey Analisa Extend Done 29.12 Need Support DMT untuk memperbaharui PKS lahan 24.12 LL Setuju Untuk Extend, Issue Renewal Kontrak Lahan | Optimis | 2026-01-29 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Mar | Mar | PT INDOJAR MULIA ABADI | PT MULTI BMITRA SEJAHTERA | Extend Pole | Extend 3m | 106.8768 | -6.3251 |  |  |  |  | Monopole 20 1Leg | Privat |  | Extend 3m | Ari | 081329816978 | [6 empty] | Extend 3m OG | Extend 3m
203 | Area 2 | JTX067 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0120 | JTX067 | SMP275DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | Extend Done | 21.04 : Material On Site, STR & Extend OG 08.04 : Fabrikasi STR dan Extend Done, Waiting Pickup, Belting OG 16.03 : APD Done, Fabrikasi OG, Plan RFI W2 April 05.01 Need Support Surat Pengajuan Extend 3 m Dari DMT 24.12 Menunggu Surat KKOP untuk Persetujuan Penambahan Ketinggian (Menunggu Surat Dari DMT) | Optimis | 2026-01-29 | Add 3 RF Add 10 RRU Final Sow Rescope: 3. reheight tower | 2026-04-30 | Apr | PT LAYTON ENTER PRISE | PT MULTI BMITRA SEJAHTERA | Extend Pole | Done DRM | 106.8934 | -6.2583 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 3m | Hardi Puspadana | 081311265520 | [6 empty] | Extend 3m OG | Extend 3m
85 | Area 2 | JTX249 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0124 | JTX249 | MAKASARMAKASAR12DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | Site Opening | 21.04 : Site Opening Done, Waiting Arahan TMII 08.04 : Soil Test Done, APD Rilis Plan Jumat 10/04 16.03 : Validasi Cand Q OK, OG Pengurusan KKOP 13.01 Need Validasi Cand P (-6,30268 ; 106,88860) 24.12 Menunggu Perizinan Lahan Cand (Plan 07/01) | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-15 | Mei | PT LAYTON ENTER PRISE | PT MULTI BMITRA SEJAHTERA | BTR |  | 106.8902 | -6.3006 |  |  |  |  | Monopole 20 1Leg | Fasum TMII |  | BTR | Hardi Puspadana | 081311265520 | [7 empty] | BTR
232 | Area 2 | JTX359 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0042 | JTX359 | PINTUUTAMATMIIDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 8. Lock Trial | LOCK TRIAL | 08.04 : Lock Trial TSEL 25.02 : Menunggu App TMII Join Survey 24.02 : Validasi Cand Q OK, Waiting PKS Dengan TMII 13.02 : Validasi Cand P NOK, Need Validasi Cand Q (-6,30183 ; 106,88763) 12.01 : Cand Berada Diluar TMII, Milik Yayasan Bu Tien (Sedang Kordinasi Mengenai Sewa Lahan, Paralel Menunggu Validasi 24.12 Menunggu Perizinan Lahan Cand (Plan 07/01) | Not Optimis | 2026-03-20 | Add 3 RF Add 7 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT MANDAU JAYA KONTRINDO | PT MULTI BMITRA SEJAHTERA | BTR | BTR Monopole 25m | 106.886701 | -6.301901 |  |  |  |  | Monopole 18 1Leg | Fasum TMII |  | BTR | [9 empty] | BTR
266 | Area 2 | JTX379 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0044 | JTX379 | MAKASARKRAMATJATIDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | Site Opening | 08.04 : Paralel Masih Menunggu Rekomendasi KKOP, dan Eskalasi SITAC 25.02 : diusahakan pakai rekom lurcam, RFC 5 Maret 19.02 : APD OG Process, Proses Rekomendasi Lurcam 13.02 : OG 5 KK Lagi, Hammer Test Done 19.01 : Harga Sewa 25 Juta/Tahun, Sosialisasi Warga Kamis 22/01 13.01 : Validasi OK, BAN/BAK OG 29.12 Need Validasi Cand A (106.875830 -6.278490) RT 9m + Stacking 3m + Pole 15m | Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-15 | Mei | PT MANDAU JAYA KONTRINDO | PT MULTI BMITRA SEJAHTERA | BTR | 200m arah 90 degree | 106.8738 | -6.2788 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR |  | 277777777.7778 | [7 empty] | BTR
235 | Area 2 | JTX382 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0043 | JTX382 | NUSAINDAHMALAKADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW OG | 08.04 : BAN NY Approve, Permintaan Kompensasi Warga Negosiasi Plan 13/04 25.02 : BAN 40Jt Submit To Regional, IW Paralel (Target RFC 13 Maret) 13.02 : Plan Soswar 14/02, IW Potensial OK, Harga Sewa Masih 40jt/Tahun 19.01 : Menunggu Jadwal Pertemuan Dengan Pihak P3RSR Sebagai Pengelola Lahan 12.01 : Belum Ada Balasan Dari Pihak Perumnas 05.01 Validasi OK,Menunggu Jawaban Terkait Surat Permohonan Pengelolaan Lahan Fasum Ke Perumnas 1. 18.12 Need Validasi CAN A ( 106.93347 -6.21785) GF 32m | Optimis | 2026-03-20 | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-25 | Mei | PT MANDAU JAYA KONTRINDO | PT MULTI BMITRA SEJAHTERA | BTR | BTR Lahan Masjid | 106.9334 | -6.2179 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR |  | 444444444.4444 | [7 empty] | BTR
292 | Area 2 | JTX387 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0083 | JTX387 | BUNGARAMPAIDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Rehunting | 08.04 : Hard Cand, Hard SITAC Not Optimis 25.02 : siapkan JR, Area mana yang terjadi penolakan 13.02 : Pihak RT dan Sekolah Menolak, OG Submit Cand Baru Yang Menjauh Hari Sabtu 12.01 : Negosiasi Harga OG, Paralel Rehunting SAR 200m 05.01 Validasi OK, Pihak Gereja HKBP Meminta Harga Sewa 100jt/Tahun (OG Negosiasi 1. 18.12 Need Validasi CAN A ( 106.93458 -6.2219) GF 32m 25.02 : siapkan JR, Area mana yang terjadi penolakan | Not Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Mei | PT MANDAU JAYA KONTRINDO | PT MULTI BMITRA SEJAHTERA | BTR | 120 Degree 110m | 106.9346 | -6.2215 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | [9 empty] | BTR
286 | Area 2 | JTX397 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0081 | JTX397 | TOLBAMBUAPUSTIMURDUADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | Site Opening | 08.04 : KKOP Proses Menunggu Hasil Rekomendasi 25.02 : Pararel fabrikasi, tidak pakai surat rekomendasi OG TTD Lurah hri ini, ttd camat besok, kkop (RFC 28/02) 13.02 : IW Done, Rekom OG, APD OG 21.01 : Validasi OK Can Q 19.01 : Need Validasi Cand Q (-6.30983 ; 106.89902) 12.01 : Harga Sewa Lahan 90 Jt/Tahun, Negosiasi Harga oG 05.01 Validasi OK, LL Meminta Waktu Sampai Hari Rabu 07/01 Untu Musyawarah Terkait Harga Sewa Lahan 1. 18.12 Need Validasi CAN A ( 106.89855 -6.30976) GF 32m | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-15 | Mei | PT MANDAU JAYA KONTRINDO | PT MULTI BMITRA SEJAHTERA | BTR | 130 Degree 120m | 106.8984 | -6.3091 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | [9 empty] | BTR
388 | Area 2 | BKX288 | Eastern Jabodetabek | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS09Z0034 | BKX288 | PTSOSROPENGGILINGANCAKUNGDMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK | 24.02 : Validasi OK, Harga 55jt/Tahun 13.02 : Need Validasi (-6.19282 ; 106.97100) 07/01: issue pihak gedung sulit dikontak, plan rehunting need JR kandidat diatas 4 Rehunting | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: BTR to Macro |  | Apr | PT MITRA SARANA KARYA BANGSA | PT MULTI BMITRA SEJAHTERA | BTR |  | 106.9712 | -6.1926 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [8 empty] | Lanjut BTR ketinggian 29m RT | BTR
389 | Area 2 | DPK239 | Eastern Jabodetabek | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS09B0008 | DPK239 | JLJUANDABAKTIJAYATBG | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 4. CME | Erection | 08.04 : Need NOD MP 36 Section 3m 16.03 : Rebaring Pile Cap Done, Need NOD untuk Pickup Angkur Template 24.02 : Tim CME On Site, Perapihan Lahan dan Galian OG 08.01 Site Opening Done, Menunggu DP Sewa Lahan 06.01 APD BOQ Release, Menunggu Jadwal SKOM 24.12 Rekom Lurah Done, OG Rekom Camat (Estimasi Hari Ini Done), Paralel Jadwal Soil Test | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: BTR to Mini Macro | 2026-03-17 | Apr | PT MULTI BAGASANTI MAHDY | PT MULTI BMITRA SEJAHTERA | BTR |  | 106.8483 | -6.3792 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
351 | Area 2 | JKT711 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0086 | JKT711 | JAKARTAPRIMASTEELDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW | 08.04 : IW Done, Rekom Lurcam OG Paralel Hammer Test (Menunngu Konsultan) 16.03 : Extend 6 m OK by RT/RW, IW OG 24.02 : Perihal Extend Masih Diskusikan 14.01 : Validasi OK CAN A 23.12 : Need Validasi Cand A (106.927931, -6.180525) Need Support Bersurat ke PT. HIBA UTAMA | Optimis | 2026-03-20 | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-04-28 | Apr | PT MULTI BAGASANTI MAHDY | PT MULTI BMITRA SEJAHTERA | BTR |  | 106.9281 | -6.1795 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Herlina | 081310994005 | [7 empty] | BTR
311 | Area 2 | JSA012 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0064 | JSA012 | SEKOLAHKOMANDOTNIALDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW | 08.04 : IW Kurang 3 Orang Dari 8 Orang (Plan Done 13/04) 24.02 : OK untuk Extend 3m 21.01 : Validasi OK Can B 19.01 : Need Validasi Cand B (-6.24036 ; 106.77792) 29.12 Need Validasi Cand A (106.78007, -6.23877) | Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-18 | Mei | PT MULTI BAGASANTI MAHDY | PT MULTI BMITRA SEJAHTERA | BTR | 270' 150m | 106.7779 | -6.2404 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 3m | Herlina | 081310994005 | [6 empty] | Extend 3m OG | Extend 3m
215 | Area 2 | JTX211 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0015 | JTX211 | KESATRIAN3DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW | 08.04 : Extend 3 m, IW OG (Berapa/Berapa) Plan Done 17/04 24.02 : Diskusi LL Terkait Extend 21.01 : Validasi NOK Can A 29.12 : Need Validasi Cand A (106.87003, -620384) | Optimis | 2026-03-20 | Add 3 RF Add 11 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-22 | Mei | PT MULTI BAGASANTI MAHDY | PT MULTI BMITRA SEJAHTERA | BTR | 170m arah 150 degree | 106.869 | -6.2017 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Herlina | 081310994005 | [6 empty] | Propose BTR Utara (30 degree) | BTR
195 | Area 2 | JTX255 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0118 | JTX255 | SUMURUTARADURENSAWITDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. Sitac | IW Done | 24.04 NBAE meminta untuk extend 4m 05.01 IW Done, Paralel Rekom dan Menunggu Jadwal Survey by Konsultan 29.12 Proses IW Extend Pole OG | Not Optimis | 2026-01-29 | Add 3 RF Add 11 RRU Final Sow Rescope: 3. reheight tower |  |  | PT MULTI BAGASANTI MAHDY | PT MULTI BMITRA SEJAHTERA | Lock Trial | Extend 3m | 106.9129 | -6.2162 |  |  |  |  | Monopole 20 1Leg | Privat |  | Extend 3m | Warnoko | 081284619397 | [7 empty] | Lock Trial
256 | Area 2 | JTX310 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0050 | JTX310 | KLENDERDURENSAWITDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | Site Opening | 08.04 : APD Rilis Hari Ini, Dokumen SITAC Clear Pengajuan DP dan NOD OG 16.03 : Rekom Done, Soil Test OG 24.02 : Harga 26 Jt/Tahun, IW OG 19.02 : Validiasi Cand B OK, BAN/BAK OG 19.01 : Need Validasi Cand B (-6.21789 ; 106.90768) 1. Validasi NBAE NOK : 18/12/2025 (Cand P : -6.22179,106.90643) | Optimis | 2026-03-20 | Rehunting | 2026-04-30 | Apr | PT MULTI BAGASANTI MAHDY | PT MULTI BMITRA SEJAHTERA | BTR | 200m arah 180 degree | 106.9073 | -6.2188 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Herlina | 081310994005 | [7 empty] | BTR
263 | Area 2 | JTX327 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0049 | JTX327 | POMADPASARREBODMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Validasi | 08.04 : Menunggu Hasil Validasi 24.02 : Minta Digeser Titiknya Sudah Submit 19.02 : Masih Menunggu Jadwal Bertemu Komandan 04/02/26 : Validasi OK Cand R (-6.32824,106.84452) 19.01 : Need Validasi Cand B (-6.32828 106.84525) Need Validasi Cand C (-6.32824 ; 106.84452) 12.01 : Validasi OK, Nego Sewa Lahan OG 05.01 Need Validasi Cand A (106.84525 ; -6.32828) | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-25 | Mei | PT MULTI BAGASANTI MAHDY | PT MULTI BMITRA SEJAHTERA | BTR | 200m arah 90 degree | 106.8448 | -6.3284 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Herlina | 081310994005 | [7 empty] | BTR
239 | Area 2 | JTX381 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 24TS08Z0002 | JTX381 | UTANKAYUUTRMATRAMANINDAHDMT | Plan ≥ 2026 | RESCOPING |  | 0. ATP | ATP | RFI (Solution Issue lahan eksisting Gusur LRT) | Optimis | RFI : 06/11/2024 | Solution, menggunakan project Solution, terkait project program pembebasan untuk LRT, on air | RFI | Done RFI | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | BTR | RFI DONE | 106.8595 | -6.1955 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [5 empty] | 1.5 | 1.5 | 3 |  | Extend 6m
317 | Area 2 | JTX502 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0039 | JTX502 | JLRADENINTEN2DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 7. DROP | DROP | Propose Drop | Not Optimis | 2026-02-22 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  |  | PT MULTI BAGASANTI MAHDY | PT MULTI BMITRA SEJAHTERA | Lock Trial | BTR Arah 150m 100 degree | 106.9193 | -6.2415 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Terminate | Warnoko | 081284619397 | [7 empty] | Lock Trial
319 | Area 2 | JTX507 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0035 | JTX507 | JALANDUYUNGRAWAMANGUNDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | Hammer Test | 08.04 : Hammer Test OG, Kompensasi RW 20jt Need Approval 24.02 : Need Analisa 23/01/26 : Need Validasi Cand Q (-6.19644,106.89404) validasi OK 19.01 : Need Validasi Cand B (-6.19644 ; 106.89404) 29.12 Validasi NOK, Rehunting 18.12 Need Validais CAN A (106.89483 -6.19704) | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-13 | Mei | PT MULTI BAGASANTI MAHDY | PT MULTI BMITRA SEJAHTERA | BTR | BTR Arah 100m 340 degree | 106.8942 | -6.1972 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Herlina | 081310994005 | [7 empty] | BTR
212 | Area 2 | JTX510 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0038 | JTX510 | KOMPLEKKEBAKARANDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 3. RFC | RFC | 08.04 : Need Follow Up Penggunaan SST 42m (APD Done) 16.03 : APD Rilis, Plan SKOM Setelah Lebaran 24.02 : Soil Jumat 27/02, APD Senin 02/03, SKOM Selasa 03/03 19.02 : IW Done, Rekom OG, Collect Document LL 19.01 : Harga Sewa Lahan 35 Juta/Tahun, (Paralel Rehunting, LL Tidak Mau Nego) 29.12 Validasi Cand A OK, Nego Sewa Lahan OG 18.12 Need Validais CAN A (106.87897 -6.33107 ) | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-08 | Mei | PT MULTI BAGASANTI MAHDY | PT MULTI BMITRA SEJAHTERA | BTR | BTR Arah 100m 250 Degree | 106.879 | -6.3313 |  |  |  |  | Monopole 20 1Leg | Fasum | 32 m | BTR | Herlina | 081310994005 | [7 empty] | BTR
278 | Area 2 | JTX388 | Jabat |  | Non MKT | Non MKT | 0 | Non-HBTS | NY | JTX388 | RAWAPULOKAMBINGDMT | Plan ≥ 2026 | MCP |  | NY DRM |  |  | NY DRM |  | site non BTSH (site MCP) |  |  |  |  | MCP |  | 106.9106 | -6.19 |  |  |  |  | Monopole 25 1Leg |  |  | NON BTSH | [9 empty] | MCP
277 | Area 2 | JTX391 | Jabat |  | Non MKT | Non MKT | 0 | Non-HBTS | NY | JTX391 | RAWASUMURBARATDMT | Plan ≥ 2026 | MCP |  | NY DRM |  |  | NY DRM |  | site non BTSH (site MCP) |  |  |  |  | MCP |  | 106.9147 | -6.2066 |  |  |  |  | Monopole 25 1Leg |  |  | NON BTSH | [9 empty] | MCP
334 | Area 2 | JTX394 | Jabat |  | Non MKT | Non MKT | 0 | Non-HBTS | NY | JTX394 | PULOLENTUTRAYADMT | Plan ≥ 2026 | MCP |  | NY DRM |  |  | NY DRM |  | site non BTSH (site MCP) |  |  |  |  | MCP |  | 106.9151 | -6.1894 |  |  |  |  | Monopole 25 1Leg |  |  | NON BTSH | [9 empty] | MCP
276 | Area 2 | JTX395 | Jabat |  | Non MKT | Non MKT | 0 | Non-HBTS | 25TS08N1768 | JTX395 | KYOESTEELDMT | Plan ≥ 2026 | MCP |  | NY DRM |  |  | NY DRM |  | site non BTSH (site MCP) |  |  |  |  | MCP |  | 106.9092 | -6.1961 |  |  |  |  | Monopole 25 1Leg |  |  | NON BTSH | [9 empty] | MCP
275 | Area 2 | JTX396 | Jabat |  | Non MKT | Non MKT | 0 | Non-HBTS | NY | JTX396 | RAWAGEMILANGLIMADMT | Plan ≥ 2026 | MCP |  | NY DRM |  |  | NY DRM |  | site non BTSH (site MCP) |  |  |  |  | MCP |  | 106.9114 | -6.1999 |  |  |  |  | Monopole 25 1Leg |  |  | NON BTSH | [9 empty] | MCP
165 | Area 2 | JTX098 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0115 | JTX098 | SQUADRONHALIM3DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK | 08.04 : Need Support Partnership DMT Untuk Masuk Ke KASEMKOM 16.03 : Belum Ada Respon Dari KASEMKOM, NEED Support Partenrship DMT 13.02 : Sampai Saat Ini Blm Ada Surat Untuk Ke Kasemkom 19.01 : Need Surat DMT Ke Kasemkom 05.01 Need Support Surat Pengajuan Extend 3 m Dari DMT 29.12 Need Surat Pengajuan Extend 3m 18.12 : Pengurusan Lingkungan Extend 3m | Not Optimis | 2026-01-29 | Add 3 RF Add 5 RRU Final Sow Rescope: 3. reheight tower |  | Apr | PT SAMANTA FIBRA ABADI | PT MULTI BMITRA SEJAHTERA | Extend Pole | Done DRM | 106.8861 | -6.2756 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 3m | Herlina | 081310994005 | [6 empty] | Extend 3m OG | Extend 3m
206 | Area 2 | JTX241 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0098 | JTX241 | JLERAMAS2000DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Rehunting | 08.04 : Hunting BTR dan Extend Fail (Not Optimis) 16.03 : Plan Extend Pole Gagal, Ada Penolakan Warga 13.02 : Opsi Extend di Lahan Eksisting OG 05.01 Need Arahan Hunting (Hard Cand dan Hard SITAC) 18.12 : HARD CANDIDAT JR DONE | Not Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT SAMANTA FIBRA ABADI | PT MULTI BMITRA SEJAHTERA | BTR |  | 106.9483 | -6.2075 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 6m | Herlina | 081310994005 | [6 empty] | Extend 6m | Extend 6m
208 | Area 2 | JTX257 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0117 | JTX257 | JATINEGARAKAUMSELATANDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Validasi | 08.04 : Need Validasi Cand -6.20817 ; 106.89864 16.03 : Hard Cand, Rehunting Belum Dapat Kandidat Lagi 13.02 : IW Kurang 1 Warga, Menghindari Penolakan Tinggi Turun Ke 25 m (Menunggu Approval) 19.01 : Harga Sewa Lahan 29 Juta/Tahun, IW Sounding OG 12.01 : Nego Sewa Lahan, 75 JT/Tahun 05.01 Validasi OK, Negosiasi Sewa Lahan OG 1. 18.12 : Need Validasi CAN B (106.89923 -6.20902) GF 32m | Optimis | 2026-01-29 | Add 3 RF Add 9 RRU Final Sow Rescope: 3. reheight tower | 2026-05-25 | Mei | PT SAMANTA FIBRA ABADI | PT MULTI BMITRA SEJAHTERA | Extend Pole | Extend 3m | 106.8985 | -6.2087 |  |  |  |  | Monopole 20 1Leg | Privat |  | Extend 3m | Herlina | 081310994005 | [6 empty] | Extend 3m OG | Extend 3m
260 | Area 2 | JTX383 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0101 | JTX383 | MELATIASEMGEDEMATRAMANDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW OG | 08.04 : Hard SITAC Extend (Not Optimis) 16.03 : Belum Ada Konfirmasi Pertemuan 13.02 : Butuh Waktu Pembahasan PKS Dengan RT dan Warga 05.01 Need Info Mengenai PKS Terbaru, PKS Yang Dikirim sudah Expired 29.12 Need PKS Baru 18.12 : Pengurusan Lingkungan Extend 3m | Optimis | 2026-01-29 | Add 3 RF Add 6 RRU Final Sow Rescope: 3. reheight tower |  | Apr | PT SAMANTA FIBRA ABADI | PT MULTI BMITRA SEJAHTERA | Extend Pole | Extend 3m | 106.8562 | -6.2079 |  |  |  |  | Monopole 20 1Leg | Fasum Lahan TNI |  | Extend 3m | Herlina | 081310994005 | [6 empty] | Extend 3m OG | Extend 3m
603 | Area 2 | JTX412 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JTX412 | CIBUBURRAYADMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.8691 | -6.3422 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
234 | Area 2 | JTX398 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0012 | JTX398 | LAPANGANKENANGADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK | 08.04 : Harga 35Jt/Tahun, Pergeseran Lokasi Belum Final (Fixsasi Minggu Ini) 16.03 : Pihak Kampus Sedang Mengkondisikan Lokasi Baru, Lokasi Sebelumnya Ada Rencana Pembangunan 13.02 : Menunggu Jawaban Dari Pihak Yayasan Kampus 12.01 : Validasi OK, Negosiasi OG 05.01 Need Validasi Cand Q 29.12 Menunggu Konfirmasi LL untuk disewakan 1. Validasi NBAE NOK : 18/12/2025 (Cand P : -6.31406,106.89728) 2. 19.12 Need Validasi CAN B (106.89728 -6.31406) GF 32m | Optimis | 2026-03-20 | Rehunting | 2026-05-25 | Mei | PT SAMANTA FIBRA ABADI | PT MULTI BMITRA SEJAHTERA | BTR | 200m arah 275 degree | 106.9 | -6.3149 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Herlina | 081310994005 | [7 empty] | BTR
265 | Area 2 | JTX408 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0037 | JTX408 | JAYASAKTI3DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Rehunting | 08.04 : Rehunting Cand (Extend Fail LL Menolak) 16.03 : Hard SITAC, Proposed Extend 3m 13.02 : Opsi Extend di Lahan Eksisting OG 01/02/26 : Rehunting 19.01 : Validasi OK, OG Nego Sewa Lahan 05.01 Validasi Cand P (-6.33659 ; 106.860330) 29.12 HARD CANDIDAT JR DONE | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-25 | Mei | PT SAMANTA FIBRA ABADI | PT MULTI BMITRA SEJAHTERA | BTR | 200m arah 90 degree | 106.8598 | -6.3352 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Herlina | 081310994005 | [7 empty] | BTR
252 | Area 2 | JTX410 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0041 | JTX410 | PALEMKARTIKAKOMPLEKTNIADDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | Site Opening | 16.03 : Waiting DP Lahan, Start Plan Setelah Lebaran 13.02 : Rekom Done, APD Done, Menunggu FInal MKT 27 m 01/02/26 : waiting approval BAN from DMT 12.01 : Harga Masih Tinggi, Paralel Rehunting 05.01 Negosiasi Harga OG, Paralel Rehunting 29.12 Harga Sewa 70jt/Tahun, OG Nego Paralel Rehunting Validasi NBAE OK : 18/12/2025 (Cand P : -6.3111,106.896) | Optimis | 2026-03-20 | 1. 18.12 BAN/BAK OG | 2026-05-15 | Mei | PT SAMANTA FIBRA ABADI | PT MULTI BMITRA SEJAHTERA | BTR | 300m arah 270 degree | 106.8992 | -6.312 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Herlina | 081310994005 | [7 empty] | BTR
284 | Area 2 | JTX418 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0070 | JTX418 | RAYAJENGKIKEBONPALADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | Site Opening | 16.03 : Waiting DP Lahan, Start Plan Setelah Lebaran 13.02 : IW Done, Rekom OG 28.01 : Need Validasi Cand B (-6.25066 ; 106.86941) 19.01 : IW Fail (Warga Provokatif), OG Rehunting 13.01 : IW Sisa 2 Warga Belu Bersedia 12.01 : BAN/BAK 27 Jt/Tahun Approve, IW OG 05.01 Validasi OK, Negosiasi Sewa Lahan OG 1. 18.12 : Need Validasi CAN A (106.87021 -6.25085) RT 4 + pole 20m | Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-15 | Mei | PT SAMANTA FIBRA ABADI | PT MULTI BMITRA SEJAHTERA | BTR | 110 degree arah 120m | 106.8693 | -6.2505 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Herlina | 081310994005 | [7 empty] | BTR
230 | Area 2 | JTX471 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | WO Proses | JTX471 | DEPNAKER2DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 5. RFI | RFI | Hunting | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Done RFI | WO PROSES | WO PROSES | BTR |  | 106.8518 | -6.2863 |  |  |  |  | Monopole 20 1Leg | Fasum | 32m | Reloc Tower DMT | [8 empty] | Validasi OK Reloc To Monopole DMT 32m (106.85034 -6.28606) | Reloc to existing MTEL
590 | Area 2 | JTX476 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0122 | JTX476 | KEMANDORAN7DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 0. ATP | ATP OK | 16/03/26 : ATP done 09/02/26 PLN & Pondasi RBS done, Plan penyelesaian Perkuatan tower 25/01/2026 PLN OG | Optimis | 2025-12-28 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | ATP OK | Done RFI | PT INFRAKO DAYAMITRA | PT TRITECH CONSULT | Reloc to existing MTEL | Reloc Ke Tower terdekat DMT (106.9368333 -6.20561115) | 106.9367 | -6.205881 |  |  |  |  | Monopole 20 1Leg | Privat | 42m | Reloc Tower DMT |  |  | Lahan mesjid | Hexagonal | [5 empty] | Reloc to existing MTEL
610 | Area 2 | JTX490 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JTX490 | KOMPANGGREKLOKADMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.8991 | -6.3456 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
612 | Area 2 | JTX491 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JTX491 | PAMITRANCIJANTUNGDMT | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.857 | -6.3217 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
306 | Area 2 | JTX493 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS09B0011 | JTX493 | TAMANBAMBUDMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 4. CME | CME OG | 05/05/26 : Wait DP lahan, PLN OK 22/04/26 : Menunggu dp lahan (erection belum bisa) 21/04/26 : pekerjaan sementara dihentikan LL terkait pembayaran DP belum terealisasi (Menunggu pembayaran DP lahan) 15/04/26 : Curing time day 7 14/04/26 : Curing time day 6, pekerjaan sementara dihentikan LL terkait pembayaran DP belum terealisasi 13/04/26 : Curing time day 5 12/04/26 : Curing time day 4 11/04/26 : Curing time day 3 10/04/26 : Curing time day 2 09/04/26 : Curing time day 1 08/04/26 : Pouring done, menunggu dp lahan 07/04/26 : Plan pouring Rabu, 08 April 2026 05/04/26 : Galian OG (Galian Bore ke 8) 01/04/26 : Galian OG 31/03/26 : Galian OG 29/3/26: Galian OG 16/03/26 : NOD OK, template OK, DP belum di bayar 04/03/26 : Menunggu NOD, DP high capex 25/02/26: Menungu NOD & DP sewa lahan 22/01/26 : Menunggu NOD, Menunggu DP sewa lahan 21/1/26 : SKOM done 20/01/26 : Submit APD, Plan SKOM 21/1/26 15/01/26: Plan Soiltest 13/01/26: Rekom Lurah OG, BAN/BAK done, IW done 05/01: Wait approval BAN (325jt/10 tahun) by Mitratel 01/12 : Wait approval BAN (325jt/10 tahun) by Mitratel 26/11 : Wait approval BAN (325jt/10 tahun) 20/11 : Sinergi submit BAN/BAK (325jt/10th) 19/11 : Need Validation cand. B (-6.30311 106.91530) 7/11 : BAN/BAK OG, LL masih di luar kota, potensi IW 75% 31/10 : Validasi OK | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-25 | Mar | PT SINERGI REKTA DENTA | PT TRITECH CONSULT | BTR |  | 106.9155 | -6.3033 |  |  |  |  | Monopole 20 1Leg |  | MP32m | BTR | 6x6 | 361111111.1111 |  |  |  | 1.5 | 1.5 | 3 | MP32m | Extend 6m
283 | Area 2 | JTX419 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0036 | JTX419 | HAJIYAHYAKPMELAYUDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 1. SIS/SES | Rehunting | 08.04 : Possible Extend 6 m (Menunggu Diskusi Warga Terkait Kompensasi Extend) 16.03 : High Price 150jt/Tahun, Need Arahan 13.02 : Menunggu FInalisasi Harga 19.01 : Need Validasi Cand B (-6.34063 ; 106.87640) 12.01 : Validasi NOK, Rehunting Sesuai Arahan 05.01 Validasi Cand P ( 29.12 Menunggu Konfirmasi LL untuk disewakan | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-25 | Mei | PT SAMANTA FIBRA ABADI | PT MULTI BMITRA SEJAHTERA | BTR | BTR Arah 320m 0 degree | 106.8749 | -6.3405 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Herlina | 081310994005 | [7 empty] | BTR
89 | Area 2 | JTX460 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0107 | JTX460 | TMII6DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK | 08.04 : Soil Test Done, IW OG (Plan Done 12/04), APD Rilis Jumat 10/04 16.03 : KKOP OG, Need Izin Soil Test dari TMII 19.01 : Need Validasi Cand P 24.12 Menunggu Perizinan Lahan Cand (Plan 07/01) | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | 2026-05-15 | Mei | PT SAMANTA FIBRA ABADI | PT MULTI BMITRA SEJAHTERA | BTR | BTR Monopole 25m | 106.902 | -6.3032 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR | Herlina | 081310994005 | [7 empty] | BTR
380 | Area 2 | BKX116 | Eastern Jabodetabek | In Hand | Non MKT | Non MKT |  | BTSH | 25TS09Z0029 | BKX116 | PALEMBARAT12DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 2. SITAC | IW | 08.04 : BAN/BAK 35Jt, IW OG Kurang 2 KK (Plan Sabtu 11/04) | Optimis | 2026-03-20 | 12.12 validasi NOK, rehunting kandidat ke 4 | 2026-05-25 | Mei | PT SUMBERSOLUSINDO HITECH | PT MULTI BMITRA SEJAHTERA | BTR |  | 106.9809 | -6.2652 |  |  |  |  | Monopole 18 1Leg |  |  | BTR | [9 empty] | BTR
378 | Area 2 | BKX163 | Eastern Jabodetabek | In Hand | Non MKT | Non MKT |  | BTSH | 25TS09Z0032 | BKX163 | JATIASIHKALIMANTANDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 2. SITAC | IW | 08.04 : Informasi Bangun Tower Baru Hold Untuk Kota Bekasi, Plan Extend 6 m (Need Soswar 08/04) 25.02 : 2 Warga Menolak Sudah Diberikan Surat Jaminan, Paralel Kordinasi Extend Eksisting, Target 06/03 10.01 Sosialisasi Warga Ulang | Optimis | 2026-04-06 | 12.12 proses IW dan proses BAN/BAK | 2026-05-08 | Mei | PT SUMBERSOLUSINDO HITECH | PT MULTI BMITRA SEJAHTERA | BTR |  | 106.9707 | -6.2914 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
108 | Area 2 | JTX505 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0121 | JTX505 | JENGKIKEBONPALA | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 7. DROP | BAN/BAK | 22/04/26 : Ada permintaan LL sebesar 12jt utk kompensasi extend pole 3m 01/04/26 : Extend 6m, LL sudah setuju, mitra akan konsultasi dgn konsultan untk desaign extend nya 16/3/26: Proposed extend hanya bisa 3m(issue space lahan), paralel Proses BAN/BAK 09/03/26 : Proses izin extend tower (belum bertemu LL karna sedang berada diluar kota) 28/1/26 : Pihak kawasan Halim meminta surat permohonan ke Mitratel 27/01/26 : Pengajuan dari Halim menunggu proses surat permohonan kerja sama. 13/01/26: Validasi NBAE NOK, rehunting 05/01/26 : Need Validation 24/12/25 : Need Validasi CAN P ( 106.880015 -6.251693 ) RT 5 Lantai + Pole 6 m | Not Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | APD : 8/4/26 | Apr | PT MULTI BAGASANTI MAHDY | PT TRITECH CONSULT | BTR | 300' 100m | 106.8822 | -6.2573 |  |  |  |  | Monopole 20 1Leg | Fasum | extend 3m | Terminate |  |  | Lahan warga | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 3 m Lock Trial | HOLD By Tsel (Propose DROP)
368 | Area 2 | BKX173 | Eastern Jabodetabek | In Hand | Non MKT | Non MKT |  | BTSH | 25TS09Z0030 | BKX173 | BINTARACIPTABARATDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | 08.04 : RFI Done, ATP Done 16.03 : Site SRFI Menunggu PLN Koneksi 25.02 : Jumat Start CME 06.01 Menunggu DP Sewa Lahan 05.01 APD Release, SKOM Today 24.12 Hammer Test Done, Proses APD OG (SITAC Clear) | Optimis | 2026-03-12 | 12.12 Rekom OG 10.12 Rekom OG |  | Mar | PT SUMBERSOLUSINDO HITECH | PT MULTI BMITRA SEJAHTERA | BTR |  | 106.9569 | -6.23 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
379 | Area 2 | BKX174 | Eastern Jabodetabek | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS09Z0033 | BKX174 | JLDARAMAHKOTADMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 3. RFC | RFC | 08.04 : MP 25m Menunggu Persetujuan Warga 2 Orang (Plan 12/04), Rekom Camat NY, Status RFC 25.02 : Dokumen SITAC TTD Camat Kamis, Target RFC 27/02 13.02 : SKOM Senin 15 Februari 2026 13.01 : Rekom Lurcam OG, Soil Test Plan Kamis 15/01 05.01 Proses Meminta TTD Satu RT Lagi | Optimis | 2026-04-06 | Add 3 RF Add 6 RRU Final Sow Rescope: BTR to Mini Macro | 2026-05-15 | Mei | PT SUMBERSOLUSINDO HITECH | PT MULTI BMITRA SEJAHTERA | BTR |  | 106.923 | -6.2621 |  |  |  |  | Monopole 18 1Leg |  |  | BTR | [9 empty] | BTR
228 | Area 2 | JTX611 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JTX611 | RELOCBATUAMPAR ex NUSA1KRAMATJATI | Plan ≥ 2026 | BTS HOTEL |  | 7. DROP | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.858 | -6.2935 |  |  |  |  | Monopole 20 1Leg |  |  | Terminate | [9 empty] | Lock Trial
160 | Area 2 | JUX011 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0436 | JUX011 | PLUITSAMUDRA1DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 7. DROP | Justifikasi Report | HARD CANDIDAT Propose DROP | Not Optimis | 2026-02-14 | Propose Drop Terminate |  | DROP | PT NAER TUNAS INDONESIA | PT ATRYA REKAYASA | Terminate |  | 106.7963 | -6.1089 |  |  |  |  | Monopole 15 1Leg |  |  | Terminate | [8 empty] | Terminate | Terminate
301 | Area 2 | JUX048 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0084 | JUX048 | JLSWATIRTAKBBAWANGDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG IW done | 22/04/26 : Wait approved BAN BAK (43jt/thn) 16/04/26 : Waiting approval BAN BAK (43jt/thn), IW done 08/04/26 : Wait approval BAN (43jt/thn) 05/04/26 : Wait Approval BAN (43jt/th) IW Done 1/4/26: Wait Approval BAN(45jt/th) IW done 16/03/26 : Wait approved BAN BAK (45jt/thn) 25/02/26: IW done, waiting approval BAN 4. 28/1/26 : BAN/BAK (45jt/thn) OG, IW OK 3. 13/01/26: Validasi NBAE OK (can P :-6.11942 106.884335) Lanjut BAN/BAK 2. 05/01/26 : Need Validasi CAN P ( 106.88435 -6.11942) GF 32m 1. 22.12 Need Validasi CAN P ( 106.88435 -6.11942) GF 32m | Optimis | 2026-03-20 | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | w3 Mei 2026 | Mar | PT GEAF SOLUSIANDA PRATAMA | PT TRITECH CONSULT | BTR | 340 Degree arah 60m | 106.8842 | -6.1201 |  | 106.8843 | -6.1194 | JL ENIM 2 NO 84 RT 007/003 KEL.SUNGAI BAMBU KEC.TANJUNG PRIUK JAKARTA UTARA | Monopole 20 1Leg |  | MP32m | BTR | 3x4 | 477777777.7778 | dalam lahan berpagar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | MP 32m | BTR
268 | Area 2 | JUX051 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | WO Proses | JUX051 | PELABUHANKALIADEMPLUITDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | SITAC | Extend 6m | Extend 6m | Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | WO PROSES | WO PROSES | BTR | 200m arah 300 degree | 106.7714 | -6.1061 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 6m | Didin | [7 empty] | Extend 6m | Extend 6m
285 | Area 2 | JUX053 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0082 | JUX053 | ATTAQWATUGUPERMAIDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | Propose Drop | Justifikasi Report | 04/03/26 : SUbmit JR, comcase 25/02/26: submit JR, menunggu arahan Mitratel, tidak bisa extend krn penolakan warga 09/02/26 : Mitra Submit JR 30/01/26 : Need Validasi Cand R ( -6.12762,106.91191), Validasi OK Cand R 28/01/26 : Plan JOVIS 29/1/26 13/01/26 : Validasi cand Q NOK, rehunting new cand K3. 26.12 Need Validasi CAN Q ( 106.90889 -6.12845 ) GF 25m 2. Validasi NBAE Not OK /reject : 23/12/2025 ( Rehunting as note) 1. 22.12 Need Validasi CAN P ( 106.91053 -6.12514 ) RT 10m + 15m | Not Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT AJIAN TRI SUKSES | PT TRITECH CONSULT | BTR | BTR Arah 100m 90 degree | 106.9104 | -6.1269 |  | 106.9119 | -6.1276 |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | Taman | Tubular | Flenge Luar | 1,5 | 1,5 | 3 |  | BTR
140 | Area 2 | JUX178 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0413 | JUX178 | SWASEMBADATIMUR21DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 2. SITAC | APD | 21/04/26 : Revisi ketinggian APD dengan menggunakan MP 30 utk 23 space 04/02/26 : Schedule visit dengan konsultan mengakomodir ketinggian 32 karna keterbatasan lahan 5/1/202 Proses APD, Monopole 32M TARGET CLEAR REKOM 19 DESEMBER 2025 (GF MONOPOLE 30 METER) | Optimis | 2026-02-14 | 12.12 4.12 proses rekom, Lanjut B2R | W4 2026 | Mar | PT NAER TUNAS INDONESIA | PT ATRYA REKAYASA | BTR |  | 106.8877 | -6.1188 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
229 | Area 2 | JUX209 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0093 | JUX209 | JLWARAKAS4DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | Propose Drop | IW OG | 22/04/26 : Negosiasi kompensasi IW (awal 5jt/kk total 17kk) 08/04/26 : Negosiasi ulang 11/4/26 1/4/26: Proses negosiasi kompensasi warga( plan 5/4/26) 16/3/26: Untuk site NOM(eksisting) Info RT warga mengajukan kompensasi 5jt/kk (17 KK) jika akan dilanjutkan extend 6m, 04/03/26 : Rehunting 25/02/26: Need Validasi CAN Q(106.87946 -06.12011) RT 8.5m + Pole 9 9. 26/01/26 : IW Failed 8. 15/1/26 : 3 warga tetap menolak tower, paralel rehunting 7.13/01/26: IW OG ( proses nego 3 warga radius) 6.07/01: BAN/BAK OG nego (40jt/th) plan submit BAN 08/01 5. 05/0126: Validasi NBAE OK 4. 05/01 Need Validasi CAN P (106.87872 -6.12065) RT 8 + Pole 20m 3. Penolakan warga untuk di bongkar, submit datek cand P 05.01.2026 2. Paralel hunting cand. P 1. 23.12.2025 : Rehunting karena site eksisting ada issue warga, plan submit datek 30.12.2025 | Optimis | 2026-01-29 | Add 3 RF Add 9 RRU Final Sow Rescope: 3. reheight tower | Info : 11/4/26 |  | PT SUMBERSOLUSINDO HITECH | PT TRITECH CONSULT | Extend Pole | Done DRM | 106.8798 | -6.1207 |  | 106.8787 | -6.1207 |  | RT 7m + Pole 9m = 16m | Fasum | extend 6m | Extend 3m |  |  | Rooftop | Pole | Pole | 3 | 5 | 8 | Extend 3m OG | Extend 3m
218 | Area 2 | JUX247 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0128 | JUX247 | JALANANANTARAYADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | IW OG | 22/04/26 : IW OK, tanda tangan komandan SATANG AIR 24/4/26 08/04/26 : IW OG, Penjadwalan ulang pertemuan dgn SATANGAIR 1/4/26: IPPT sudah ditunjukan, pihak SATANGAIR sudah setuju secara lisan, paralel proses IW (4KK), plan soil test 7/4/26 16/3/26: Komandan SATANGAIR AL mengklaim lahan tower masuk lahan mereka,meminta PKS eksisting sebelum kelanjutan proses extend towr eksisting 04/03/26 : IW done, extend 6 m 25/02/26: hasil koordinasi dengan pihak koramil mempertanyakan legalitas site eksisting, jika ada bisa lanjut sudah direquest ke DMT 5. 26/01/26 : planing bertemu dengan warga & pengurus lingkungan 27/01/26 4. 15/1/26 : IW +/- 10 warga, soswar 22 Jan 26 3. 13/01/26 plan pertemuan perangkat lingkungan 2. Plan 07.01.2026 meeting dengan perangkat lingkungan (RT/RW) 1. Submit datek 31.12.2025 | Optimis | 2026-01-29 | Add 3 RF Add 6 RRU Final Sow Rescope: 3. reheight tower | Pertemuan dgn SATANGAIR : 10/4/26 | Apr | PT SUMBERSOLUSINDO HITECH | PT TRITECH CONSULT | Extend Pole | Extend 3m | 106.9226 | -6.1322 |  |  |  |  | Monopole 20 1Leg | Fasum | extend 6m | Extend 3m |  |  | Taman | Tubular | Flenge Luar | 1,5 | 1,5 | 3 | Extend 6 m | Extend 6 m
174 | Area 2 | JUX263 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0099 | JUX263 | SUNTERKARYAUTARADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK | 27/04/26 : Mitra submit APD ke sol eng 16/4/26 01/04/26 : Menunggu APD dari konsultan, 10/03/26 : Koordinasi dgn Konsultan survey lokasi 04/03/26 : Hard candidate, optional extend 6 m 04/02/26 : Menunggu Arahan TSEL, 03/02/26 : Menunggu persetujuan re-NOM 11/01/26: JR Submited 08/01/26 : Submit JR, menunggu arahan DMT 07/01/26 : masih optimis OG koordinasi penggunaan lahan RW ( plan submit datek 09/01) Plan submit datek 12.1.2026 Rehunting Candidate P, Menunggu jawaban dari para pemilik ruko/rukan | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | DROP | PT DENTRA MITRA ABADI | PT TRITECH CONSULT | BTR | ke gedung sebelah | 106.8684 | -6.14 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | dalam lahan berpagar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 6m | BTR
201 | Area 2 | JUX264 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0096 | JUX264 | MASJIDALMANARDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | Rekom Lurah | 1/4/26: APD done, plan request NOD 1/4/26. Rekom lurah OG plan done 8/4/26 13/03/26 : submit APD 05/03/26: BAN Approve , plan soil test 04/03/26: Soiltest menunggu approval BAN(35jt/th) 25/02/26: Soil test menunggu approval BAN 8. 05/02/26 : IW Done 7. 04/02/26 : Mediasi warga OG target IW done 6 feb 26 6. 03/02/26 : Need Validasi Cand B ( -6.12346,106.88474) 5. 19/01/26 : Untuk menghindari warga yang menolak, lokasi digeser kearah barat 30m, parallel progress IW 4. IW 70% , BAN/BAK menunggu approval (28jt/tahun) segera di submit ke Mitratel 3. 26/12/2025 BAN /BAK Done 2. Validasi NBAE OK : 23/12/2025 (Cand P : -6.12343,106.885) 1. 18.12 Need Validasi CAN P (106.885000 -6.123430) GF 25m | Optimis | 2026-03-20 | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | W4 april 26 | Mar | PT DENTRA MITRA ABADI | PT TRITECH CONSULT | BTR | Arah 160m 0 degree | 106.885 | -6.1242 |  | 106.8847 | -6.1235 | Jl. Bakti no 7E RT 003/013, kelurahan kebon bawang,kecamatan tanjong priok, Jakarta utara | Monopole 20 1Leg | Fasum |  | BTR |  |  | dalam lahan mesjid | Tubular | Flenge dalam | 1.5 | 1.5 | 3 |  | BTR
216 | Area 2 | JUX265 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0100 | JUX265 | PERTAMINADEPOPLUMPANGDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | Rekom Lurah | 27/04/26 : Skom done (17/4/26) 01/04/26 : APD done, plan request NOD 1/4/26. Rekom lurah OG plan done 8/4/26 13/03/26 : Submit APD 05/03/26 : Need Validasi Cand Q (-6.13299,106.90109) 05/03/26: BAN Approve plan soil test 04/03/26: IW done, Soiltest menunggu approval BAN (35jt/th) 25/02/26: Soil test menunggu approval BAN 8. 06/02/26 : IW DONE 7. 04/02/26 : Mediasi warga OG target IW done 5 feb 26 6. 20/01/26 : Akan dilakukan soswar dan rapat DKM 5. 11/01/26: Revisi BAN OG , IW OG 50% 4. BAN/BAK menunggu approval (35jt/thn) plan submit 07.01.2026, IW 60% 3. 26/12/2025 BAN /BAK Done 2. Validasi NBAE OK :23/12/2025 ( Cand P : -6.13310,106.90113) 1. 18.12 Need Validasi CAN P (106.90113 -6.13310) RT 11m + Stacking 5m + pole 6m | Optimis | 2026-03-20 | Add 3 RF Add 9 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Mar | PT DENTRA MITRA ABADI | PT TRITECH CONSULT | BTR | Arah 200m 300 degree | 106.9012 | -6.1342 |  | 106.9011 | -6.13310 | MASJID AT-TAUBAH Jl Plumpang Semper samping hotel Arsisi masuk jl Koramil gang AT-TAUBAH I kp.Bendungan Melayu RT008 RW001 no 74 kelurahan Rawa Badak Selatan,kecamatan Koja Jakarta utara | Monopole 20 1Leg | Fasum |  | BTR |  |  | Trotoar(pondasi tertanam) | Tubular | Flenge Luar | 1.5 | 1.5 | 3 |  | BTR
194 | Area 2 | JUX279 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0095 | JUX279 | JLTARIBALUSEDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | Propose Drop | Need Validasi | 1/4/26: Need Validasi CAN P ( -6.168755 106.910734) RT 9M + Pad 1m + pole 15m 04/03/26 : Hard candidate 11/01/26: JR submited, menunggu arahan 4. 08/01/26 : Submit JR, menunggu arahan DMT 3. 07/01 Hunting OG (plan submit 2. Plan 12.1.2026 submit datek 1. Proses hunting, | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | DROP | PT DENTRA MITRA ABADI | PT TRITECH CONSULT | BTR | 150m arah 0 degree | 106.9106 | -6.1693 |  |  |  |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | Trotoar | Tubular | Flenge dalam | 1.5 | 1.5 | 3 | Extend 6m | BTR
141 | Area 2 | JUX318 | Jabat | In Hand | Non MKT | Non MKT |  | BTSH | 24TS09B0412 | JUX318 | MESJIDPUSKESMASSUNTERDMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | 15/1/2026 RFI Done, ATP Done Minus RFI NOTICE (need ATP) | Optimis | RFI : 22/12/2025 | 10.12 curing, waiting NOD tower (msh proses pabrikasi) info week 3 ready | W4 DESEMBER 2025 | Done RFI | PT DYEVA DIGITAL SELULAR | PT ATRYA REKAYASA | BTR |  | 106.8609 | -6.1417 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
293 | Area 2 | JUX347 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0085 | JUX347 | IMPERIALGADINGDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | Propose Drop | Rehunting | 04/03/2625/02/26: Hard sitac, Proposed extend 6m 22/02/26 : Mitra submit BA perihal penolakan warga terkait pembangunan tower telekomunikasi dan mayoritas tanah warga masih berstatus tanah negara 21/02/26 : IW OG 18/02/26 : Validasi OK Cand P (-6.15974,106.92157) 03/02/26 : Need Validasi Cand A ( -6.15974,106.92157) 22/01/26 : Submit JR 28/1/26 : Pengajuan JR 10/01/2026 : Rehunting, plan 12 Jan 2026 07/01 Proposed di area mesjid milik Pelindo sedang upayakan koordinasi pihak DKM 05/01: Plan submit CAN Q Paralel hunting cand Q Survey OG LL belum bisa ditemui terkait masa libur | Not Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT AJIAN TRI SUKSES | PT TRITECH CONSULT | BTR | BTR Arah 150m 350 degree | 106.9222 | -6.1603 |  | 106.9216 | -6.1597 |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | Streetview NA |  |  | 2 | 2 | 4 |  | BTR
447 | Area 2 | JUX356 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12Z0099 | JUX356 | PELABUHANMUARABARUDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 4. CME | Pabrikasi | 27/04/26 : Start 29/4/26 22/04/26 : Material OK, plan start 25/4/26 08/04/26 : Menunggu info pick up dari DHJ 01/04/26 : Pabrikasi done, waiting jadwal pickup dari Pabrikan(DHJ) 16/3/26: Pabrikasi OG(issue perubahan APD dari konsultan) plan finish pabrikasi 18/3/26 , start CME setelah lebaran (30/3/26) 04/03/25 : Pabrikasi 13/3/26 25/02/26: Pabrikasi Perkuatan extend 3m OG(start pabrikasi 18/02, target finish 12/03) 6. 26/01/26 : APD Approved SOLENG HQ 5. 20/01/26 : Approved APD dan BOQ 4. 19/1/26 : APD menunggu approved Soleng 3.13/01/26: waiting desain extend by konsultan 2. Plan tim konsultan survey 06.01.2026 (extend 3m) 1. Hunting, plan 30.12.2025 sounding ke kel. koja menanyakan status tanah | Optimis | 2026-01-29 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | RFI : w1 Mei 2026 RFI : 25/4/26 4/20/2026 | Mar | PT SUMBERSOLUSINDO HITECH | PT TRITECH CONSULT | Extend Pole | Extend 3m | 106.9055 | -6.1084 |  |  |  |  | Monopole 20 1Leg | Fasum |  | Extend 3m |  |  | Taman | Tubular | Flenge Luar | 1,5 | 1,5 | 3 | Extend 3m OG | Extend 3m
448 | Area 2 | JUX363 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0065 | JUX363 | GOLFISLANDMWDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | Rekom Lurah OG | 22/04/26 : Rekom lurah OG 16/04/26 : Rekom Lurah OG (high price) 08/04/26 : IW done, Rekom Lurcam OG 1/4/26: Proses negosiasi Kompensasi warga, IW done(38kk) 16/03/26 : BAN dan IW OK, realisasi pembayaran setelah hari Raya 25/02/26: IW done waiting approval BAN 7. 03/02/26 : BAN/BAK (44jt/th) OG 6. 28/1/26 : BAN/BAK (47jt/thn) OG, IW OK 5. 13/01/26: Validasi NBAE OK (Can Q: -6.12333 106.92559) Lanjut BAN/BAK 4. 05/01/2026 Need Validasi CAN Q (106.92559 --6.12333) GF 30m, CAN P gagal IW , 3. Proses BAN dan IW 2. Validasi NBAE OK : 23/12/2025 (Cand P : -6.1239,106.92524) 1. 18.12 Need Validasi CAN P ( 106.92524 -6.12390) GF 32m | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Rekom lurah : 17/4/26 Rekom : 13/4/26 | Mar | PT GEAF SOLUSIANDA PRATAMA | PT TRITECH CONSULT | BTR | 290 degree arah 130m | 106.9265 | -6.1229 |  | 106.9256 | -6.1233 | JL TUGU INDAH NO 18 KEL.SEMPER BARAT KEC.CILINCING JAKARTA UTARA | Monopole 20 1Leg |  | MP32m | BTR | 3x4 | 488888888.8889 | Taman | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | MP32m | BTR
274 | Area 2 | JUX369 | Jabat |  | Non MKT | Non MKT | 0 | BTSH | NY | JUX369 | MSJDALJIHADDMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial | Locktrial | 106.9112 | -6.1129 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
273 | Area 2 | JUX377 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0067 | JUX377 | GARDENMARBEL1DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN BAK | 22/04/26 : Wait approved BAN BAK (60jt/thn) cnd Q (sekolah JAC Primary) 16/04/26 : Mitra submit datek cand R, need validasi 08/04/26 : Re-hunting 1/4/26: Need approval BAN (60jt/thn) RT 16/03/26 : Menunggu persetujuan sewa lahan dari pihak sekolah 25/02/26 : Menunggu pimpinan pihak sekolah untuk proses BAN plan 26/02 5. 30/01/26 : Need Validasi Cand Q (-6.133299,106.9170453)NB Jovis, Validasi OK Cand Q (sekolah JAC Primary) 4. 28/1/26 : Plan JOVIS 29/1/26 3. 13/01/26: Validasi NBAE NOK (Can P) rehunting 2. 05/01/2026 : Need Validasi CAN P ( 106.91488 -6.13324) GF 32m 1. 22.12 Need Validasi CAN P ( 106.91488 -6.13324) GF 32m | Optimis | 2026-03-20 | Add 3 RF Add 3 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | Datek : 16/4/26 Datek : 11/4/2026 | Apr | PT GEAF SOLUSIANDA PRATAMA | PT TRITECH CONSULT | BTR | 200m arah 270 degree | 106.9166 | -6.1335 |  | 106.917 | -6.1333 | Jl. Pegangsaan Dua Jl. Logistik No.21 5, RT.5/RW.4, Tugu Sel., Kec. Koja, Jkt Utara, Daerah Khusus Ibukota Jakarta 14260South Tugu, Koja, North Jakarta City, Jakarta | Monopole 20 1Leg |  | RT 30m +pole 3/6m | BTR |  | 666666666.6667 | Trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | RT 30m + pole 3/6 m | BTR
305 | Area 2 | JUX401 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0034 | JUX401 | KALIBARUTIMUR5DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK | 1/4/26: IW OG sisa 5 dari 30KK, submit BAN 2/4/26 04/03/26: BAN/BAK menunggu penawaran LL, IW OG 5. 26/02/26 : Validasi Cand Q OK 4. 19/02/26 : Need Validasi Cand Q (-6.09824,106.93409) monopole 30m jarak ke nom 154 m 3. Progress IW, BAN, BAK & collect dokumen sitac 2. 13/01/26: Validasi NBAE OK (Can A : -6.09959 106.93463) Lanjut BAN/BAK 1. 26.12 Need Validasi CAN A (106.93463 -6.09959) GF 30m | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT DENTRA MITRA ABADI | PT TRITECH CONSULT | BTR | 200m arah 330 degree | 106.9345 | -6.0995 |  | 106.9346 | -6.0996 | Alamat : Jl.Kalibaru Timur 6C no 25 RT 013/013, kelurahan Kalibaru,kecamatan Cilincing, Jakarta utara | Monopole 20 1Leg | Fasum |  | BTR |  |  | dalam lahan berpagar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 |  | BTR
321 | Area 2 | JUX402 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0031 | JUX402 | WARAKASGANG3DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | Validasi OG | 22/04/26 : Need validasi cand R (penawaran LL 60jt/thn) 16/04/26 : Need Validasi Cand R ( 08/04/26 : Pihak DKM tetap ingin di menara mesjid (tinggi menara masjid 19 m) 1/4/26: Waiting Approval BAN can Q(40jt/th) , IW done 16/3/26: Waiting Approval BAN can Q(40jt/th) , IW done 10/03/26 : Plan extend di site eksisting terkendala kejelasan pewaris LL(sudah meninggal), BTR terkendala persetujuan ketinggian 25/02/26: Proses BAN/BAK dengan pihak DKM Can Q 7. 30/01/26 : Validasi ok Cand Q 6. 26/01/26 : Need Validasi Cand Q, Izin warga Clear , BAN/BAK 40jt/thn 5. 19/1/26 : Need validation cand Q (106.88244 06.12453),Menara mesjid 19m cand P fail 4. 13/01/26: Validasi NBAE OK (Can P) lanjut BAN/BAK 3.31.12.2026 Need Validasi CAN P (106.88096 -6.12466) GF 32m 2. Paralel hunting cand. P 1. 23.12 : Rehunting karena site eksisting ada issue warga, plan submit datek 30.12.2025 | Optimis | 2026-01-29 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT SUMBERSOLUSINDO HITECH | PT TRITECH CONSULT | Extend Pole | Locktrial, coba diextend | 106.8817 | -6.1247 |  | 106.8824 | -6.1245 | jl warakas V Gang I no.127 rt 08 rw 03 kel warakas kec tanjung priok jakarta utara | Monopole 20 1Leg | Fasum |  | Extend 6m | 3x3 |  | Trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Extend 6m | Extend 6m
324 | Area 2 | JUX407 | Jabat | In Hand | Non MKT | Non MKT | 0 | BTSH | 23TS07B0091 | JUX407 | JLKAKAPPENJARINGANDMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 17/11/2023 |  | RFI | Done RFI | PT SINERGI REKTA DENTA | Waspang | BTR |  | 106.805 | -6.1041 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
320 | Area 2 | JUX417 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0072 | JUX417 | AKSESMARUNDADMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 3. RFC | APD OG | 29/04/26 : SKOM Done. LL meminta DP sebelum start CME, langsir material tower dan material alam, permintaan supply material dari RW 27/04 26 : SKOM 29/4/26 22/04/26 : Skom 25/4/59 20/04/26 : Mitra submit APD 16/04/26 : APD OG 15/04/26 : APD OG 12/04/26 : Submit TSSR 08/04/26 : Proses Rekom Lurcam, target 10/4/26 01/04/26 : Waiting approval BAN(30jt), proses nego kompensasi warga 16/03/26 : BAN dan IW OK, realisasi pembayaran setelah hari Raya 25/02/26: IW Done , waiting approval BAN 16/02/26 : Tsel Approved ketinggian tower 25m 28/1/26 : BAN/BAK (30jt/thn) OG, IW OK jika ketinggian tower di 25m 20/01/26 : issue ketinggian tower yang diizinkan hanya 25m (32m diprotes warga) 13/01/26: Validasi NBAE OK (Can P: -6.11692 106.93578) lanjut BAN/BAK 05/01/26 : Need Validasi CAN P ( 106.93578 -6.11692) GF 32m 22.12 Need Validasi CAN P ( 106.93578 -6.11692) GF 32m | Optimis | 2026-03-20 | Add 3 RF Add 5 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) | RFI : 15 Mei 2026 Lurcam : 10/4/28 | Mar | PT GEAF SOLUSIANDA PRATAMA | PT TRITECH CONSULT | BTR | BTR Arah 75 quadran 4 | 106.935 | -6.1175 |  | 106.9358 | -6.1169 | Jl peralihan kp sungai begog RT.008.RW.003 Kel semper timur, kec Celincing, jakrta utara | Monopole 20 1Leg |  | MP25m | BTR | 4x3 |  | Trotoar | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | MP 25 | BTR
326 | Area 2 | JUX419 | Jabat | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0123 | JUX419 | KOMPSWASEMBADABARATDMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | Propose Drop | Justifikasi Report | 04/03/26 : Hard candidate 25/02/26: Hardsitac , extend 6m tidak memungkinkan site dibawah jalur SUTET PLN 9. 09/02/26 : Mitra Submit JR 8. 30/1/26 : Need Validasi Cand Q ( -6.12617,106.89006) nb Jovis, Validasi OK Cand Q 7. 28/1/26 : Plan JOVIS 29/1/26 6. 11/01/26: Proposed extend lahan eskisting LL ok issue obstacle SUTET PLN 5. 09/01/2026 : Validasi NOK, proposed Rehunting 4. 05/01/2026 : Need Validasi CAN P (106.89181 -6.12605) GF 25m 3. Plan meeting DKM 31.12.2025 2. Plan meeting dgn DKM 29.12.2025 1. 26/12 : Plan candidat Mesjid (menunggu approval DKM) | Not Optimis | 2026-03-20 | Add 3 RF Add 8 RRU Final Sow Rescope: 1. (B2R to (MCP, Mini Macro, macro) |  | Apr | PT AJIAN TRI SUKSES | PT TRITECH CONSULT | BTR | 35' 200m | 106.8903 | -6.1271 |  | 106.8901 | -6.12617 |  | Monopole 20 1Leg | Fasum |  | BTR |  |  | dalam lahan berpagar ada jalur Sutet baru | Tubular | Flenge Luar | 1.5 | 1.5 | 3 | Lanjut BTR arah utara | BTR
375 | Area 2 | KRW172 | Eastern Jabodetabek |  | Non MKT | Non MKT |  | BTSH | NY | KRW172 | PERMANENTCMBTMITRAKARAWANGDMT | Plan ≤ 2025 | BTS HOTEL |  | 4. CME | Pabrikasi | Upgrade perangkat (As it is)-> Proses Izin Pihak KIM, Pabrikasi Platform & Belting OG | Optimis | Drop | No site List |  |  | NY | NY | Lock Trial |  | 107.3104 | -6.3819 |  |  |  |  | Monopole 20 1Leg |  |  | Contine with Macro | [9 empty] | Upgrade perangkat (As it is)-> Proses Izin Pihak KIM, Pabrikasi Platform & Belting OG
630 | Area 2 | KRW185 | Eastern Jabodetabek | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS01B0001 | KRW185 | KIS4DMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 2. SITAC | PKS | 22/04/26 : Proses PKS DMT ke KIS, pengajuan ijin untuk soil test 08/04/26 : Menunggu email BAK dan PKS dari DMT ke KIS 01/04/26 : Reminder KIS 2/4/26 mengenai penawaran harga dari DMT, koordinasi antar KIS dan Perhutani mengenai batas lahan 30/03/26 : Menunggu jawaban dari KIS 16/03/26 : Menunggu surat DMT ke KIS4DMT, soiltest NY 08/03/26 : Candidate Done, Pihak KIS akan memfollowup perijinan ke sepadan yaitu perhutani dan warga bila draft PKS diterima oleh KIS 25/02/26 : Validasi OK, menunggu respon kawasan di tikor yg baru 09/02/26 : Rehunting Candidate masih menunggu mapping lokasi dari KIS Mapping perubahan KRW185 KISBTSH, plann mapping tgl 29 Jan 2026 12/01/26 : Submit TSSR dan BA survey Need JOVIS (potensi batas perhutani) 30/12/24 : Submit resume hasil jovis 24/12/25 Pengecekan lokasi actual untuk lokasi yg sudah di setujui sesuai map | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: BTR to Macro |  | Mar | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | BTR |  | 107.3328 | -6.4067 |  |  |  |  | Monopole 20 1Leg | KIS | SST 42 | BTR | [9 empty] | BTR
362 | Area 2 | KRW807 | Eastern Jabodetabek | In Hand | Non MKT | Non MKT |  | BTSH | 25TS01B0002 | KRW807 | KIIC1DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 09/12/2025 | 0 | RFI | Done RFI | PT AGUNGMAS PRIMA SEMPURNA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 107.2727 | -6.3653 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
363 | Area 2 | KRW809 | Eastern Jabodetabek | In Hand | Non MKT | Non MKT |  | BTSH | 25TS01B0003 | KRW809 | KIIC3DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | 21.01 Soft RFI (minus Pagar) BORE PILE 16 TITIK (SST 42 METER) | Optimis | 2026-02-14 | 12.12 masih menunggu surat ijin dari pihak kawasan 10.12 Excation OG, geser 150m, Waiting Surat Kerja Pihak Kawasan | W3 2026 | Done RFI | PT AGUNGMAS PRIMA SEMPURNA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 107.2954 | -6.359 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
361 | Area 2 | KRW811 | Eastern Jabodetabek | In Hand | Non MKT | Non MKT |  | BTSH | 25TS01B0004 | KRW811 | KIIC5DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 23/09/2025 | 0 | RFI | Done RFI | PT AGUNGMAS PRIMA SEMPURNA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 107.2945 | -6.3721 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
377 | Area 2 | KRW813 | Eastern Jabodetabek |  | Non MKT | Non MKT |  | BTSH | NY | KRW813 | KIIC7DMT | Plan ≤ 2025 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop | Lock Trial |  |  | NY | NY | Lock Trial |  | 107.2743 | -6.3603 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
373 | Area 2 | KRW814 | Eastern Jabodetabek |  | Non MKT | Non MKT |  | BTSH | NY | KRW814 | KIIC8DMT | Plan ≤ 2025 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop | Lock Trial |  |  | NY | NY | Lock Trial |  | 107.2777 | -6.356 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
382 | Area 2 | KRW817 | Eastern Jabodetabek | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS01B0005 | KRW817 | KIIC13DMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI | RFI | Optimis | RFI : 23/09/2025 | Add 3 RF Add 6 RRU Final Sow Rescope: BTR to Macro | RFI | Done RFI | PT AGUNGMAS PRIMA SEMPURNA | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 107.2647 | -6.3764 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
606 | Area 2 | KRW819 | Eastern Jabodetabek |  | Non MKT | Non MKT |  | BTSH | NY | KRW819 | KIIC15DMT | Plan ≤ 2025 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop | Lock Trial |  |  | NY | NY | Lock Trial |  | 107.2942 | -6.3794 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
385 | Area 2 | KRW828 | Eastern Jabodetabek | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS01B0006 | KRW828 | KIM6DMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 1. SIS/SES | Rehunting | 21.01 : BI tidak approve need jovis Lahan Peruri | Optimis | 2026-03-20 | 4.12. plan macronisasi di site existing, upgrade perangkat (swap) type 1, Add 3 RF Add 8 RRU Final Sow Rescope: BTR to Macro |  | Apr | PT SAMANTA FIBRA ABADI | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 107.3085 | -6.3765 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
359 | Area 2 | KRW829 | Eastern Jabodetabek | In Hand | Non MKT | Non MKT |  | BTSH | 25TS01B0007 | KRW829 | KIM7DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 4. CME | Pabrikasi | Upgrade perangkat (As it is)-> Proses Izin Pihak KIM, Pabrikasi Platform & Belting OG | Optimis | 2026-03-20 | 12.12 Hunting kandidat arahan Tsel 4.12. plan macronisasi di site existing, upgrade perangkat (swap) type 1, per tahun per pole 300 Juta, need special price, geser hunting ke Peruri | SETTING TARGET AFTER JOVIS | Apr | PT SAMANTA FIBRA ABADI | KOPERASI JASA DAYAMITRA TELEKOMUNIKASI | BTR |  | 107.3153 | -6.3724 |  |  |  |  | Monopole 20 1Leg |  |  | Contine with Macro | [9 empty] | Upgrade perangkat (As it is)-> Proses Izin Pihak KIM, Pabrikasi Platform & Belting OG
629 | Area 2 | KRW831 | Eastern Jabodetabek | In Hand | Non MKT | Non MKT |  | BTSH | 25TS01B0008 | KRW831 | KIM9DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 8. Lock Trial | Pabrikasi | 16/03/26 : Perubahan SOW, mitra submit APD ke MK utk di review Upgrade perangkat (As it is)-> Proses Izin Pihak KIM, Pabrikasi Platform & Belting OG (Lock TRIAL) | Optimis | 2026-03-20 | 12.12 Hunting kandidat arahan Tsel 4.12. plan macronisasi di site existing, upgrade perangkat (swap) type 1, per tahun per pole 300 Juta, need special price | SETTING TARGET AFTER JOVIS | Apr | PT SAMANTA FIBRA ABADI | PT TRITECH CONSULT | BTR |  | 107.3083 | -6.3859 |  |  |  |  | Monopole 20 1Leg |  |  | Contine with Macro | [9 empty] | Upgrade perangkat (As it is)-> Proses Izin Pihak KIM, Pabrikasi Platform & Belting OG (LOCK TRIAL)
365 | Area 2 | KRW833 | Eastern Jabodetabek | In Hand | Non MKT | Non MKT |  | BTSH | 25TS01B0009 | KRW833 | KIM11DMT | Plan ≤ 2025 | RESCOPING | Tracker Project DMT_TSEL | 2. SITAC | Rehunting | 16/03/26 : Perubahan SOW, mitra submit APD ke MK utk di review 21.01 : BI tidak approve need jovis Lahan Peruri | Optimis | 2026-03-20 | 12.12 Hunting kandidat arahan Tsel 4.12. plan macronisasi di site existing, upgrade perangkat (swap) type 1, per tahun per pole 300 Juta, need special price, geser hunting ke Lahan BI | SETTING TARGET AFTER JOVIS | Apr | PT SAMANTA FIBRA ABADI | PT TRITECH CONSULT | BTR |  | 107.3031 | -6.3829 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | BTR
374 | Area 2 | KRW836 | Eastern Jabodetabek |  | Non MKT | Non MKT |  | BTSH | NY | KRW836 | KIS1DMT | Plan ≤ 2025 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop | Lock Trial |  |  | NY | NY | Lock Trial |  | 107.3367 | -6.3939 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
381 | Area 2 | KRW838 | Eastern Jabodetabek | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS12B0011 | KRW838 | KIS3DMT | Plan ≥ 2026 | RESCOPING MKT NEW | Tracker Project DMT_TSEL | 2. SITAC | PKS, APD OK | 22/04/26 : Review PKS by KIS 08/04/26 : Menunggu email BAK dan PKS dari DMT ke KIS 01/04/26 : Reminder KIS 2/4/26 mengenai penawaran harga dari DMT, submit timeplan pelaksanaan CME ke Daihatsu 6/4/26, APD OK 30/03/26 : Menunggu jawaban dari KIS 16/03/26 : Menunggu surat DMT ke KIS3DMT 08/03/26 : Soiltest dan APD Done, Pihak KIS menunggu Draft PKS dan ke KIS, Jalan akses ekstrim(rawa), prentasi ke daihatsu, persetujuan DMT bila akses tidak dibangun, Submited BoQ CME 18 Mar 2026 25/2/26 : Soil test OK, APD OG, BAN BAK OG (menunggu negosiasi harga DMT dan pihak kawasan) Lokasi Ok waiting Mapping perubahan KRW185 KISBTSH 12/01/26 : Submit TSSR dan BA survey JOVIS plan konfirmasi dengan Pihak KIS 05/01/2026 30/12/24 : Submit resume hasil jovis 24/12/25 Pengecekan lokasi actual untuk lokasi yg sudah di setujui sesuai map | Optimis | 2026-03-20 | Add 3 RF Add 7 RRU Final Sow Rescope: BTR to Macro |  | Mar | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | BTR |  | 107.3403 | -6.4116 |  |  |  |  | Monopole 20 1Leg | Fasum | SST 42 | BTR | [9 empty] | BTR
95 | Area 2 | KRW841 | Eastern Jabodetabek | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS01B0010 | KRW841 | KIS6DMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 2. SITAC | PKS, APD OK | 22/04/26 : Review PKS by KIS 08/04/26 : Menunggu email BAK dan PKS dari DMT ke KIS 01/04/26 : 01/04/26 : Reminder KIS 2/4/26 mengenai penawaran harga dari DMT, APD OK 30/03/26 : Menunggu jawaban dari KIS 16/03/26 : Menunggu surat DMT ke KIS6DMT 08/03/26 : Soiltest dan APD Done, Pihak KIS menunggu Draft PKS dan ke KIS, Jalan akses ekstrim(rawa) 25/02/26 : Validasi baru OK, Soil test OK, APD OG, BAN BAK OG (menunggu negosiasi harga DMT dan pihak kawasan) 09/02/26 : Lokasi ada pergeseran dari Candidate awal, waiting approval candidate Lokasi Ok waiting Mapping perubahan KRW185 KISBTSH 12/01/26 : Submit TSSR dan BA survey JOVIS plan konfirmasi dengan Pihak KIS 05/01/2026 30/12/24 : Submit resume hasil jovis 24/12/25 Pengecekan lokasi actual untuk lokasi yg sudah di setujui sesuai map | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: BTR to Macro |  | Mar | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | BTR |  | 107.3232 | -6.3873 |  |  |  |  | Monopole 20 1Leg | KIS | SST 42 | BTR | [9 empty] | BTR
383 | Area 2 | KRW842 | Eastern Jabodetabek |  | Non MKT | Non MKT | 0 | BTSH | NY | KRW842 | KIS7DMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial |  | 107.3349 | -6.3861 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
372 | Area 2 | KRW843 | Eastern Jabodetabek |  | Non MKT | Non MKT |  | BTSH | NY | KRW843 | KIS8DMT | Plan ≤ 2025 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop | Lock Trial |  |  | NY | NY | Lock Trial |  | 107.3332 | -6.4015 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
370 | Area 2 | KRW844 | Eastern Jabodetabek |  | Non MKT | Non MKT |  | BTSH | NY | KRW844 | KIS9DMT | Plan ≤ 2025 | BTS HOTEL |  | 2. SITAC | IW | Lock Trial | Not Optimis | Drop | Lock Trial |  |  | NY | PT TRITECH CONSULT | Lock Trial |  | 107.3274 | -6.3734 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
532 | Area 2 | KRW846 | Eastern Jabodetabek | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS01B0011 | KRW846 | KIS11DMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 2. SITAC | PKS, APD OK | 22/04/26 : Review PKS by KIS 08/04/26 : Menunggu email BAK dan PKS dari DMT ke KIS 01/04/26 : Reminder KIS 2/4/26 mengenai penawaran harga dari DMT, APD done 30/03/26 : Menunggu jawaban dari KIS 16/03/26 : Menunggu surat DMT ke KIS1DMT 08/03/26 : Soiltest dan APD Done, Pihak KIS menunggu Draft PKS dan ke KIS, Jalan akses ekstrim(rawa), prentasi ke daihatsu, persetujuan DMT bila akses tidak dibangun, Submited BoQ CME 18 Mar 2026 25/02/26 : Soil test OK, APD OG, BAN BAK OG (menunggu negosiasi harga DMT dan pihak kawasan) 09/02/26 : Lokasi Ok waiting PKS antara KIS dan DMT untuk start CME Lokasi Ok waiting Mapping perubahan KRW185 KISBTSH 12/01/26 : Submit TSSR dan BA survey JOVIS plan konfirmasi dengan Pihak KIS 05/01/2026 30/12/24 : Submit resume hasil jovis 24/12/25 Pengecekan lokasi actual untuk lokasi yg sudah di setujui sesuai map | Optimis | 2026-03-20 | Add 3 RF Add 6 RRU Final Sow Rescope: BTR to Macro |  | Mar | PT AGUNGMAS PRIMA SEMPURNA | PT TRITECH CONSULT | BTR |  | 107.3325 | -6.3907 |  |  |  |  | Monopole 20 1Leg | KIS | SST 42 | BTR | [9 empty] | BTR
387 | Area 2 | KRW953 | Eastern Jabodetabek | In Hand | MKT | 0004/MKT/DMT/XI/2025 | 2025-11-18 | BTSH | 25TS01B0012 | KRW953 | KIM10DMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 4. CME | Pabrikasi | 16/03/26 : Perubahan SOW, mitra submit APD ke MK utk di review Upgrade perangkat (As it is)-> Proses Izin Pihak KIM, Pabrikasi Platform & Belting OG (Lock TRIAL) | Optimis | 2026-03-20 | 4.12. plan macronisasi di site existing, upgrade perangkat (swap) type 1, Add 3 RF Add 9 RRU Final Sow Rescope: BTR to Macro |  | Apr | PT SAMANTA FIBRA ABADI | PT TRITECH CONSULT | BTR |  | 107.3136 | -6.3761 |  |  |  |  | Monopole 20 1Leg |  |  | Contine with Macro | [9 empty] | Upgrade perangkat (As it is)-> Proses Izin Pihak KIM, Pabrikasi Platform & Belting OG
401 | Area 2 | KRW954 | Eastern Jabodetabek |  | Non MKT | Non MKT | 0 | BTSH | NY | KRW954 | KIIC14DMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial |  | 107.2951 | -6.3656 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
400 | Area 2 | KRW955 | Eastern Jabodetabek |  | Non MKT | Non MKT | 0 | BTSH | NY | KRW955 | KIIC10DMT | Plan ≥ 2026 | BTS HOTEL |  | 8. Lock Trial | LOCK TRIAL | Lock Trial | Not Optimis | Drop |  |  |  | NY | NY | Lock Trial |  | 107.2886 | -6.3594 |  |  |  |  | Monopole 20 1Leg |  |  | BTR | [9 empty] | Lock Trial
[8 empty] | BTSH | 26TS02B0192 | JPX158 | CEMPAKAPUTIHBRT2EDMT | Plan ≥ 2026 | RESCOPING | Tracker Project DMT_TSEL | 1. SIS/SES | Hunting | 08.04 : Mencoba Pendekatan Untuk Mencari Kandidat (Plan Submit Cand 15/04) | Optimis |  |  | 2026-06-05 | Mei | PT SUMBERSOLUSINDO HITECH | PT MULTI BMITRA SEJAHTERA | BTR
01/04/26 : Re-negosiasi 4/4/26 (50jt/thn) 30/03/26 : Wait approved BAN 50jt/thn, IW 15 kk NY, submit BAN 18/03/26 16/03/26 : Info 16/03/26 (BAN 50jt/thn, IW 15 kk NY), submit BAN 18/03/26 08/03/26 : BAN OG pararel IW 09 Mar 2026 07/03/26 : Validasi OK Cand R (Rooftop 12m + Pole 20m) 27/2/26: Need Validasi CAN R(106.84199 -6.29108) RT 12m + Pole 20m, CAN Q cancel by LL 25/2/26 : Hold, LL Ada masalah internal keluarga, option hunting new candidate atau extend 6m 22/01/26 : IW Done 13/01/26 : Validasi cand Q OK, lanjut BAN/BAK 29/12/25 : Need Validasi CAN Q (106.84198 -6.29121) RT 12m + Pole 15m 29/12 Cand P gagal issue warga 18/12/25 : Validasi NBAE OK : 18/12/2025 (Cand P : -6.29221,106.84241)

## 17 Site Exclude BTSH DMT
PID | SITE ID BARU | Name Site | EOC | SOW TENANT | Remarks | MILESTONE | General Status | Detail Progress | Not Optimis/ Optimis | Target | General Status | Week Target Tsel | Mitra Pleno MKT | Mitra Pleno MK | UPDATE DRM BTSH (CRM) | Arahan NBAE | Long | Lat | Tower Eksisting | Lahan Eksisting | Program | Data Tim SITAC | NO HP | xcek MDC
24TS09B0401 | DPK398 | PERUMGRANDMATOADMT | Refinement 2024 | NON RESCOPING | Tracker Project DMT_TSEL | 2. SITAC | SOIL TEST |  | Optimis |  |  |  | PT SUMBERSOLUSINDO HITECH
24TS09B0457 | JBX068 | TAMANAPELUTARADMT | Refinement 2025 | NON RESCOPING | Tracker Project DMT_TSEL | 6. PROPOSE DROP | Propose Drop | [5 empty] | PT JAGANATA SAKTI UNGGUL
24TS09B0456 | JBX083 | KOTABAMBUUTARADMT | Refinement 2025 | NON RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI |  | Optimis |  |  |  | PT JAGANATA SAKTI UNGGUL
24TS09B0402 | JKB284 | INSPEKSITANGGULBARATDMT | Refinement 2024 | NON RESCOPING | Tracker Project DMT_TSEL | 6. PROPOSE DROP | Propose Drop | [5 empty] | PT JAGANATA SAKTI UNGGUL
24TS09B0403 | JKB326 | PALMADMT | Refinement 2024 | NON RESCOPING | Tracker Project DMT_TSEL | 6. PROPOSE DROP | Propose Drop | [5 empty] | PT JAGANATA SAKTI UNGGUL
24TS09B0405 | JKT118 | Kemerdekaan | Refinement 2024 | NON RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI |  | Optimis |  |  |  | PT DYEVA DIGITAL SELULAR | PT.ATRYA REKAYASA
24TS09B0406 | JKT641 | JNCPASARREBO | Refinement 2024 | NON RESCOPING | Tracker Project DMT_TSEL | 6. PROPOSE DROP | DROP | [5 empty] | PT SINERGI REKTA DENTA
24TS09B0459 | JSX311 | PINANGPDLABUDMT | Refinement 2025 | NON RESCOPING | Tracker Project DMT_TSEL | 2. SITAC | Proses Design dan Perijinan Pole Extend | [5 empty] | PT MITRA SARANA KARYA BANGSA
24TS09B0404 | JSX695 | KOMPLEKSEKNEGLAMADMT | Refinement 2024 | NON RESCOPING | Tracker Project DMT_TSEL | 6. PROPOSE DROP | Propose Drop | [5 empty] | PT SUMBERSOLUSINDO HITECH
24TS09B0458 | JTX054 | KRAMATTIMURDMT | Refinement 2025 | NON RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI |  | Optimis |  |  |  | PT CIPTA KARSA ANUGERAH SEMESTA
23TS07B0090 | JUX367 | RUSUNAWAWADUKPLUIT | Refinement 2024 | NON RESCOPING | Tracker Project DMT_TSEL | 5. RFI | RFI |  | Optimis |  |  |  | PT Naer Tunas Indonesia
25TS10B0020 | JSX288 | Lingkarluarjtpadang | Renewal 2025 | Rescoping TP Lain | Tracker Project DMT_TSEL | Proposed DROP | Proposed DROP | 22/04/26 : Mitra submit evidence high capex 08/04/26 : Pengajuan BOQ 10/4/26, High capex 01/04/26 : Proses JR 16/03/26 : Submit JR 10/03/26 : Prepare submit JR, hard candidate 04/03/26 : hard candidate, re-hunting 19/01/26 : Penolakan warga 05/01/26 : Soswar done 3 Januari 2026 24/12 : Sosialisasi warga 11/12 : menunggu approval BAN/BAK (50jt.tahun) IW on Going 04/12 : Validasi OK 28/11 : Menunggu Validasi cand A dan B 26/11 : Menunggu Validasi Cand A dan B 17/11 : Menunggu validasi 14/11 : Menunggu validasi 11/11 : Menunggu validasi cand 2 05/11 : Submit datek cand 2, need validation 04/11 : Submit datek cand 1, need validation 22/10 : KOM B2S | Optimis | Submit : 27/4/26 |  |  | PT INFRAKO | PT. Tritech Consult
25TS10B0018 | JKU984 | Gadingkirana | Renewal 2025 | Rescoping TP Lain | Tracker Project DMT_TSEL | 4. CME | BAN BAK | 22/04/26 : Mitra submit BOQ high capex 08/04/26 : Menunggu approval BA high CAPEX 1/4/26: DP menunggu approval BA highcapex 16/3/26: Implementasi menunggu DP, para 10/03/26 : Menunggu DP 25/02/26 : Waiting NOD & DP sewa lahan 28/01/26 : LL meminta DP sebelum CME di lokasi 23/02/26 : Menunggu rekom lurcam, pararel proses APD 05/01/26 : Menunggu Approval eskalasi SITAC (addcost IW) dari Procurement, submit DMT 2/01/26 03/12 : Menunggu validasi 29/11 : Need validation, mitra submit candidat A (GF) 06/11 : Hunting Candidat radius 150m dari NOM 19/11 : Re-hunting radius 150m dari NOM 17/11 : Hunting kandidat 12/11 : Hunting Candidate 04/11 : Hunting candidate 30/10 : Hunting candidate 27/10 : Submit Datek Cand 1, di arahkan mencari lokasi lain krn lahan SPBU 22/10 : KOM B2S | Optimis |  |  |  | PT Naer Tunas Indonesia | PT. Tritech Consult
25TS10B0015 | JBX061 | Pepayacengkarengbarat | Renewal 2025 | Rescoping TP Lain | Tracker Project DMT_TSEL | 1. SIS/SES | Validasi OG | 22/04/26 : Need validasi cand R 16/04/26 : Need validasi cand R 08/04/26 : Menunggu Validasi 1/4/26: need validasi Cand R 16/03/26 : Need validasi cand R 10/03/26 : Menunggu arahan DMT utk new kandidat 25/02/26 : Need Validasi CAN R 28/1/26 : Jovis done 21/1/26, menunggu info dari Tsel 07/01/2026 : Validasi NOK, Rehunting CAND R 06/01/2026 : Need Validation 22/12/2025 : Need validation, Mitra submit datek 08/12/2025 : Re-hunting sesuai arahan Mitratel (pak Ihsan) 30/11/2025 : Cand C, LL tidak bersedia lahannya di sewa, re-hunting, hard candidate (daerah padat penduduk) 26/11/2025 : Cand B cancel, lokasi tidak masuk spesifikasi, new cand C (LL sama) 24/11/2025 : New cand B, sedang diskusi keluarga LL 19/11/2025 : Need koordinat arahan yg baru 17/11/2025 : Re-hunting 14/11/2025 : Re-hunting 12/11/2025 : Proses rehunting 04/11/2025 : Proses re-hunting 27/10/2025 : Proses re-hunting new cand 24/10/2025 : Validasi NOK, re-hunting new cand 23/10/2025 : Submit cand A, need validation 21/10/2025 : KOM B2S | Optimis |  |  |  | PT GEAF SOLUSIANDA PRATAMA | PT. Tritech Consult
25TS10B0019 | JSX273 | Kemangselatan12 | Renewal 2025 | Rescoping TP Lain | Tracker Project DMT_TSEL | 2. SITAC | BAN/BAK OG | 22/04/26 : Mitra submit evidence high capex 08/04/26 : LL minta 50jt/tahun, menunggu BAN BAK 01/06/26 : Need Approved BAN BAK (275jt/11 th) 16/03/26 : BAN BAK OG, paralel soft copy submit ke pak Ihsan 10/03/26 : BAN sudah di submit ke DMT (pak Riza), menunggu hasil survey konsultan 04/03/26 : IW done 20/2/26 : Submit BAN 09/01/26 : Mitra submit BAN/BAK, menunggu approval (275jt/11thn) 28/12/26 : Menunggu approval BAN/BAK (50jt/tahun) 28/11 : Menunggu approval BAN (50jt/tahun) 26/11 : Menunggu approval BAN (50jt/th) 17/11 : Menunggu approval BAN 14/11 : Menunggu approval BAN 12/11 : Submit BAN/BAK, proses nego 05/11 : Proses BAN/BAK 30/10 : Kandidat 2 Validasi OK 29/10 : Submit datek kandidat2, kandidat 1 cancel by LL 28/10 : Validasi OK 24/10 : Submit datek kandidat 1, need validation 22/10 : KOM B2S | Optimis | Submit : 27/4/26 |  |  | PT INFRAKO | PT. Tritech Consult
25TS10B0016 | JKB537 | Tanahsereal2 | Renewal 2025 | Rescoping TP Lain | Tracker Project DMT_TSEL | 1. SIS/SES | re-Hunting | 22/04/26 : Proposed submit JR 08/04/26 : Hunting OG 1/4/26: Rehunting plan submit candidat 7/4/26 16/03/26 : re-Hunting 04/03/26 : Hunting new cand 25/02/26: Rehunting Hard candidat, plan proposed extend 6m 29/12 : Validasi OK 30/11 :menunggu validasi 26/11 : Need validasi, submit datek cand baru | Not Optimis |  |  |  | PT SINERGI REKTA DENTA | PT. Tritech Consult
25TS10B0017 | JKU976 | Gayamotorsunter | Renewal 2025 | Rescoping TP Lain | Tracker Project DMT_TSEL | 2. SITAC | Rekom Lurcam, IW OG | 25/02/26: Soiltest terkendala jalur utilitas eksisting, 28/1/26 : Mitra akan menggali di sekitar lokasi untuk mengetahui utilitas eksisting 20/01/2026 : Terdapat jalur FO dan PDAM pada lahan Gayamotorsunter 05/01: Proses Rekom Lurah Camat plan 07/01/26 03/12 : IW done 26/11 : IW done, rekom lurcam plan 28/11 19/11 : Pengurusan perijinan PEMDA 17/11 : Menunggu info PKS eksisting dari DMT 14/11 : Menunggu desain APD spesial 12/11 : Menunggu desain APD 06/11 : Validasi OK 04/11 : Waiting validatio 31/10 : Submit datek, need validation 29/10 : Submit TSSR 22/10 : KOM B2S |  |  |  |  | PT AJIAN TRI SUKSES | PT. Tritech Consult

## PIVOT
| Column Labels |  |  | Row Labels | Count of SITE ID BARU | Row Labels | Count of SITE ID BARU |  | Count of SITE ID BARU | Column Labels | [5 empty] | Not Optimis/ Optimis | Optimis | EOC | Plan ≤ 2025 | Row Labels | Count of SITE ID BARU
| Eastern Jabodetabek | Jabat | Grand Total | Plan ≤ 2025 | 95 | 5. RFI | 23 |  | Row Labels | Optimis | NY DRM | Not Optimis | Terminate | Lock Trial | Grand Total |  |  | Not Optimis/ Optimis | Optimis | Plan ≤ 2025 | 95
Count of SITE ID BARU | 38 | 271 | 309 | Plan ≥ 2026 | 214 | 4. CME | 4 |  | 5. RFI | 23 |  |  |  |  | 23 | Row Labels | Count of SITE ID BARU |  |  | Optimis | 38
|  |  |  | Grand Total | 309 | 3. RFC | 1 |  | 4. CME | 4 |  |  |  |  | 4 | RFI | 21 | Count of SITE ID BARU |  | Lock Trial | 7
[6 empty] | 2. SITAC | 31 |  | 3. RFC | 1 |  |  |  |  | 1 | 2025-12-28 | 5 | MILESTONE | Total | Not Optimis | 37
[6 empty] | 1. SIS/SES | 143 |  | 2. SITAC | 30 |  | 1 |  |  | 31 | 2025-12-29 | 2 | RFI | 18 | Terminate | 13
[6 empty] | 6. PROPOSE DROP | 32 |  | 1. SIS/SES | 143 |  |  |  |  | 143 | 2026-01-29 | 37 | CME | 3 | Plan ≥ 2026 | 214
[6 empty] | 7. DROP | 24 |  | NY DRM |  | 5 |  |  |  | 5 | 2026-02-14 | 7 | RFC | 1 | Optimis | 164
[6 empty] | Lock Trial | 39 |  | 6. PROPOSE DROP |  |  | 32 |  |  | 32 | 2026-02-22 | 1 | SITAC | 14 | Lock Trial | 38
[6 empty] | NY DRM | 5 |  | 7. DROP |  |  | 8 | 16 |  | 24 | 2026-03-20 | 123 | SURVEY | 1 | Not Optimis | 4
[6 empty] | 8. Lock Trial | 7 |  | Lock Trial | 1 |  |  |  | 38 | 39 | 2026-01-07 | 1 | Lock Trial | 1 | NY DRM | 5
[6 empty] | Grand Total | 309 |  | 8. Lock Trial |  |  |  |  | 7 | 7 | 2026-02-28 | 5 | Grand Total | 38 | Terminate | 3
[9 empty] | Grand Total | 202 | 5 | 41 | 16 | 45 | 309 | Grand Total | 202 |  |  | Grand Total | 309
[18 empty] | EOC | Plan ≥ 2026
[18 empty] | Not Optimis/ Optimis | Optimis
[16 empty] | Traget | PID
[16 empty] | W4 Dec | 11 | Count of SITE ID BARU
[16 empty] | W2 Jan | 2 | MILESTONE | Total
[16 empty] | W4 Jan | 40 | RFI | 5
[16 empty] | W2 Feb | 1 | CME | 1
[16 empty] | W4 Feb | 1 | SITAC | 16
[16 empty] | W2 Mar | 37 | SURVEY | 142
[16 empty] | W3 Mar | 65 | Grand Total | 164
[16 empty] | W4 Mar | 35
[7 empty] | Row Labels | PID
SOW | Eastern | Jabat |  |  |  |  | RFI | 21
BTR | 20 | 135 |  |  |  |  | CME | 5
Extend Pole |  | 45 |  |  |  |  | RFC | 7
Contine with Macro |  | 9 |  |  |  |  | SITAC | 20
Actual Macro | 1 | [5 empty] | SURVEY | 161
One Leg |  | 1 |  |  |  |  | NY DRM | 5
NY DRM |  | 5 |  |  |  |  | Prop.DROP | 25
Reloc to existing MTEL |  | 4 |  |  |  |  | DROP | 20
Relocation to other TP |  | 7 |  |  |  |  | Lock Trial | 45
Lock Trial | 10 | 52
Terminate | 7 | 13
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Summary
YEAR PLAN CAT | Plan ≤ 2025
ELD Update | (All)
Count of SITE ID BARU | Column Labels
Row Labels | R01 Sumbagut | R02 Sumbagsel | R10 Sumbagteng | R03 Jabotabek Inner | R12 Jabotabek Outer | R04 Jawa Barat | R05 Jawa Tengah | R06 Jawa Timur | R08 Kalimantan | R09 Sulawesi | Grand Total
RFI | 9 | 2 | 20 | 15 | 2 |  | 9 |  |  | 19 | 76 | Lanjut Target 2025
SRFI |  |  | 18 | [7 empty] | 18
CME |  |  | 4 |  | 1 | [5 empty] | 5
DRM | [7 empty] | 4 |  |  | 4
RFC |  |  | 2 | 2 | [6 empty] | 4
SITAC2 |  | 1 |  | 1 | 3 | [5 empty] | 5
SITAC |  |  | 15 | 20 | 3 | [5 empty] | 38 | Skema 3 Bulan
SIS |  |  | 7 | 13 | 6 |  | 1 |  | 2 |  | 29
Terminate | 3 | 20 | 14 | 19 | 10 | 2 |  | 1 | 7 | 3 | 79 | Cancel
Grand Total | 12 | 23 | 80 | 70 | 25 | 2 | 10 | 5 | 9 | 22 | 258
Skema ELD+3 Bulan
YEAR PLAN CAT | Plan ≤ 2025
ELD Update | (All)
Row Labels | Count of SITE ID BARU
RFI | 94
In SLA | 58
Out SLA | 36
NY RFI | 85
In SLA | 20
Out SLA | 65
Terminate | 79
Terminate | 79
Grand Total | 258

## Detail1
Details for Count of SITE ID BARU - Summary Progress: OG, YEAR PLAN CAT: Plan ≤ 2025, REGIONAL NAME: R08 Kalimantan
NO | AREA | REGIONAL NAME | REGIONAL_ID | SITE ID | SITE ID BARU | PID | PID Sales1 | PID Sales2 | True PID | SITE NAME | Longitude | Latitude | Status MKT | MKT | Tanggal MKT | SoW Actual | Mitra TP | TP GROUP | SLD Update | ELD Update | ELD+3 Bulan | RFI | Aging SLA | SLA Category | YEAR PLAN CAT | X | Deatail Status | Tipe Rescoping | General Status | Status Akhir | Summary Progress | Remark Akhir | Target RFI | SOW | remarks
410 | Area 4 | R08 Kalimantan | 8 | SMR436 | SMR436 |  | 24TS08Z0004 | #N/A | 24TS08Z0004 | MTH_GUBERNURANSMD2 | 117.1412 | -0.5017 | Non MKT | Non MKT |  |  | MITRATEL | Mitratel | 2015-10-28 | 2025-10-27 | 2026-01-25 | 2026-01-31 | -6 | Out SLA | Plan ≤ 2025 | #N/A | 08.SIS |  | SIS/SES | Hunting | OG | 4.12 Rehunting, hard kandidat, waiting arahan tsel regional, Lahan Fasum, tidak bisa peninggian 10, bisanya 3m, tetap di titik eksisting | Hold | BTR
409 | Area 4 | R08 Kalimantan | 8 | SMR461 | SMR461 |  | 24TS08Z0006 | #N/A | 24TS08Z0006 | MTH_UNMULSMD1 | 117.1515 | -0.46982 | Non MKT | Non MKT |  |  | MITRATEL | Mitratel | 2015-09-14 | 2025-09-13 | 2025-12-12 | 2026-01-31 | -50 | Out SLA | Plan ≤ 2025 | #N/A | 08.SIS |  | SITAC | BAN/BAK | OG | 4.12 BAN/BAK, menunggu tim asset negosiasi dengan pihak fakultas Unmul, Lahan Fasum, tidak bisa peninggian 10, bisanya 3m, tetap di titik eksisting | Hold | BTR

## Summary2
YEAR PLAN CAT | (Multiple Items) | [11 empty] | YEAR PLAN CAT | Plan ≥ 2026
Count of SITE ID BARU | Column Labels | [11 empty] | Count of SITE ID BARU | Column Labels |  |  | Count of SITE ID BARU | Column Labels
PROGRESS | SGUT | STENG | SSEL | JBTBK INNER | JBR | JTNG | JTM | KAL | SLWS | JBTBK Outer | (blank) | Grand Total | REGIONAL | MKT | Non MKT | Grand Total | PROGRESS | SGUT | SSEL | JBTK INNER | JBR | JTNG | JTM | KAL | SLWS | STENG | JBTK OUTER | Grand Total
RFI | 9 | 32 | 2 | 16 |  | 9 |  |  | 19 | 2 |  | 89 | R01 Sumbagut | 40 | 3 | 43 | Plan ≤ 2025 | 12 | 23 | 70 | 2 | 10 | 5 | 9 | 22 | 80 | 25 | 258
CME |  | 4 |  | 3 | [5 empty] | 1 |  | 8 | R02 Sumbagsel |  | 15 | 15 | RFI | 9 | 2 | 16 |  | 9 |  |  | 19 | 32 | 2 | 89
RFC |  | 15 |  | 6 | [7 empty] | 21 | R03 Jabotabek Inner | 148 | 51 | 199 | OG |  | 1 | 24 |  | 1 | 4 | 2 |  | 33 | 13 | 78
SITAC2 |  |  |  | 1 | [7 empty] | 1 | R06 Jawa Timur |  | 6 | 6 | Proposed Drop |  |  | 11 | [5 empty] | 1 |  | 12
SITAC |  | 13 | 1 | 10 |  |  |  | 1 |  | 4 |  | 29 | R08 Kalimantan |  | 2 | 2 | Terminate | 3 | 20 | 19 | 2 |  | 1 | 7 | 3 | 14 | 10 | 79
SIS/SES |  | 1 |  | 4 |  | 1 | 4 | 1 |  | 8 |  | 19 | R09 Sulawesi | 4 | 5 | 9 | Plan ≥ 2026 | 43 | 15 | 199 |  |  | 6 | 2 | 9 | 88 | 15 | 377
Terminate | 3 | 14 | 20 | 19 | 2 |  | 1 | 7 | 3 | 10 |  | 79 | R10 Sumbagteng | 81 | 7 | 88 | RFI | [8 empty] | 5 | 1 | 6
(blank) | [12 empty] | R12 Jabotabek Outer | 12 | 3 | 15 | OG | 43 | 15 | 199 |  |  | 6 | 2 | 9 | 83 | 14 | 371
DROP |  | 1 | [9 empty] | 1 | Grand Total | 285 | 92 | 377 | Grand Total | 55 | 38 | 269 | 2 | 10 | 11 | 11 | 31 | 168 | 40 | 635
Proposed Drop |  |  |  | 11 | [7 empty] | 11
Grand Total | 12 | 80 | 23 | 70 | 2 | 10 | 5 | 9 | 22 | 25 |  | 258

## Sheet4
AREA | Area 2
Column Labels
| PT AGUNGMAS PRIMA SEMPURNA | PT AJIAN TRI SUKSES | PT ANUGERAH SELARAS RAYA | PT CELEBES KONTRUKSINDO | PT CIPTA KARSA ANUGERAH SEMESTA | PT DENTRA MITRA ABADI | PT DESATRIA ALARD MANDIRI | PT DYEVA DIGITAL SELULAR | PT GEAF SOLUSIANDA PRATAMA | PT INDOJAR MULIA ABADI | PT INFRAKO DAYAMITRA | PT INTEGRA LINTAS TEKNOLOGI | PT INTERTEL MEDIA PRIMA | PT JAGANATA SAKTI UNGGUL | PT MANDAU JAYA KONTRINDO | PT MITRA SARANA KARYA BANGSA | PT MULTI BAGASANTI MAHDY | PT NAER TUNAS INDONESIA | PT PERSADA SOKKA TAMA | PT SAMANTA FIBRA ABADI | PT SINERGI REKTA DENTA | PT SUMBERSOLUSINDO HITECH | PT SURYASANTIKA INFRASTRUKTUR MEDIASELARAS | #N/A | Grand Total
Count of SITE ID | 9 | 4 | 4 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 11 | 4 | 5 | 7 | 5 | 6 | 6 | 4 | 10 | 6 | 12 | 11 | 4 | 134 | 274

## Sheet1
Type 1 | BTSH, change perangkat mitratel swab dengan perangkat Tsel
Type 5 | Rehight, Extend tower 3 - 10 m